## DocumentInformation
Document Information
Project Name |  |  | JLR Halewood – South Apron BIW Building
Project Code |  |  | HSA
Document Reference |  |  | HSA-RDG-XX-XX-L-S-000408
Task Team |  |  | Discpline |  | Structural Engineering
|  |  | Task Team Name |  | Ridge & Partners
|  |  | Task Team Code |  | RDG
Document Control
Revision | Suitability | Issue Date | Edited By | Approved By | Notes
P01 | S2 | 09.02.2023 | AA | BM
Reference Documents
Name |  |  | Document Reference |  |  | Revision

## TIDP
Classification | Information Container Code | Container ID Builder (from Picklists) | [7 empty] | Dependency |  | Level of Information Need (Information Container) |  |  | RIBA 2 |  | RIBA 3 |  | RIBA 4a |  | RIBA 4b |  | RIBA 5 |  | RIBA 6 |  | RIBA 7
|  | Project | Originator | Functional Breakdown | Spatial Breakdown | Form | Discipline | Number | Title | Dependent on | Late Dependency Risk | Scale | Format | Notes | Time Taken (Weeks) | Delivery Date | Time Taken (Weeks) | Delivery Date | Time Taken (Weeks) | Delivery Date | Time Taken (Weeks) | Delivery Date | Time Taken (Weeks) | Delivery Date | Time Taken (Weeks) | Delivery Date | Time Taken (Weeks) | Delivery Date
PM_40_40_01 : 2D plan drawings | HSA-RDG-01-01-D-S-0001 | HSA | RDG | 01 | 01 | D | S | 0001 | Level 01 Steelwork General Arrangment | Architectural Building Information | At least 28 days delay | 1:100 | .xlsx | Slab constructions noted | 2 | 2020-02-01 | 2 | 2020-02-01 | 2 | 2020-02-01 | 2 | 2020-02-01 | 2 | 2020-02-01 | 2 | 2020-02-01 | 2 | 2020-02-01
PM_40_35_83 : Structural engineering models | HSA-RDG-ZZ-XX-M-S-0001 | HSA | RDG | ZZ | XX | M | S | 0001 | Structural Model |  |  | NTS | .rvt | Foundations and floor slabs only | n/a |  | n/a |  | 6 | 2022-11-18 | 8 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z1-FN-D-S-0900 | HSA | RDG | Z1 | FN | D | S | 0900 | Piling GA - Zone 01 | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z2-FN-D-S-0901 | HSA | RDG | Z2 | FN | D | S | 0901 | Piling GA - Zone 02 | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z3-FN-D-S-0902 | HSA | RDG | Z3 | FN | D | S | 0902 | Piling GA - Zone 03 | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z4-FN-D-S-0903 | HSA | RDG | Z4 | FN | D | S | 0903 | Piling GA - Zone 04 | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z1-FN-D-S-0905 | HSA | RDG | Z1 | FN | D | S | 0905 | Foundation GA - Zone 01 | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z2-FN-D-S-0906 | HSA | RDG | Z2 | FN | D | S | 0906 | Foundation GA - Zone 02 | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z3-FN-D-S-0907 | HSA | RDG | Z3 | FN | D | S | 0907 | Foundation GA - Zone 03 | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z4-FN-D-S-0908 | HSA | RDG | Z4 | FN | D | S | 0908 | Foundation GA - Zone 04 | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z1-00-D-S-1000 | HSA | RDG | Z1 | 00 | D | S | 1000 | Ground Floor GA - Zone 1 | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z2-00-D-S-1001 | HSA | RDG | Z2 | 00 | D | S | 1001 | Ground Floor GA - Zone 2 | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z3-00-D-S-1002 | HSA | RDG | Z3 | 00 | D | S | 1002 | Ground Floor GA - Zone 3 | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z4-00-D-S-1003 | HSA | RDG | Z4 | 00 | D | S | 1003 | Ground Floor GA - Zone 4 | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z1-01-D-S-1010 | HSA | RDG | Z1 | 01 | D | S | 1010 | First Floor GA - Zone 1 | [9 empty] | 3 | 2022-11-18
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z2-01-D-S-1011 | HSA | RDG | Z2 | 01 | D | S | 1011 | First Floor GA - Zone 2 | [9 empty] | 3 | 2022-11-18
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z3-01-D-S-1012 | HSA | RDG | Z3 | 01 | D | S | 1012 | First Floor GA - Zone 3 | [9 empty] | 3 | 2022-11-18
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z4-01-D-S-1013 | HSA | RDG | Z4 | 01 | D | S | 1013 | First Floor GA - Zone 4 | [9 empty] | 3 | 2022-11-18
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z1-01-D-S-1015 | HSA | RDG | Z1 | 01 | D | S | 1015 | First Floor Slab GA - Zone 01 | [9 empty] | 3 | 2022-11-18
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z2-01-D-S-1016 | HSA | RDG | Z2 | 01 | D | S | 1016 | First Floor Slab GA - Zone 02 | [9 empty] | 3 | 2022-11-18
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z3-01-D-S-1017 | HSA | RDG | Z3 | 01 | D | S | 1017 | First Floor Slab GA - Zone 03 | [9 empty] | 3 | 2022-11-18
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z4-01-D-S-1018 | HSA | RDG | Z4 | 01 | D | S | 1018 | First Floor Slab GA - Zone 04 | [9 empty] | 3 | 2022-11-18
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z1-RF-D-S-1020 | HSA | RDG | Z1 | RF | D | S | 1020 | Roof GA - Zone 01 | [9 empty] | 3 | 2022-11-18
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z2-RF-D-S-1021 | HSA | RDG | Z2 | RF | D | S | 1021 | Roof GA - Zone 02 | [9 empty] | 3 | 2022-11-18
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z3-RF-D-S-1022 | HSA | RDG | Z3 | RF | D | S | 1022 | Roof GA - Zone 03 | [9 empty] | 3 | 2022-11-18
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z4-RF-D-S-1023 | HSA | RDG | Z4 | RF | D | S | 1023 | Roof GA - Zone 04 | [9 empty] | 3 | 2022-11-18
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z1-M1-D-S-1024 | HSA | RDG | Z1 | M1 | D | S | 1024 | Toilet Block Slab GA | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-Z2-ZZ-D-S-1025 | HSA | RDG | Z2 | ZZ | D | S | 1025 | Amenity Block Slab GAs | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_18 : Cross-section drawings | HSA-RDG-ZZ-ZZ-D-S-2000 | HSA | RDG | ZZ | ZZ | D | S | 2000 | Building Sections | [9 empty] | 3 | 2022-11-18
PM_40_40_01 : 2D plan drawings | HSA-RDG-ZZ-FN-D-S-2005 | HSA | RDG | ZZ | FN | D | S | 2005 | Pile Cap Details | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_18 : Cross-section drawings | HSA-RDG-ZZ-00-D-S-2006 | HSA | RDG | ZZ | 00 | D | S | 2006 | Ground Floor Details | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_18 : Cross-section drawings | HSA-RDG-ZZ-01-D-S-2007 | HSA | RDG | ZZ | 01 | D | S | 2007 | First Floor Slab Details | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-ZZ-FN-D-S-2020 | HSA | RDG | ZZ | FN | D | S | 2020 | Piling Schedule - Sheet 1 | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-ZZ-FN-D-S-2021 | HSA | RDG | ZZ | FN | D | S | 2021 | Piling Schedule - Sheet 2 | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-ZZ-FN-D-S-2022 | HSA | RDG | ZZ | FN | D | S | 2022 | Piling Schedule - Sheet 3 | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-ZZ-FN-D-S-2023 | HSA | RDG | ZZ | FN | D | S | 2023 | Piling Schedule - Sheet 4 | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_27 : Elevation drawings | HSA-RDG-ZZ-ZZ-D-S-2500 | HSA | RDG | ZZ | ZZ | D | S | 2500 | Building Elevations Sheet 1 | [9 empty] | 3 | 2022-11-18
PM_40_40_27 : Elevation drawings | HSA-RDG-ZZ-ZZ-D-S-2501 | HSA | RDG | ZZ | ZZ | D | S | 2501 | Building Elevations Sheet 2 | [9 empty] | 3 | 2022-11-18
PM_40_40_01 : 2D plan drawings | HSA-RDG-ZZ-FN-D-S-3000 | HSA | RDG | ZZ | FN | D | S | 3000 | Foundation Loads | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-ZZ-00-D-S-3000 | HSA | RDG | ZZ | 00 | D | S | 3000 | Ground Floor Loading Plan | [9 empty] | 3 | 2022-11-18 | 4 | 2023-01-27
PM_40_40_01 : 2D plan drawings | HSA-RDG-ZZ-01-D-S-3001 | HSA | RDG | ZZ | 01 | D | S | 3001 | First Floor Loading Plan | [9 empty] | 3 | 2022-11-18
PM_40_40_01 : 2D plan drawings | HSA-RDG-ZZ-RF-D-S-3002 | HSA | RDG | ZZ | RF | D | S | 3002 | Roof Loading Plan | [9 empty] | 3 | 2022-11-18
| HSA-RDG-XX-XX-SP-S-0001 | HSA | RDG | XX | XX | SP | S | 0001 | Piling Specification | [11 empty] | 2 | 2023-01-27
| HSA-RDG-XX-XX-SP-S-0002 | HSA | RDG | XX | XX | SP | S | 0002 | Concrete Specification | [11 empty] | 2 | 2023-01-27
| HSA-RDG-XX-XX-SP-S-0003 | HSA | RDG | XX | XX | SP | S | 0003 | Upper-Floor Decking Specification | [11 empty] | 2 | 2023-01-27
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This column is formula generated
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This information is filled in the Document Information tab
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This information is filled in the Document Information tab

## Picklists
Project | Project Description | Originator | Originator Description | Zone | Functional Breakdown (Zone) Description | Levels | Spatial Breakdown/Level Description | Type | Type Description | Role | Role Description | Column1 | Number | Number Description | Format | Milestone | Status | Status (project override) | Description
HSA | XXXXXXX | RDG | Ridge and Partners | ZZ | Multiple Zones | ZZ | Multiple levels | DR | Drawing | A | Architecture | A | 0000 | BS EN ISO 19650‑2:2018 NA.3.8 Number | .bcf | 1 | S0 | S0 | Information container being developed within a task team
|  | XXX | XXXXXXX | XX | No applicable zone e.g. Not spatial information | XX | No applicable levels e.g. Not spatial information | G | Diagram | B | Building Surveying | B |  |  | .docx | 2 | S1 | S1 | Information containers that are suitable for geometrical and/or non-geometrical coordination within a delivery team
|  | XXX | XXXXXXX | 00 | Zone 0 | 00 | Ground Floor | I | Image | C | Civil Engineering | C |  |  | .dwf | 3 | S2 | S2 | Information containers that are suitable for information/ reference by other task teams within a delivery team
|  | XXX | XXXXXXX | Z1 | Zone 1 | 01 | First Floor | L | List | D | Demolition/dismantling | D |  |  | .dwg | 4 | S3 | S3 | Information containers that are suitable for review and comment within a delivery team
|  | XXX | XXXXXXX | Z2 | Zone 2 | 02 | Second Floor | M3 | Model | E | Electrical Engineering | E |  |  | .dwt | 5 | S4 | S4 | Information containers that are suitable for review and authorization by a lead appointed party
|  | XXX | XXXXXXX | Z3 | Zone 3 | 03 | Third Floor | T | Textual | F | Facilities/asset management | F |  |  | .exe | 6 | S5 | S5 | Information containers suitable for review and acceptance by an appointing party (
|  | XXX | XXXXXXX | Z4 | Zone 4 | 04 | Fourth Floor | Sp | Schedule | G | Ground engineering | G |  |  | .ifc | 7 | A1 | A1 | Information containers where there are no comments from the party being invited to either: • authorize them (if they are in response to a lead appointed party exchange information requirement); or • accept them (if they are in response to an appointing party exchange information requirement) NOTE 1 ‘n’ relates to the work stages defined within BS 8536‑1:2015 and BS 8536‑2:2016, unless an alternative approach has been documented in the project’s information standard.
|  |  |  | 05 | Zone 5 | 05 | Fifth Floor | V | Video/ Audio | H | Highways and transport engineering | H |  |  | .jpg |  | A2 | A2
|  |  |  | 06 | Zone 6 | 06 | Sixth Floor |  |  | L | Landscape Architecture | L |  |  | .json |  | A3 | A3
|  |  |  | 07 | Zone 7 | 07 | Seventh Floor |  |  | M | Mechanical Engineering | M |  |  | .mp4 |  | A4 | A4
|  |  |  | 08 | Zone 8 | 08 | Eighth Floor |  |  | O | Other discipline | O |  |  | .nwc |  | A5 | A5
|  |  |  | 09 | Zone 9 | 09 | Ninth Floor |  |  | P | Public health engineering | P |  |  | .nwd |  | A6 | A6
|  |  |  | 10 | Zone 10 | 10 | Tenth Floor |  |  | Q | Quantity surveying / Cost Consultancy | Q |  |  | .nwf |  | A7 | A7
|  |  |  | 11 | Zone 11 | 11 | Eleventh Floor |  |  | R | Project Management | R |  |  | .pdf
|  |  |  | 12 | Zone 12 | 12 | Twelfth Floor |  |  | S | Structural Engineering | S |  |  | .pla
|  |  |  | 13 | Zone 13 | 13 | Thirteenth Floor |  |  | T | Town and country planning and building control | T |  |  | .pln
|  |  |  | 14 | Zone 14 | 14 | Fourteenth Floor |  |  | W | Water engineering | W |  |  | .png
|  |  |  | 15 | Zone 15 | 15 | Fifteenth Floor |  |  | X | Non-Discipline Specific or Not Applicable | X |  |  | .pptx
|  |  |  | 16 | Zone 16 | 16 | Sixteenth Floor |  |  | Y | Topographical Surveying | Y |  |  | .rvt
|  |  |  | 17 | Zone 17 | 17 | Seventeenth Floor |  |  | Z | Multiple Disciplines | Z |  |  | .smc
|  |  |  | 18 | Zone 18 | 18 | Eighteenth Floor |  |  |  |  | 0 |  |  | .smv
|  |  |  | 19 | Zone 19 | 19 | Nineteenth Floor | [7 empty] | .txt
|  |  |  | 20 | Zone 20 | 20 | Twentieth Floor | [7 empty] | .wbk
[6 empty] | 21 | Twenty-first Floor | [7 empty] | .xlsx
[6 empty] | 22 | Twenty-second Floor | [7 empty] | .xml
[6 empty] | 23 | Twenty-third Floor
[6 empty] | 24 | Twenty-fourth Floor
[6 empty] | 25 | Twenty-fifth Floor
[6 empty] | 26 | Twenty-sixth Floor
[6 empty] | 27 | Twenty-seventh Floor
[6 empty] | 28 | Twenty-eighth Floor
[6 empty] | 29 | Twenty-ninth Floor
[6 empty] | 30 | Thirtieth Floor
[6 empty] | B1 | Basement First
[6 empty] | B2 | Basement Second
[6 empty] | M0 | Mezzanine (Over Ground)
[6 empty] | M1 | Mezzanine (Over First)
[6 empty] | LG | Lower Ground Floor
[6 empty] | UG | Upper Ground Floor
[6 empty] | RF | Roof
[6 empty] | R1 | Roof 1
[6 empty] | R2 | Roof 2
[6 empty] | R3 | Roof 3
[6 empty] | FN | Foundations
[6 empty] | F1 | Foundations 1
[6 empty] | F2 | Foundations 2
[6 empty] | F3 | Foundations 3

## PM Classification
_airtableRecordId | _airtableRecordCreatedAt | Code | Title | Version | Current | Uniclass | Name | Table | ID
recZ3oMSJCbEsQiOT | 2021-06-14T07:47:08.000Z | PM_10 | Project information | [List] | TRUE | PM_10 : Project information | PM_10 : Project information | Project Management | recZ3oMSJCbEsQiOT
recih0xboK51NdN87 | 2021-06-14T07:47:08.000Z | PM_10_10 | Project | [List] | TRUE | PM_10_10 : Project | PM_10_10 : Project | Project Management | recih0xboK51NdN87
rec4hgHDKYUZqSyyj | 2021-06-14T07:47:08.000Z | PM_10_10_60 | Project description | [List] | TRUE | PM_10_10_60 : Project description | PM_10_10_60 : Project description | Project Management | rec4hgHDKYUZqSyyj
recYYyYWxi6U9Bbsd | 2021-06-14T07:47:08.000Z | PM_10_20 | Client requirements | [List] | TRUE | PM_10_20 : Client requirements | PM_10_20 : Client requirements | Project Management | recYYyYWxi6U9Bbsd
rec6UOJ7PZ3WDU8XI | 2021-06-14T07:47:08.000Z | PM_10_20_03 | Appointment document | [List] | TRUE | PM_10_20_03 : Appointment document | PM_10_20_03 : Appointment document | Project Management | rec6UOJ7PZ3WDU8XI
recIZf4CbBfv4y6ZE | 2021-06-14T07:47:08.000Z | PM_10_20_07 | Brief | [List] | TRUE | PM_10_20_07 : Brief | PM_10_20_07 : Brief | Project Management | recIZf4CbBfv4y6ZE
recZqRnibMlMxGMho | 2021-06-14T07:47:08.000Z | PM_10_20_09 | Buildability statement | [List] | TRUE | PM_10_20_09 : Buildability statement | PM_10_20_09 : Buildability statement | Project Management | recZqRnibMlMxGMho
rec1luHAT1BDzSoI1 | 2021-06-14T07:47:08.000Z | PM_10_20_11 | Carbon road map | [List] | TRUE | PM_10_20_11 : Carbon road map | PM_10_20_11 : Carbon road map | Project Management | rec1luHAT1BDzSoI1
recUxFSheEyDsiqmM | 2021-11-11T11:10:56.000Z | PM_10_20_13 | Community analysis | [List] | TRUE | PM_10_20_13 : Community analysis | PM_10_20_13 : Community analysis | Project Management | recUxFSheEyDsiqmM
reck10URW9JWHtoAm | 2021-06-14T07:47:08.000Z | PM_10_20_14 | Community and tenant liaison plan | [List] | TRUE | PM_10_20_14 : Community and tenant liaison plan | PM_10_20_14 : Community and tenant liaison plan | Project Management | reck10URW9JWHtoAm
rec1wZE4sZ9bbw4Fw | 2021-06-14T07:47:08.000Z | PM_10_20_16 | Construction industry registration scheme requirements | [List] | TRUE | PM_10_20_16 : Construction industry registration scheme requirements | PM_10_20_16 : Construction industry registration scheme requirements | Project Management | rec1wZE4sZ9bbw4Fw
recUZN6I9DQlp7gm0 | 2021-06-14T07:47:08.000Z | PM_10_20_17 | Core requirements statement | [List] | TRUE | PM_10_20_17 : Core requirements statement | PM_10_20_17 : Core requirements statement | Project Management | recUZN6I9DQlp7gm0
recGLZj5ylMJkY0KD | 2021-06-14T07:47:08.000Z | PM_10_20_18 | Cost benefit analysis | [List] | TRUE | PM_10_20_18 : Cost benefit analysis | PM_10_20_18 : Cost benefit analysis | Project Management | recGLZj5ylMJkY0KD
recE5q0iT0CTx7nJY | 2021-11-11T11:10:56.000Z | PM_10_20_21 | Data quality plans | [List] | TRUE | PM_10_20_21 : Data quality plans | PM_10_20_21 : Data quality plans | Project Management | recE5q0iT0CTx7nJY
recaMRCTNlAEoX9CP | 2021-06-14T07:47:08.000Z | PM_10_20_26 | Environmental policy | [List] | TRUE | PM_10_20_26 : Environmental policy | PM_10_20_26 : Environmental policy | Project Management | recaMRCTNlAEoX9CP
recwvTkKkco36E0kV | 2021-06-14T07:47:08.000Z | PM_10_20_27 | Environmental reporting information | [List] | TRUE | PM_10_20_27 : Environmental reporting information | PM_10_20_27 : Environmental reporting information | Project Management | recwvTkKkco36E0kV
recIrThJIqRiIR0X8 | 2021-06-14T07:47:08.000Z | PM_10_20_28 | Exchange information requirements | [List] | TRUE | PM_10_20_28 : Exchange information requirements | PM_10_20_28 : Exchange information requirements | Project Management | recIrThJIqRiIR0X8
rec07N3t73sNdOw8e | 2021-06-14T07:47:08.000Z | PM_10_20_30 | Feasibility study | [List] | TRUE | PM_10_20_30 : Feasibility study | PM_10_20_30 : Feasibility study | Project Management | rec07N3t73sNdOw8e
recXEcpqoGpyu3wIe | 2021-06-14T07:47:08.000Z | PM_10_20_69 | Quality plan | [List] | TRUE | PM_10_20_69 : Quality plan | PM_10_20_69 : Quality plan | Project Management | recXEcpqoGpyu3wIe
recrdkztJVuGgTknb | 2021-06-14T07:47:08.000Z | PM_10_20_75 | Stakeholder engagement plan | [List] | TRUE | PM_10_20_75 : Stakeholder engagement plan | PM_10_20_75 : Stakeholder engagement plan | Project Management | recrdkztJVuGgTknb
recp4sZmo1T0RH48A | 2021-06-14T07:47:08.000Z | PM_10_20_82 | Statement of requirements | [List] | TRUE | PM_10_20_82 : Statement of requirements | PM_10_20_82 : Statement of requirements | Project Management | recp4sZmo1T0RH48A
recU4cFa95vF18vOk | 2021-06-14T07:47:08.000Z | PM_10_20_84 | Statement of security requirements | [List] | TRUE | PM_10_20_84 : Statement of security requirements | PM_10_20_84 : Statement of security requirements | Project Management | recU4cFa95vF18vOk
recZZ6ILjnszCCnCK | 2021-06-14T07:47:08.000Z | PM_10_20_86 | Sustainable development engagement plan | [List] | TRUE | PM_10_20_86 : Sustainable development engagement plan | PM_10_20_86 : Sustainable development engagement plan | Project Management | recZZ6ILjnszCCnCK
recXIhzV2FsM32ZgZ | 2021-06-14T07:47:08.000Z | PM_10_20_90 | Technical statement of requirements (TSOR) | [List] | TRUE | PM_10_20_90 : Technical statement of requirements (TSOR) | PM_10_20_90 : Technical statement of requirements (TSOR) | Project Management | recXIhzV2FsM32ZgZ
recboQUaa1ATHR5xW | 2021-06-14T07:47:08.000Z | PM_10_20_92 | User requirement document | [List] | TRUE | PM_10_20_92 : User requirement document | PM_10_20_92 : User requirement document | Project Management | recboQUaa1ATHR5xW
recKpqVIc9jmWbrjD | 2021-06-14T07:47:08.000Z | PM_10_80 | Space management requirements | [List] | TRUE | PM_10_80 : Space management requirements | PM_10_80 : Space management requirements | Project Management | recKpqVIc9jmWbrjD
recHAwGwcN5t94AWx | 2021-06-14T07:47:08.000Z | PM_10_80_10 | Accommodation and layout plan | [List] | TRUE | PM_10_80_10 : Accommodation and layout plan | PM_10_80_10 : Accommodation and layout plan | Project Management | recHAwGwcN5t94AWx
recg5VsWAGZAete0V | 2021-06-14T07:47:08.000Z | PM_10_80_75 | Space design | [List] | TRUE | PM_10_80_75 : Space design | PM_10_80_75 : Space design | Project Management | recg5VsWAGZAete0V
rec1ccVIQoAuFrPc5 | 2021-06-14T07:47:08.000Z | PM_10_80_80 | Space plan | [List] | TRUE | PM_10_80_80 : Space plan | PM_10_80_80 : Space plan | Project Management | rec1ccVIQoAuFrPc5
reccnf4RwvYIj0jqI | 2021-06-14T07:47:08.000Z | PM_10_80_85 | Space standard | [List] | TRUE | PM_10_80_85 : Space standard | PM_10_80_85 : Space standard | Project Management | reccnf4RwvYIj0jqI
recSNhQc1f5KJFJ12 | 2021-06-14T07:47:08.000Z | PM_30 | Site, ground and environmental information | [List] | TRUE | PM_30 : Site, ground and environmental information | PM_30 : Site, ground and environmental information | Project Management | recSNhQc1f5KJFJ12
rec7PYSq8Y8AtFosr | 2021-06-14T07:47:08.000Z | PM_30_10 | Site survey information | [List] | TRUE | PM_30_10 : Site survey information | PM_30_10 : Site survey information | Project Management | rec7PYSq8Y8AtFosr
rechWPUZFafteuYOO | 2021-06-14T07:47:08.000Z | PM_30_10_15 | Condition survey information | [List] | TRUE | PM_30_10_15 : Condition survey information | PM_30_10_15 : Condition survey information | Project Management | rechWPUZFafteuYOO
recbWPpK1P7IwRzy9 | 2021-06-14T07:47:08.000Z | PM_30_10_22 | Dimensional information | [List] | TRUE | PM_30_10_22 : Dimensional information | PM_30_10_22 : Dimensional information | Project Management | recbWPpK1P7IwRzy9
rec2YuZ27vRKLoRIn | 2022-01-28T12:20:29.000Z | PM_30_10_26 | Electrical power quality asessment information | [List] | TRUE | PM_30_10_26 : Electrical power quality asessment information | PM_30_10_26 : Electrical power quality asessment information | Project Management | rec2YuZ27vRKLoRIn
recjBZLvCPDKnFsyh | 2021-06-14T07:47:08.000Z | PM_30_10_28 | Existing structure information | [List] | TRUE | PM_30_10_28 : Existing structure information | PM_30_10_28 : Existing structure information | Project Management | recjBZLvCPDKnFsyh
rec0yBgrY2ZOxyiqM | 2021-11-11T11:10:56.000Z | PM_30_10_36 | Historic site survey information | [List] | TRUE | PM_30_10_36 : Historic site survey information | PM_30_10_36 : Historic site survey information | Project Management | rec0yBgrY2ZOxyiqM
rec10Fl11fY0raDIz | 2021-06-14T07:47:08.000Z | PM_30_10_37 | Historic building survey information | [List] | TRUE | PM_30_10_37 : Historic building survey information | PM_30_10_37 : Historic building survey information | Project Management | rec10Fl11fY0raDIz
recNC3LX9wLpmD5sj | 2021-06-14T07:47:08.000Z | PM_30_10_38 | Hydraulic information | [List] | TRUE | PM_30_10_38 : Hydraulic information | PM_30_10_38 : Hydraulic information | Project Management | recNC3LX9wLpmD5sj
recEiHDCqMn43Dc5F | 2021-06-14T07:47:08.000Z | PM_30_10_39 | Hydrology information | [List] | TRUE | PM_30_10_39 : Hydrology information | PM_30_10_39 : Hydrology information | Project Management | recEiHDCqMn43Dc5F
rec8Ecgmfnga54GaF | 2021-06-14T07:47:08.000Z | PM_30_10_47 | Land registration information | [List] | TRUE | PM_30_10_47 : Land registration information | PM_30_10_47 : Land registration information | Project Management | rec8Ecgmfnga54GaF
recpN1EFBCM0yr6BC | 2021-06-14T07:47:08.000Z | PM_30_10_58 | Mapping information | [List] | TRUE | PM_30_10_58 : Mapping information | PM_30_10_58 : Mapping information | Project Management | recpN1EFBCM0yr6BC
recnmN088KbwkPilS | 2021-06-14T07:47:08.000Z | PM_30_10_60 | Party wall survey information | [List] | TRUE | PM_30_10_60 : Party wall survey information | PM_30_10_60 : Party wall survey information | Project Management | recnmN088KbwkPilS
recEN4VbSc1PHfuwt | 2021-06-14T07:47:08.000Z | PM_30_10_76 | Scan survey information | [List] | TRUE | PM_30_10_76 : Scan survey information | PM_30_10_76 : Scan survey information | Project Management | recEN4VbSc1PHfuwt
recIGBlkIFNfc0piP | 2021-06-14T07:47:08.000Z | PM_30_10_78 | Site abnormal information | [List] | TRUE | PM_30_10_78 : Site abnormal information | PM_30_10_78 : Site abnormal information | Project Management | recIGBlkIFNfc0piP
rec9KC1c86V4U9I3r | 2021-06-14T07:47:08.000Z | PM_30_10_80 | Site boundary information | [List] | TRUE | PM_30_10_80 : Site boundary information | PM_30_10_80 : Site boundary information | Project Management | rec9KC1c86V4U9I3r
recQImVequCcmPlMX | 2021-11-11T11:10:56.000Z | PM_30_10_85 | Structural survey information | [List] | TRUE | PM_30_10_85 : Structural survey information | PM_30_10_85 : Structural survey information | Project Management | recQImVequCcmPlMX
rec9erTEQwTFkPUiP | 2021-06-14T07:47:08.000Z | PM_30_10_88 | Topographical survey information | [List] | TRUE | PM_30_10_88 : Topographical survey information | PM_30_10_88 : Topographical survey information | Project Management | rec9erTEQwTFkPUiP
rec5V6K54YJdj4QZA | 2021-06-14T07:47:08.000Z | PM_30_10_90 | Transport feasibility survey information | [List] | TRUE | PM_30_10_90 : Transport feasibility survey information | PM_30_10_90 : Transport feasibility survey information | Project Management | rec5V6K54YJdj4QZA
rec1QEn0lQ8Kvc4uG | 2021-06-14T07:47:08.000Z | PM_30_10_93 | Utilities and services survey information | [List] | TRUE | PM_30_10_93 : Utilities and services survey information | PM_30_10_93 : Utilities and services survey information | Project Management | rec1QEn0lQ8Kvc4uG
rec2pDF2aSmbOWNtX | 2021-06-14T07:47:08.000Z | PM_30_20 | Ground investigation and survey reports | [List] | TRUE | PM_30_20 : Ground investigation and survey reports | PM_30_20 : Ground investigation and survey reports | Project Management | rec2pDF2aSmbOWNtX
recgBq7zcXCigfGuO | 2021-06-14T07:47:08.000Z | PM_30_20_02 | Archaeological survey report | [List] | TRUE | PM_30_20_02 : Archaeological survey report | PM_30_20_02 : Archaeological survey report | Project Management | recgBq7zcXCigfGuO
recKap11FsQIzIrMS | 2021-06-14T07:47:08.000Z | PM_30_20_10 | Geological survey report | [List] | TRUE | PM_30_20_10 : Geological survey report | PM_30_20_10 : Geological survey report | Project Management | recKap11FsQIzIrMS
recsaGLknBMAmkG1j | 2021-06-14T07:47:08.000Z | PM_30_20_17 | Contaminated land survey report | [List] | TRUE | PM_30_20_17 : Contaminated land survey report | PM_30_20_17 : Contaminated land survey report | Project Management | recsaGLknBMAmkG1j
rechCxH6eaadvLOM5 | 2021-06-14T07:47:08.000Z | PM_30_20_24 | Underground services survey report | [List] | TRUE | PM_30_20_24 : Underground services survey report | PM_30_20_24 : Underground services survey report | Project Management | rechCxH6eaadvLOM5
recSY8z7dbKmILimQ | 2021-06-14T07:47:08.000Z | PM_30_20_33 | Geotechnical survey report | [List] | TRUE | PM_30_20_33 : Geotechnical survey report | PM_30_20_33 : Geotechnical survey report | Project Management | recSY8z7dbKmILimQ
rec5vJYQLuy3WbCJ0 | 2021-06-14T07:47:08.000Z | PM_30_20_35 | Ground investigation report | [List] | TRUE | PM_30_20_35 : Ground investigation report | PM_30_20_35 : Ground investigation report | Project Management | rec5vJYQLuy3WbCJ0
recV1vkt4dCoAsPlm | 2021-06-14T07:47:08.000Z | PM_30_20_46 | Land quality assessment report | [List] | TRUE | PM_30_20_46 : Land quality assessment report | PM_30_20_46 : Land quality assessment report | Project Management | recV1vkt4dCoAsPlm
recxUo0d2LLvClrQp | 2021-06-14T07:47:08.000Z | PM_30_20_89 | Topographic survey report | [List] | TRUE | PM_30_20_89 : Topographic survey report | PM_30_20_89 : Topographic survey report | Project Management | recxUo0d2LLvClrQp
recoVCOO8AS5VGWS1 | 2021-06-14T07:47:08.000Z | PM_30_20_92 | Underground drainage closed-circuit television (CCTV) condition survey information | [List] | TRUE | PM_30_20_92 : Underground drainage closed-circuit television (CCTV) condition survey information | PM_30_20_92 : Underground drainage closed-circuit television (CCTV) condition survey information | Project Management | recoVCOO8AS5VGWS1
recUO8JEGYryogjXg | 2021-06-14T07:47:08.000Z | PM_30_30 | Environmental information | [List] | TRUE | PM_30_30 : Environmental information | PM_30_30 : Environmental information | Project Management | recUO8JEGYryogjXg
recTZNFIJx7Y74jRX | 2021-06-14T07:47:08.000Z | PM_30_30_02 | Acoustic survey information | [List] | TRUE | PM_30_30_02 : Acoustic survey information | PM_30_30_02 : Acoustic survey information | Project Management | recTZNFIJx7Y74jRX
reccbldyHinRkaso6 | 2021-06-14T07:47:08.000Z | PM_30_30_03 | Air quality survey information | [List] | TRUE | PM_30_30_03 : Air quality survey information | PM_30_30_03 : Air quality survey information | Project Management | reccbldyHinRkaso6
rec9BeqVZQaRUlTdH | 2021-06-14T07:47:08.000Z | PM_30_30_04 | Arboricultural survey information | [List] | TRUE | PM_30_30_04 : Arboricultural survey information | PM_30_30_04 : Arboricultural survey information | Project Management | rec9BeqVZQaRUlTdH
recIW82ijEgKYXdwU | 2021-11-11T11:10:56.000Z | PM_30_30_08 | Broad scale model | [List] | TRUE | PM_30_30_08 : Broad scale model | PM_30_30_08 : Broad scale model | Project Management | recIW82ijEgKYXdwU
rec4YYvrNzI6pIz98 | 2021-06-14T07:47:08.000Z | PM_30_30_10 | Carbon calculation report | [List] | TRUE | PM_30_30_10 : Carbon calculation report | PM_30_30_10 : Carbon calculation report | Project Management | rec4YYvrNzI6pIz98
recyhpxBIFNnOF3uo | 2021-06-14T07:47:08.000Z | PM_30_30_15 | Coastal model | [List] | TRUE | PM_30_30_15 : Coastal model | PM_30_30_15 : Coastal model | Project Management | recyhpxBIFNnOF3uo
recgxCJlW95ZnOazL | 2021-06-14T07:47:08.000Z | PM_30_30_23 | Drainage model | [List] | TRUE | PM_30_30_23 : Drainage model | PM_30_30_23 : Drainage model | Project Management | recgxCJlW95ZnOazL
recwmGCkEoUnf2hcZ | 2021-11-11T11:10:56.000Z | PM_30_30_24 | Environmental constraints report | [List] | TRUE | PM_30_30_24 : Environmental constraints report | PM_30_30_24 : Environmental constraints report | Project Management | recwmGCkEoUnf2hcZ
reci1jXVbEglG1KDy | 2021-06-14T07:47:08.000Z | PM_30_30_25 | Ecology survey report | [List] | TRUE | PM_30_30_25 : Ecology survey report | PM_30_30_25 : Ecology survey report | Project Management | reci1jXVbEglG1KDy
recN2V7PR6dT2zCYs | 2021-06-14T07:47:08.000Z | PM_30_30_26 | Environmental action report | [List] | TRUE | PM_30_30_26 : Environmental action report | PM_30_30_26 : Environmental action report | Project Management | recN2V7PR6dT2zCYs
rec4b58msSCUsaquX | 2021-06-14T07:47:08.000Z | PM_30_30_27 | Environmental impact report | [List] | TRUE | PM_30_30_27 : Environmental impact report | PM_30_30_27 : Environmental impact report | Project Management | rec4b58msSCUsaquX
recaqTASHFKgdhOV3 | 2021-06-14T07:47:08.000Z | PM_30_30_28 | Environmental survey report | [List] | TRUE | PM_30_30_28 : Environmental survey report | PM_30_30_28 : Environmental survey report | Project Management | recaqTASHFKgdhOV3
recpcVvn04hAC7zQZ | 2021-06-14T07:47:08.000Z | PM_30_30_29 | Flood risk assessment report | [List] | TRUE | PM_30_30_29 : Flood risk assessment report | PM_30_30_29 : Flood risk assessment report | Project Management | recpcVvn04hAC7zQZ
rec7NVyX20DFusRpb | 2021-06-14T07:47:08.000Z | PM_30_30_30 | Flood forecasting model | [List] | TRUE | PM_30_30_30 : Flood forecasting model | PM_30_30_30 : Flood forecasting model | Project Management | rec7NVyX20DFusRpb
reciyxvyloTuGbR5h | 2021-11-11T11:10:56.000Z | PM_30_30_31 | Flood protection information | [List] | TRUE | PM_30_30_31 : Flood protection information | PM_30_30_31 : Flood protection information | Project Management | reciyxvyloTuGbR5h
recGaOBO53zFs5x85 | 2021-06-14T07:47:08.000Z | PM_30_30_32 | Fluvial flow model | [List] | TRUE | PM_30_30_32 : Fluvial flow model | PM_30_30_32 : Fluvial flow model | Project Management | recGaOBO53zFs5x85
recv6gNS7Zgz2fbzs | 2021-11-11T11:10:56.000Z | PM_30_30_33 | Flood simulation model | [List] | TRUE | PM_30_30_33 : Flood simulation model | PM_30_30_33 : Flood simulation model | Project Management | recv6gNS7Zgz2fbzs
recHQDwxiXuqUwLPE | 2021-06-14T07:47:08.000Z | PM_30_30_39 | Hydrological model | [List] | TRUE | PM_30_30_39 : Hydrological model | PM_30_30_39 : Hydrological model | Project Management | recHQDwxiXuqUwLPE
recK3EeJt7u3mPnB6 | 2021-06-14T07:47:08.000Z | PM_30_30_41 | Integrated catchment model | [List] | TRUE | PM_30_30_41 : Integrated catchment model | PM_30_30_41 : Integrated catchment model | Project Management | recK3EeJt7u3mPnB6
recAVXaPv2p8FR3dy | 2021-11-11T11:10:56.000Z | PM_30_30_46 | Landscape impact assessment | [List] | TRUE | PM_30_30_46 : Landscape impact assessment | PM_30_30_46 : Landscape impact assessment | Project Management | recAVXaPv2p8FR3dy
recA2GtPahplCIDKD | 2021-06-14T07:47:08.000Z | PM_30_30_51 | Measured building survey information | [List] | TRUE | PM_30_30_51 : Measured building survey information | PM_30_30_51 : Measured building survey information | Project Management | recA2GtPahplCIDKD
recUq2KyVzFl7rXiH | 2021-11-11T11:10:56.000Z | PM_30_30_53 | Model calibration information | [List] | TRUE | PM_30_30_53 : Model calibration information | PM_30_30_53 : Model calibration information | Project Management | recUq2KyVzFl7rXiH
rec61dGi0jJLnjwy9 | 2021-06-14T07:47:08.000Z | PM_30_30_58 | Operational waste management plan | [List] | TRUE | PM_30_30_58 : Operational waste management plan | PM_30_30_58 : Operational waste management plan | Project Management | rec61dGi0jJLnjwy9
recx1jtuKVSPCUqoY | 2021-06-14T07:47:08.000Z | PM_30_30_65 | Pluvial flow model | [List] | TRUE | PM_30_30_65 : Pluvial flow model | PM_30_30_65 : Pluvial flow model | Project Management | recx1jtuKVSPCUqoY
recvS7x3487xuB9ST | 2021-06-14T07:47:08.000Z | PM_30_30_72 | Road safety audit report | [List] | TRUE | PM_30_30_72 : Road safety audit report | PM_30_30_72 : Road safety audit report | Project Management | recvS7x3487xuB9ST
recHxOcVW9svUGYII | 2021-06-14T07:47:08.000Z | PM_30_30_75 | Seismic survey report | [List] | TRUE | PM_30_30_75 : Seismic survey report | PM_30_30_75 : Seismic survey report | Project Management | recHxOcVW9svUGYII
recR0Im9Bzfj9LP0M | 2021-06-14T07:47:08.000Z | PM_30_30_85 | Sustainability information | [List] | TRUE | PM_30_30_85 : Sustainability information | PM_30_30_85 : Sustainability information | Project Management | recR0Im9Bzfj9LP0M
recXr8cVkQdZnZhnZ | 2021-06-14T07:47:08.000Z | PM_30_30_86 | Thermal and environmental model | [List] | TRUE | PM_30_30_86 : Thermal and environmental model | PM_30_30_86 : Thermal and environmental model | Project Management | recXr8cVkQdZnZhnZ
recA55EtHazLGCXkG | 2021-06-14T07:47:08.000Z | PM_30_30_87 | Tidal information | [List] | TRUE | PM_30_30_87 : Tidal information | PM_30_30_87 : Tidal information | Project Management | recA55EtHazLGCXkG
recoZFaDL95xljXGa | 2021-06-14T07:47:08.000Z | PM_30_30_88 | Tidal and coastal boundary information | [List] | TRUE | PM_30_30_88 : Tidal and coastal boundary information | PM_30_30_88 : Tidal and coastal boundary information | Project Management | recoZFaDL95xljXGa
recyZ7tUjJ2SiHDwe | 2021-06-14T07:47:08.000Z | PM_30_30_96 | Water management information | [List] | TRUE | PM_30_30_96 : Water management information | PM_30_30_96 : Water management information | Project Management | recyZ7tUjJ2SiHDwe
rec9Sv9E7LXqTlJZU | 2021-11-11T11:10:56.000Z | PM_30_30_97 | Water quality assessment information | [List] | TRUE | PM_30_30_97 : Water quality assessment information | PM_30_30_97 : Water quality assessment information | Project Management | rec9Sv9E7LXqTlJZU
recYtHCmxjsFOztTC | 2021-06-14T07:47:08.000Z | PM_30_30_98 | Weather and climate information | [List] | TRUE | PM_30_30_98 : Weather and climate information | PM_30_30_98 : Weather and climate information | Project Management | recYtHCmxjsFOztTC
recOtVgQL6B1ZqSLQ | 2021-06-14T07:47:08.000Z | PM_30_40 | Hazardous substances information | [List] | TRUE | PM_30_40 : Hazardous substances information | PM_30_40 : Hazardous substances information | Project Management | recOtVgQL6B1ZqSLQ
reclB1OGOUXJUi5KT | 2021-06-14T07:47:08.000Z | PM_30_40_06 | Asbestos survey report | [List] | TRUE | PM_30_40_06 : Asbestos survey report | PM_30_40_06 : Asbestos survey report | Project Management | reclB1OGOUXJUi5KT
recpmNLhYb6s08aiG | 2021-06-14T07:47:08.000Z | PM_30_40_10 | Biological agents survey report | [List] | TRUE | PM_30_40_10 : Biological agents survey report | PM_30_40_10 : Biological agents survey report | Project Management | recpmNLhYb6s08aiG
recEdKi9LYKtALw9n | 2021-06-14T07:47:08.000Z | PM_30_40_33 | Gases survey report | [List] | TRUE | PM_30_40_33 : Gases survey report | PM_30_40_33 : Gases survey report | Project Management | recEdKi9LYKtALw9n
rec6K54RpIeLGpybf | 2021-06-14T07:47:08.000Z | PM_30_40_36 | Hazardous chemicals survey report | [List] | TRUE | PM_30_40_36 : Hazardous chemicals survey report | PM_30_40_36 : Hazardous chemicals survey report | Project Management | rec6K54RpIeLGpybf
recuGtLrOGfX6LNz1 | 2021-06-14T07:47:08.000Z | PM_30_40_39 | Heavy metals survey report | [List] | TRUE | PM_30_40_39 : Heavy metals survey report | PM_30_40_39 : Heavy metals survey report | Project Management | recuGtLrOGfX6LNz1
recjIGbAUZcYovI6m | 2021-06-14T07:47:08.000Z | PM_30_40_46 | Lead survey report | [List] | TRUE | PM_30_40_46 : Lead survey report | PM_30_40_46 : Lead survey report | Project Management | recjIGbAUZcYovI6m
recRqlLGGs2KYT8XU | 2021-06-14T07:47:08.000Z | PM_30_40_70 | Radioactive waste survey report | [List] | TRUE | PM_30_40_70 : Radioactive waste survey report | PM_30_40_70 : Radioactive waste survey report | Project Management | recRqlLGGs2KYT8XU
recfH0q2ge9VNcUu8 | 2021-06-14T07:47:08.000Z | PM_30_40_92 | Unexploded ordnance survey report | [List] | TRUE | PM_30_40_92 : Unexploded ordnance survey report | PM_30_40_92 : Unexploded ordnance survey report | Project Management | recfH0q2ge9VNcUu8
recBywTKmBnTi2SmL | 2021-06-14T07:47:08.000Z | PM_30_40_94 | Volatile organic compounds survey report | [List] | TRUE | PM_30_40_94 : Volatile organic compounds survey report | PM_30_40_94 : Volatile organic compounds survey report | Project Management | recBywTKmBnTi2SmL
recdPz6G439ITtsgf | 2021-06-14T07:47:08.000Z | PM_35 | Project performance requirements | [List] | TRUE | PM_35 : Project performance requirements | PM_35 : Project performance requirements | Project Management | recdPz6G439ITtsgf
recqZMnsIHei0TWHg | 2021-06-14T07:47:08.000Z | PM_35_05 | Project context requirements | [List] | TRUE | PM_35_05 : Project context requirements | PM_35_05 : Project context requirements | Project Management | recqZMnsIHei0TWHg
rec33TChI5UShD5Gn | 2021-06-14T07:47:08.000Z | PM_35_05_22 | Development performance requirements | [List] | TRUE | PM_35_05_22 : Development performance requirements | PM_35_05_22 : Development performance requirements | Project Management | rec33TChI5UShD5Gn
rec9JxEG1YEGwar0h | 2021-06-14T07:47:08.000Z | PM_35_05_79 | Site context requirements | [List] | TRUE | PM_35_05_79 : Site context requirements | PM_35_05_79 : Site context requirements | Project Management | rec9JxEG1YEGwar0h
recp7ynweOvxGTJ26 | 2021-06-14T07:47:08.000Z | PM_35_10 | Quality and operational properties performance requirements | [List] | TRUE | PM_35_10 : Quality and operational properties performance requirements | PM_35_10 : Quality and operational properties performance requirements | Project Management | recp7ynweOvxGTJ26
recWP2wSlZ79J9RHG | 2021-06-14T07:47:08.000Z | PM_35_10_13 | Comfort performance requirements | [List] | TRUE | PM_35_10_13 : Comfort performance requirements | PM_35_10_13 : Comfort performance requirements | Project Management | recWP2wSlZ79J9RHG
recYq5SObMKTtGbjm | 2021-06-14T07:47:08.000Z | PM_35_10_15 | Condensation control performance requirements | [List] | TRUE | PM_35_10_15 : Condensation control performance requirements | PM_35_10_15 : Condensation control performance requirements | Project Management | recYq5SObMKTtGbjm
recSyVVW764UKC9UG | 2021-06-14T07:47:08.000Z | PM_35_10_22 | Design quality performance requirements | [List] | TRUE | PM_35_10_22 : Design quality performance requirements | PM_35_10_22 : Design quality performance requirements | Project Management | recSyVVW764UKC9UG
recE1eSusYBEwgsqJ | 2021-06-14T07:47:08.000Z | PM_35_10_25 | Durability performance requirements | [List] | TRUE | PM_35_10_25 : Durability performance requirements | PM_35_10_25 : Durability performance requirements | Project Management | recE1eSusYBEwgsqJ
recuGbBbZMys8RaH6 | 2021-06-14T07:47:08.000Z | PM_35_10_32 | Functional properties performance requirements | [List] | TRUE | PM_35_10_32 : Functional properties performance requirements | PM_35_10_32 : Functional properties performance requirements | Project Management | recuGbBbZMys8RaH6
recqxQCxK0DVYzbut | 2021-06-14T07:47:08.000Z | PM_35_10_47 | Life cycle performance requirements | [List] | TRUE | PM_35_10_47 : Life cycle performance requirements | PM_35_10_47 : Life cycle performance requirements | Project Management | recqxQCxK0DVYzbut
recQ8x9CsxrnfVO3f | 2021-06-14T07:47:08.000Z | PM_35_10_60 | Performance compliance requirements | [List] | TRUE | PM_35_10_60 : Performance compliance requirements | PM_35_10_60 : Performance compliance requirements | Project Management | recQ8x9CsxrnfVO3f
recUGaagnJkuGKVV8 | 2021-06-14T07:47:08.000Z | PM_35_10_96 | Watertightness performance requirements | [List] | TRUE | PM_35_10_96 : Watertightness performance requirements | PM_35_10_96 : Watertightness performance requirements | Project Management | recUGaagnJkuGKVV8
reccd1ABdqgxzczlJ | 2021-06-14T07:47:08.000Z | PM_35_20 | Structural performance requirements | [List] | TRUE | PM_35_20 : Structural performance requirements | PM_35_20 : Structural performance requirements | Project Management | reccd1ABdqgxzczlJ
recYtvviYsYR9PbUD | 2021-06-14T07:47:08.000Z | PM_35_20_03 | Accidental loading performance requirements | [List] | TRUE | PM_35_20_03 : Accidental loading performance requirements | PM_35_20_03 : Accidental loading performance requirements | Project Management | recYtvviYsYR9PbUD
reci1wrAALgZUBZbz | 2021-06-14T07:47:08.000Z | PM_35_20_26 | Earthquake loading performance requirements | [List] | TRUE | PM_35_20_26 : Earthquake loading performance requirements | PM_35_20_26 : Earthquake loading performance requirements | Project Management | reci1wrAALgZUBZbz
recqkGoC6d06pxcXm | 2021-06-14T07:47:08.000Z | PM_35_20_33 | Geotechnical performance requirements | [List] | TRUE | PM_35_20_33 : Geotechnical performance requirements | PM_35_20_33 : Geotechnical performance requirements | Project Management | recqkGoC6d06pxcXm
recl9XgDcTupfNpxh | 2021-06-14T07:47:08.000Z | PM_35_20_42 | Imposed loads performance requirements | [List] | TRUE | PM_35_20_42 : Imposed loads performance requirements | PM_35_20_42 : Imposed loads performance requirements | Project Management | recl9XgDcTupfNpxh
recLdZw0QrEKSnamc | 2021-06-14T07:47:08.000Z | PM_35_20_62 | Permanent loads performance requirements | [List] | TRUE | PM_35_20_62 : Permanent loads performance requirements | PM_35_20_62 : Permanent loads performance requirements | Project Management | recLdZw0QrEKSnamc
recoSnU6WXYt2p2D8 | 2021-06-14T07:47:08.000Z | PM_35_20_76 | Snow and ice load performance requirements | [List] | TRUE | PM_35_20_76 : Snow and ice load performance requirements | PM_35_20_76 : Snow and ice load performance requirements | Project Management | recoSnU6WXYt2p2D8
recfjYJbgfBONoZz3 | 2021-06-14T07:47:08.000Z | PM_35_20_80 | Structural design performance requirements | [List] | TRUE | PM_35_20_80 : Structural design performance requirements | PM_35_20_80 : Structural design performance requirements | Project Management | recfjYJbgfBONoZz3
recpMuif8YljQTZHR | 2021-11-11T11:10:56.000Z | PM_35_20_81 | Structural robustness performance requirements | [List] | TRUE | PM_35_20_81 : Structural robustness performance requirements | PM_35_20_81 : Structural robustness performance requirements | Project Management | recpMuif8YljQTZHR
recYk4K6xTVmXhZtJ | 2021-06-14T07:47:08.000Z | PM_35_20_82 | Subsidence mitigation performance requirements | [List] | TRUE | PM_35_20_82 : Subsidence mitigation performance requirements | PM_35_20_82 : Subsidence mitigation performance requirements | Project Management | recYk4K6xTVmXhZtJ
rec33iA6ri6sOQAyV | 2021-06-14T07:47:08.000Z | PM_35_20_90 | Thermal actions performance requirements | [List] | TRUE | PM_35_20_90 : Thermal actions performance requirements | PM_35_20_90 : Thermal actions performance requirements | Project Management | rec33iA6ri6sOQAyV
recy7KuyAcpRzinRZ | 2021-06-14T07:47:08.000Z | PM_35_20_96 | Wind loading performance requirements | [List] | TRUE | PM_35_20_96 : Wind loading performance requirements | PM_35_20_96 : Wind loading performance requirements | Project Management | recy7KuyAcpRzinRZ
recN6yzXWbHo8WBMp | 2021-06-14T07:47:08.000Z | PM_35_30 | Fire performance requirements | [List] | TRUE | PM_35_30 : Fire performance requirements | PM_35_30 : Fire performance requirements | Project Management | recN6yzXWbHo8WBMp
recmMZ9PzAIo6oCfB | 2021-06-14T07:47:08.000Z | PM_35_30_04 | Automatic fire suppression performance requirements | [List] | TRUE | PM_35_30_04 : Automatic fire suppression performance requirements | PM_35_30_04 : Automatic fire suppression performance requirements | Project Management | recmMZ9PzAIo6oCfB
recE9Kownq0JKuVXJ | 2021-06-14T07:47:08.000Z | PM_35_30_20 | Escape lighting performance requirements | [List] | TRUE | PM_35_30_20 : Escape lighting performance requirements | PM_35_30_20 : Escape lighting performance requirements | Project Management | recE9Kownq0JKuVXJ
reclsWVR8sBXIdl2u | 2021-06-14T07:47:08.000Z | PM_35_30_24 | Fire and rescue service requirements | [List] | TRUE | PM_35_30_24 : Fire and rescue service requirements | PM_35_30_24 : Fire and rescue service requirements | Project Management | reclsWVR8sBXIdl2u
recyqJAGGjNgL8Q9A | 2021-06-14T07:47:08.000Z | PM_35_30_26 | Fire protection zone requirements | [List] | TRUE | PM_35_30_26 : Fire protection zone requirements | PM_35_30_26 : Fire protection zone requirements | Project Management | recyqJAGGjNgL8Q9A
recTdGuzvWmJ1TX9L | 2021-06-14T07:47:08.000Z | PM_35_30_28 | Fire resistance performance requirements | [List] | TRUE | PM_35_30_28 : Fire resistance performance requirements | PM_35_30_28 : Fire resistance performance requirements | Project Management | recTdGuzvWmJ1TX9L
recWVMVXuLUjVtuEb | 2021-06-14T07:47:08.000Z | PM_35_30_30 | Fire safety performance requirements | [List] | TRUE | PM_35_30_30 : Fire safety performance requirements | PM_35_30_30 : Fire safety performance requirements | Project Management | recWVMVXuLUjVtuEb
rect4VcRDMfoG31d7 | 2021-06-14T07:47:08.000Z | PM_35_30_70 | Reaction to fire performance requirements | [List] | TRUE | PM_35_30_70 : Reaction to fire performance requirements | PM_35_30_70 : Reaction to fire performance requirements | Project Management | rect4VcRDMfoG31d7
recOO6Tn5zYCHI1UM | 2021-06-14T07:47:08.000Z | PM_35_30_80 | Spread of fire performance requirements | [List] | TRUE | PM_35_30_80 : Spread of fire performance requirements | PM_35_30_80 : Spread of fire performance requirements | Project Management | recOO6Tn5zYCHI1UM
recRPvVvP6eTnUm9x | 2021-06-14T07:47:08.000Z | PM_35_30_85 | Structural fire performance requirements | [List] | TRUE | PM_35_30_85 : Structural fire performance requirements | PM_35_30_85 : Structural fire performance requirements | Project Management | recRPvVvP6eTnUm9x
recZYHuYigG48rrq2 | 2021-06-14T07:47:08.000Z | PM_35_30_96 | Wildfire protection performance requirements | [List] | TRUE | PM_35_30_96 : Wildfire protection performance requirements | PM_35_30_96 : Wildfire protection performance requirements | Project Management | recZYHuYigG48rrq2
recN17mjMYjNx9W4E | 2021-06-14T07:47:08.000Z | PM_35_40 | Environmentally sustainable design requirements | [List] | TRUE | PM_35_40 : Environmentally sustainable design requirements | PM_35_40 : Environmentally sustainable design requirements | Project Management | recN17mjMYjNx9W4E
rec4iEudqVJreKJrs | 2021-06-14T07:47:08.000Z | PM_35_40_08 | Biodiversity performance requirements | [List] | TRUE | PM_35_40_08 : Biodiversity performance requirements | PM_35_40_08 : Biodiversity performance requirements | Project Management | rec4iEudqVJreKJrs
reczQA4ieLinIRwU1 | 2022-01-28T12:20:29.000Z | PM_35_40_28 | Earthworks and groundworks schedules | [List] | TRUE | PM_35_40_28 : Earthworks and groundworks schedules | PM_35_40_28 : Earthworks and groundworks schedules | Project Management | reczQA4ieLinIRwU1
recLiCe7J1puMEz7d | 2021-06-14T07:47:08.000Z | PM_35_40_30 | Environmental scheme performance requirements | [List] | TRUE | PM_35_40_30 : Environmental scheme performance requirements | PM_35_40_30 : Environmental scheme performance requirements | Project Management | recLiCe7J1puMEz7d
rec87zunBTA7297uC | 2021-06-14T07:47:08.000Z | PM_35_40_32 | Flood defence performance requirements | [List] | TRUE | PM_35_40_32 : Flood defence performance requirements | PM_35_40_32 : Flood defence performance requirements | Project Management | rec87zunBTA7297uC
recNd8H5kgReW73VG | 2021-06-14T07:47:08.000Z | PM_35_40_34 | Habitat performance requirements | [List] | TRUE | PM_35_40_34 : Habitat performance requirements | PM_35_40_34 : Habitat performance requirements | Project Management | recNd8H5kgReW73VG
recnauGDsvU9jnsbd | 2021-06-14T07:47:08.000Z | PM_35_40_35 | Hazardous materials control requirements | [List] | TRUE | PM_35_40_35 : Hazardous materials control requirements | PM_35_40_35 : Hazardous materials control requirements | Project Management | recnauGDsvU9jnsbd
rec6Wr1gh1BqqFDJw | 2021-06-14T07:47:08.000Z | PM_35_40_38 | Hydrological performance requirements | [List] | TRUE | PM_35_40_38 : Hydrological performance requirements | PM_35_40_38 : Hydrological performance requirements | Project Management | rec6Wr1gh1BqqFDJw
recJDAu8oyJmbSHrx | 2021-06-14T07:47:08.000Z | PM_35_40_72 | Resistance to ground contaminants requirements | [List] | TRUE | PM_35_40_72 : Resistance to ground contaminants requirements | PM_35_40_72 : Resistance to ground contaminants requirements | Project Management | recJDAu8oyJmbSHrx
recbbFfF05x1mslZO | 2021-06-14T07:47:08.000Z | PM_35_40_84 | Sustainability performance requirements | [List] | TRUE | PM_35_40_84 : Sustainability performance requirements | PM_35_40_84 : Sustainability performance requirements | Project Management | recbbFfF05x1mslZO
recrv3xT9vkrWawPT | 2021-06-14T07:47:08.000Z | PM_35_50 | Safety performance requirements | [List] | TRUE | PM_35_50 : Safety performance requirements | PM_35_50 : Safety performance requirements | Project Management | recrv3xT9vkrWawPT
recawT3IaiCHNToHw | 2021-06-14T07:47:08.000Z | PM_35_50_01 | Accessibility performance requirements | [List] | TRUE | PM_35_50_01 : Accessibility performance requirements | PM_35_50_01 : Accessibility performance requirements | Project Management | recawT3IaiCHNToHw
recT9yklfXgvUMfS1 | 2021-06-14T07:47:08.000Z | PM_35_50_08 | Biosecurity performance requirements | [List] | TRUE | PM_35_50_08 : Biosecurity performance requirements | PM_35_50_08 : Biosecurity performance requirements | Project Management | recT9yklfXgvUMfS1
recQutxwjK2YD5ypg | 2021-06-14T07:47:08.000Z | PM_35_50_47 | Lightning protection performance requirements | [List] | TRUE | PM_35_50_47 : Lightning protection performance requirements | PM_35_50_47 : Lightning protection performance requirements | Project Management | recQutxwjK2YD5ypg
recxxvbnxSiqpmXEK | 2021-06-14T07:47:08.000Z | PM_35_50_65 | Project and site safety performance requirements | [List] | TRUE | PM_35_50_65 : Project and site safety performance requirements | PM_35_50_65 : Project and site safety performance requirements | Project Management | recxxvbnxSiqpmXEK
rec6Gr1siN40lG2SG | 2021-06-14T07:47:08.000Z | PM_35_50_72 | Safety and protection performance requirements | [List] | TRUE | PM_35_50_72 : Safety and protection performance requirements | PM_35_50_72 : Safety and protection performance requirements | Project Management | rec6Gr1siN40lG2SG
recD7XXiInhI5pzaJ | 2021-06-14T07:47:08.000Z | PM_35_50_74 | Security performance requirements | [List] | TRUE | PM_35_50_74 : Security performance requirements | PM_35_50_74 : Security performance requirements | Project Management | recD7XXiInhI5pzaJ
recB0qw4VegyM5Imt | 2021-06-14T07:47:08.000Z | PM_35_60 | Acoustic performance requirements | [List] | TRUE | PM_35_60 : Acoustic performance requirements | PM_35_60 : Acoustic performance requirements | Project Management | recB0qw4VegyM5Imt
rec3FMeaLwuHONORG | 2021-06-14T07:47:08.000Z | PM_35_60_01 | Acoustic attenuation performance requirements | [List] | TRUE | PM_35_60_01 : Acoustic attenuation performance requirements | PM_35_60_01 : Acoustic attenuation performance requirements | Project Management | rec3FMeaLwuHONORG
recRNQEgA7AWuv90O | 2021-06-14T07:47:08.000Z | PM_35_60_03 | Acoustic diffusion performance requirements | [List] | TRUE | PM_35_60_03 : Acoustic diffusion performance requirements | PM_35_60_03 : Acoustic diffusion performance requirements | Project Management | recRNQEgA7AWuv90O
recLZSXNPmMFtf626 | 2021-06-14T07:47:08.000Z | PM_35_60_05 | Acoustic separation performance requirements | [List] | TRUE | PM_35_60_05 : Acoustic separation performance requirements | PM_35_60_05 : Acoustic separation performance requirements | Project Management | recLZSXNPmMFtf626
recjUR77WHwOwBKVl | 2021-06-14T07:47:08.000Z | PM_35_60_95 | Vibration control performance requirements | [List] | TRUE | PM_35_60_95 : Vibration control performance requirements | PM_35_60_95 : Vibration control performance requirements | Project Management | recjUR77WHwOwBKVl
recFL2aqKikdEjFC0 | 2021-06-14T07:47:08.000Z | PM_35_70 | Energy performance requirements | [List] | TRUE | PM_35_70 : Energy performance requirements | PM_35_70 : Energy performance requirements | Project Management | recFL2aqKikdEjFC0
recKHVeAJnAZ9uTcB | 2021-06-14T07:47:08.000Z | PM_35_70_03 | Airtightness performance requirements | [List] | TRUE | PM_35_70_03 : Airtightness performance requirements | PM_35_70_03 : Airtightness performance requirements | Project Management | recKHVeAJnAZ9uTcB
rec9BDnjEfEXjcNJ9 | 2021-06-14T07:47:08.000Z | PM_35_70_05 | Air conditioning performance requirements | [List] | TRUE | PM_35_70_05 : Air conditioning performance requirements | PM_35_70_05 : Air conditioning performance requirements | Project Management | rec9BDnjEfEXjcNJ9
recpIcuYBAOjftfsc | 2021-06-14T07:47:08.000Z | PM_35_70_15 | Chilled water performance requirements | [List] | TRUE | PM_35_70_15 : Chilled water performance requirements | PM_35_70_15 : Chilled water performance requirements | Project Management | recpIcuYBAOjftfsc
recICUxYf1V0PQcQy | 2021-06-14T07:47:08.000Z | PM_35_70_17 | Combustion appliance performance requirements | [List] | TRUE | PM_35_70_17 : Combustion appliance performance requirements | PM_35_70_17 : Combustion appliance performance requirements | Project Management | recICUxYf1V0PQcQy
recUk85YyoxCkIE7I | 2021-06-14T07:47:08.000Z | PM_35_70_20 | Daylight and shading performance requirements | [List] | TRUE | PM_35_70_20 : Daylight and shading performance requirements | PM_35_70_20 : Daylight and shading performance requirements | Project Management | recUk85YyoxCkIE7I
recRLpdgLHLyR0kXZ | 2021-06-14T07:47:08.000Z | PM_35_70_36 | Heating performance requirements | [List] | TRUE | PM_35_70_36 : Heating performance requirements | PM_35_70_36 : Heating performance requirements | Project Management | recRLpdgLHLyR0kXZ
recVkoHjd9xQVcV3s | 2021-06-14T07:47:08.000Z | PM_35_70_38 | Hot and cold water supply performance requirements | [List] | TRUE | PM_35_70_38 : Hot and cold water supply performance requirements | PM_35_70_38 : Hot and cold water supply performance requirements | Project Management | recVkoHjd9xQVcV3s
recoequTe6KMmwbCZ | 2021-06-14T07:47:08.000Z | PM_35_70_46 | Lighting performance requirements | [List] | TRUE | PM_35_70_46 : Lighting performance requirements | PM_35_70_46 : Lighting performance requirements | Project Management | recoequTe6KMmwbCZ
recbLaACKTeBhpnpJ | 2021-06-14T07:47:08.000Z | PM_35_70_92 | Thermal performance requirements | [List] | TRUE | PM_35_70_92 : Thermal performance requirements | PM_35_70_92 : Thermal performance requirements | Project Management | recbLaACKTeBhpnpJ
recJ4v6SOCpHgJe42 | 2021-06-14T07:47:08.000Z | PM_35_70_94 | Ventilation performance requirements | [List] | TRUE | PM_35_70_94 : Ventilation performance requirements | PM_35_70_94 : Ventilation performance requirements | Project Management | recJ4v6SOCpHgJe42
recJ6F9E7RVUvUSQk | 2021-06-14T07:47:08.000Z | PM_40 | Design and approvals information | [List] | TRUE | PM_40 : Design and approvals information | PM_40 : Design and approvals information | Project Management | recJ6F9E7RVUvUSQk
rec7pRFyswxxOtIbh | 2021-06-14T07:47:08.000Z | PM_40_20 | Design strategies | [List] | TRUE | PM_40_20 : Design strategies | PM_40_20 : Design strategies | Project Management | rec7pRFyswxxOtIbh
recuW2XFAfkmmFCai | 2021-06-14T07:47:08.000Z | PM_40_20_01 | Access and maintenance strategy | [List] | TRUE | PM_40_20_01 : Access and maintenance strategy | PM_40_20_01 : Access and maintenance strategy | Project Management | recuW2XFAfkmmFCai
recsqT0bKsvNM68aj | 2021-06-14T07:47:08.000Z | PM_40_20_02 | Acoustic strategy | [List] | TRUE | PM_40_20_02 : Acoustic strategy | PM_40_20_02 : Acoustic strategy | Project Management | recsqT0bKsvNM68aj
rec1BHp7bhK6e3Q2s | 2021-06-14T07:47:08.000Z | PM_40_20_05 | Air conditioning design strategy | [List] | TRUE | PM_40_20_05 : Air conditioning design strategy | PM_40_20_05 : Air conditioning design strategy | Project Management | rec1BHp7bhK6e3Q2s
rec6J9Har10Gg5oOb | 2021-06-14T07:47:08.000Z | PM_40_20_10 | Building services strategy | [List] | TRUE | PM_40_20_10 : Building services strategy | PM_40_20_10 : Building services strategy | Project Management | rec6J9Har10Gg5oOb
recVBOIk1KMLgnfXs | 2021-06-14T07:47:08.000Z | PM_40_20_13 | Civil engineering design strategy | [List] | TRUE | PM_40_20_13 : Civil engineering design strategy | PM_40_20_13 : Civil engineering design strategy | Project Management | recVBOIk1KMLgnfXs
reciJCySP5QJgOTbp | 2021-06-14T07:47:08.000Z | PM_40_20_15 | Commissioning strategy | [List] | TRUE | PM_40_20_15 : Commissioning strategy | PM_40_20_15 : Commissioning strategy | Project Management | reciJCySP5QJgOTbp
recjKtOnhBYvGr0Fe | 2021-06-14T07:47:08.000Z | PM_40_20_17 | Conservation strategy | [List] | TRUE | PM_40_20_17 : Conservation strategy | PM_40_20_17 : Conservation strategy | Project Management | recjKtOnhBYvGr0Fe
recoJvOVljdNkBaql | 2021-06-14T07:47:08.000Z | PM_40_20_19 | Cost plan strategy | [List] | TRUE | PM_40_20_19 : Cost plan strategy | PM_40_20_19 : Cost plan strategy | Project Management | recoJvOVljdNkBaql
recb8Biph66chb7GZ | 2021-06-14T07:47:08.000Z | PM_40_20_21 | Daylight design strategy | [List] | TRUE | PM_40_20_21 : Daylight design strategy | PM_40_20_21 : Daylight design strategy | Project Management | recb8Biph66chb7GZ
recVz2pAVKpjmuVNe | 2021-06-14T07:47:08.000Z | PM_40_20_26 | Energy strategy | [List] | TRUE | PM_40_20_26 : Energy strategy | PM_40_20_26 : Energy strategy | Project Management | recVz2pAVKpjmuVNe
recLK8FRmbik7z3S9 | 2021-06-14T07:47:08.000Z | PM_40_20_30 | Fire safety strategy | [List] | TRUE | PM_40_20_30 : Fire safety strategy | PM_40_20_30 : Fire safety strategy | Project Management | recLK8FRmbik7z3S9
recorA4HijjsCTK2L | 2021-06-14T07:47:08.000Z | PM_40_20_36 | Health and safety strategy | [List] | TRUE | PM_40_20_36 : Health and safety strategy | PM_40_20_36 : Health and safety strategy | Project Management | recorA4HijjsCTK2L
rec3CNsABVEtEmCeO | 2021-06-14T07:47:08.000Z | PM_40_20_38 | Heating and cooling design strategy | [List] | TRUE | PM_40_20_38 : Heating and cooling design strategy | PM_40_20_38 : Heating and cooling design strategy | Project Management | rec3CNsABVEtEmCeO
recP1qBdyKwLI5qGM | 2021-06-14T07:47:08.000Z | PM_40_20_42 | Inclusive design strategy | [List] | TRUE | PM_40_20_42 : Inclusive design strategy | PM_40_20_42 : Inclusive design strategy | Project Management | recP1qBdyKwLI5qGM
recLspDNpfVZkKIZP | 2021-06-14T07:47:08.000Z | PM_40_20_43 | Information and communications technology (ICT) strategy | [List] | TRUE | PM_40_20_43 : Information and communications technology (ICT) strategy | PM_40_20_43 : Information and communications technology (ICT) strategy | Project Management | recLspDNpfVZkKIZP
recC4MZ5mmwycSvtk | 2021-06-14T07:47:08.000Z | PM_40_20_47 | Lighting strategy | [List] | TRUE | PM_40_20_47 : Lighting strategy | PM_40_20_47 : Lighting strategy | Project Management | recC4MZ5mmwycSvtk
recCLSW97cXpwo3zK | 2021-06-14T07:47:08.000Z | PM_40_20_63 | Planning strategy | [List] | TRUE | PM_40_20_63 : Planning strategy | PM_40_20_63 : Planning strategy | Project Management | recCLSW97cXpwo3zK
recNwlEoD9VnIsa8C | 2021-06-14T07:47:08.000Z | PM_40_20_64 | Plant and equipment replacement strategy | [List] | TRUE | PM_40_20_64 : Plant and equipment replacement strategy | PM_40_20_64 : Plant and equipment replacement strategy | Project Management | recNwlEoD9VnIsa8C
recfh1dFwhrWQkFwC | 2021-06-14T07:47:08.000Z | PM_40_20_65 | Plan for use strategy | [List] | TRUE | PM_40_20_65 : Plan for use strategy | PM_40_20_65 : Plan for use strategy | Project Management | recfh1dFwhrWQkFwC
rec4noiY8b70pkQWW | 2021-06-14T07:47:08.000Z | PM_40_20_77 | Security strategy | [List] | TRUE | PM_40_20_77 : Security strategy | PM_40_20_77 : Security strategy | Project Management | rec4noiY8b70pkQWW
reccUZs6DWLCCw2Gz | 2021-06-14T07:47:08.000Z | PM_40_20_83 | Structural engineering design strategy | [List] | TRUE | PM_40_20_83 : Structural engineering design strategy | PM_40_20_83 : Structural engineering design strategy | Project Management | reccUZs6DWLCCw2Gz
recgFjraQYyBasOdG | 2021-06-14T07:47:08.000Z | PM_40_20_85 | Sustainability strategy | [List] | TRUE | PM_40_20_85 : Sustainability strategy | PM_40_20_85 : Sustainability strategy | Project Management | recgFjraQYyBasOdG
recYfwso7orBcafnn | 2021-06-14T07:47:08.000Z | PM_40_20_94 | Ventilation design strategy | [List] | TRUE | PM_40_20_94 : Ventilation design strategy | PM_40_20_94 : Ventilation design strategy | Project Management | recYfwso7orBcafnn
recmbFKF9N55Wp5tK | 2021-06-14T07:47:08.000Z | PM_40_30 | Design information | [List] | TRUE | PM_40_30 : Design information | PM_40_30 : Design information | Project Management | recmbFKF9N55Wp5tK
recwilG1STeayFE8C | 2021-06-14T07:47:08.000Z | PM_40_30_17 | Concept analysis | [List] | TRUE | PM_40_30_17 : Concept analysis | PM_40_30_17 : Concept analysis | Project Management | recwilG1STeayFE8C
recHpyVKYo6d4rgju | 2021-06-14T07:47:08.000Z | PM_40_30_18 | Construction specification | [List] | TRUE | PM_40_30_18 : Construction specification | PM_40_30_18 : Construction specification | Project Management | recHpyVKYo6d4rgju
recxZVtqRFlZjf9V1 | 2021-06-14T07:47:08.000Z | PM_40_30_20 | Design calculations | [List] | TRUE | PM_40_30_20 : Design calculations | PM_40_30_20 : Design calculations | Project Management | recxZVtqRFlZjf9V1
rec45SXX9jdfcFfeA | 2021-06-14T07:47:08.000Z | PM_40_30_21 | Design development register information | [List] | TRUE | PM_40_30_21 : Design development register information | PM_40_30_21 : Design development register information | Project Management | rec45SXX9jdfcFfeA
rechoU7pbPpsvVw9c | 2021-11-11T11:10:56.000Z | PM_40_30_22 | Designer health and safety risk assessment | [List] | TRUE | PM_40_30_22 : Designer health and safety risk assessment | PM_40_30_22 : Designer health and safety risk assessment | Project Management | rechoU7pbPpsvVw9c
recLJFgGcmv6oQ5D8 | 2021-06-14T07:47:08.000Z | PM_40_30_23 | Design philosophy statement | [List] | TRUE | PM_40_30_23 : Design philosophy statement | PM_40_30_23 : Design philosophy statement | Project Management | recLJFgGcmv6oQ5D8
rec74iPm0CkxXyizN | 2021-06-14T07:47:08.000Z | PM_40_30_24 | Design responsibility matrix | [List] | TRUE | PM_40_30_24 : Design responsibility matrix | PM_40_30_24 : Design responsibility matrix | Project Management | rec74iPm0CkxXyizN
rec74tqUyalkpjmKA | 2021-06-14T07:47:08.000Z | PM_40_30_25 | Developmental control plan | [List] | TRUE | PM_40_30_25 : Developmental control plan | PM_40_30_25 : Developmental control plan | Project Management | rec74tqUyalkpjmKA
reculEvwy1GSAAcKo | 2021-06-14T07:47:08.000Z | PM_40_30_27 | Energy target | [List] | TRUE | PM_40_30_27 : Energy target | PM_40_30_27 : Energy target | Project Management | reculEvwy1GSAAcKo
recfDCfKZUKUWc2HF | 2021-06-14T07:47:08.000Z | PM_40_30_34 | Graphical information | [List] | TRUE | PM_40_30_34 : Graphical information | PM_40_30_34 : Graphical information | Project Management | recfDCfKZUKUWc2HF
recLlbCYEE9MyMUl8 | 2021-06-14T07:47:08.000Z | PM_40_30_50 | Management control plan | [List] | TRUE | PM_40_30_50 : Management control plan | PM_40_30_50 : Management control plan | Project Management | recLlbCYEE9MyMUl8
recLSFrXewiOpfdG4 | 2021-06-14T07:47:08.000Z | PM_40_30_52 | Mechanical, electrical, instrumentation, controls and automation (MEICA) design | [List] | TRUE | PM_40_30_52 : Mechanical, electrical, instrumentation, controls and automation (MEICA) design | PM_40_30_52 : Mechanical, electrical, instrumentation, controls and automation (MEICA) design | Project Management | recLSFrXewiOpfdG4
rec4ldKv9NhFEDjTP | 2021-06-14T07:47:08.000Z | PM_40_30_58 | Outline specification | [List] | TRUE | PM_40_30_58 : Outline specification | PM_40_30_58 : Outline specification | Project Management | rec4ldKv9NhFEDjTP
recVKfTT9ByMpfrip | 2021-06-14T07:47:08.000Z | PM_40_30_60 | Parametric information | [List] | TRUE | PM_40_30_60 : Parametric information | PM_40_30_60 : Parametric information | Project Management | recVKfTT9ByMpfrip
recQjaesnXgpliGSX | 2021-06-14T07:47:08.000Z | PM_40_30_61 | Performance specification | [List] | TRUE | PM_40_30_61 : Performance specification | PM_40_30_61 : Performance specification | Project Management | recQjaesnXgpliGSX
recgGVX6h2Qostd1q | 2021-06-14T07:47:08.000Z | PM_40_30_62 | Photorealistic visualization images | [List] | TRUE | PM_40_30_62 : Photorealistic visualization images | PM_40_30_62 : Photorealistic visualization images | Project Management | recgGVX6h2Qostd1q
recNOrJnZuwGIDbUZ | 2021-06-14T07:47:08.000Z | PM_40_30_63 | Photorealistic visualization model | [List] | TRUE | PM_40_30_63 : Photorealistic visualization model | PM_40_30_63 : Photorealistic visualization model | Project Management | recNOrJnZuwGIDbUZ
receIT2R9HN2kRgus | 2021-06-14T07:47:08.000Z | PM_40_30_70 | Room data | [List] | TRUE | PM_40_30_70 : Room data | PM_40_30_70 : Room data | Project Management | receIT2R9HN2kRgus
recwxSQ38LU0Bm25p | 2021-06-14T07:47:08.000Z | PM_40_30_89 | Technical information | [List] | TRUE | PM_40_30_89 : Technical information | PM_40_30_89 : Technical information | Project Management | recwxSQ38LU0Bm25p
recUmh2xUGvM77yu7 | 2021-06-14T07:47:08.000Z | PM_40_35 | Design models | [List] | TRUE | PM_40_35 : Design models | PM_40_35 : Design models | Project Management | recUmh2xUGvM77yu7
recDZH53taHgsurCp | 2021-06-14T07:47:08.000Z | PM_40_35_04 | Architects models | [List] | TRUE | PM_40_35_04 : Architects models | PM_40_35_04 : Architects models | Project Management | recDZH53taHgsurCp
recvC87wTErU69Y6f | 2021-06-14T07:47:08.000Z | PM_40_35_10 | Building services models | [List] | TRUE | PM_40_35_10 : Building services models | PM_40_35_10 : Building services models | Project Management | recvC87wTErU69Y6f
recPKJTncP5gS45yJ | 2021-06-14T07:47:08.000Z | PM_40_35_11 | Catering models | [List] | TRUE | PM_40_35_11 : Catering models | PM_40_35_11 : Catering models | Project Management | recPKJTncP5gS45yJ
rec2izkfLgsSFh2IH | 2021-06-14T07:47:08.000Z | PM_40_35_15 | Civil engineering models | [List] | TRUE | PM_40_35_15 : Civil engineering models | PM_40_35_15 : Civil engineering models | Project Management | rec2izkfLgsSFh2IH
recsPzmO6I98pG95s | 2021-06-14T07:47:08.000Z | PM_40_35_29 | Fittings, furnishings and equipment (FF&E) models | [List] | TRUE | PM_40_35_29 : Fittings, furnishings and equipment (FF&E) models | PM_40_35_29 : Fittings, furnishings and equipment (FF&E) models | Project Management | recsPzmO6I98pG95s
rec7bsdZA8x2ejZK0 | 2021-06-14T07:47:08.000Z | PM_40_35_45 | Landscape models | [List] | TRUE | PM_40_35_45 : Landscape models | PM_40_35_45 : Landscape models | Project Management | rec7bsdZA8x2ejZK0
recT9SaOiJz8abGXL | 2021-11-11T11:10:56.000Z | PM_40_35_65 | Process models | [List] | TRUE | PM_40_35_65 : Process models | PM_40_35_65 : Process models | Project Management | recT9SaOiJz8abGXL
recdn06ISDqecA6aV | 2021-06-14T07:47:08.000Z | PM_40_35_83 | Structural engineering models | [List] | TRUE | PM_40_35_83 : Structural engineering models | PM_40_35_83 : Structural engineering models | Project Management | recdn06ISDqecA6aV
rec5Uvj3OkGvYHZql | 2021-06-14T07:47:08.000Z | PM_40_40 | Design drawings | [List] | TRUE | PM_40_40 : Design drawings | PM_40_40 : Design drawings | Project Management | rec5Uvj3OkGvYHZql
rec0KJOpyrTPPIeWL | 2021-06-14T07:47:08.000Z | PM_40_40_01 | 2D plan drawings | [List] | TRUE | PM_40_40_01 : 2D plan drawings | PM_40_40_01 : 2D plan drawings | Project Management | rec0KJOpyrTPPIeWL
recShxOjSrxXaDREd | 2021-06-14T07:47:08.000Z | PM_40_40_02 | 3D plan drawings | [List] | TRUE | PM_40_40_02 : 3D plan drawings | PM_40_40_02 : 3D plan drawings | Project Management | recShxOjSrxXaDREd
recV3dkJcoEF4dwBj | 2021-06-14T07:47:08.000Z | PM_40_40_10 | Builders' work drawings | [List] | TRUE | PM_40_40_10 : Builders' work drawings | PM_40_40_10 : Builders' work drawings | Project Management | recV3dkJcoEF4dwBj
recuqxX5UVluaSY8i | 2021-06-14T07:47:08.000Z | PM_40_40_15 | Coordination drawings | [List] | TRUE | PM_40_40_15 : Coordination drawings | PM_40_40_15 : Coordination drawings | Project Management | recuqxX5UVluaSY8i
recP9SDyuzIzgwKGP | 2021-06-14T07:47:08.000Z | PM_40_40_18 | Cross-section drawings | [List] | TRUE | PM_40_40_18 : Cross-section drawings | PM_40_40_18 : Cross-section drawings | Project Management | recP9SDyuzIzgwKGP
recOcPAxOoSxK0Ntf | 2021-06-14T07:47:08.000Z | PM_40_40_20 | Decant drawings | [List] | TRUE | PM_40_40_20 : Decant drawings | PM_40_40_20 : Decant drawings | Project Management | recOcPAxOoSxK0Ntf
recS8S5Rja3y2TOu3 | 2021-06-14T07:47:08.000Z | PM_40_40_22 | Diagrammatical drawings | [List] | TRUE | PM_40_40_22 : Diagrammatical drawings | PM_40_40_22 : Diagrammatical drawings | Project Management | recS8S5Rja3y2TOu3
recYTxC28f5vVzd89 | 2021-06-14T07:47:08.000Z | PM_40_40_27 | Elevation drawings | [List] | TRUE | PM_40_40_27 : Elevation drawings | PM_40_40_27 : Elevation drawings | Project Management | recYTxC28f5vVzd89
reci440OqhHsLLoY9 | 2021-06-14T07:47:08.000Z | PM_40_40_34 | General arrangement drawings | [List] | TRUE | PM_40_40_34 : General arrangement drawings | PM_40_40_34 : General arrangement drawings | Project Management | reci440OqhHsLLoY9
recNixoSydQ9SqfuM | 2021-06-14T07:47:08.000Z | PM_40_40_42 | Isometric drawings | [List] | TRUE | PM_40_40_42 : Isometric drawings | PM_40_40_42 : Isometric drawings | Project Management | recNixoSydQ9SqfuM
recr6oioWLF1ox8Oc | 2021-06-14T07:47:08.000Z | PM_40_40_50 | Manufacturer's drawings | [List] | TRUE | PM_40_40_50 : Manufacturer's drawings | PM_40_40_50 : Manufacturer's drawings | Project Management | recr6oioWLF1ox8Oc
recSLh07kVvTbIaMd | 2021-06-14T07:47:08.000Z | PM_40_40_54 | Multi-view drawings | [List] | TRUE | PM_40_40_54 : Multi-view drawings | PM_40_40_54 : Multi-view drawings | Project Management | recSLh07kVvTbIaMd
recbPDFKHNtmloJZo | 2021-06-14T07:47:08.000Z | PM_40_40_63 | Phasing drawings | [List] | TRUE | PM_40_40_63 : Phasing drawings | PM_40_40_63 : Phasing drawings | Project Management | recbPDFKHNtmloJZo
recSsETx20IaOr6EI | 2021-06-14T07:47:08.000Z | PM_40_40_75 | Schematic drawings | [List] | TRUE | PM_40_40_75 : Schematic drawings | PM_40_40_75 : Schematic drawings | Project Management | recSsETx20IaOr6EI
recCrirggc2sBxsun | 2021-06-14T07:47:08.000Z | PM_40_40_79 | Sketch drawings | [List] | TRUE | PM_40_40_79 : Sketch drawings | PM_40_40_79 : Sketch drawings | Project Management | recCrirggc2sBxsun
rec8Vy2dflx29pxJ3 | 2021-06-14T07:47:08.000Z | PM_40_40_88 | Technical design drawings | [List] | TRUE | PM_40_40_88 : Technical design drawings | PM_40_40_88 : Technical design drawings | Project Management | rec8Vy2dflx29pxJ3
rec4WexVqeWeHWYUt | 2021-06-14T07:47:08.000Z | PM_40_50 | Approvals information | [List] | TRUE | PM_40_50 : Approvals information | PM_40_50 : Approvals information | Project Management | rec4WexVqeWeHWYUt
rectbhTbvrl6uYbnc | 2021-06-14T07:47:08.000Z | PM_40_50_03 | Approvals and assurance plan | [List] | TRUE | PM_40_50_03 : Approvals and assurance plan | PM_40_50_03 : Approvals and assurance plan | Project Management | rectbhTbvrl6uYbnc
recBfZOM3BNpyQitJ | 2021-06-14T07:47:08.000Z | PM_40_50_10 | Building codes application | [List] | TRUE | PM_40_50_10 : Building codes application | PM_40_50_10 : Building codes application | Project Management | recBfZOM3BNpyQitJ
recSSyO6uW5rXPWOQ | 2021-06-14T07:47:08.000Z | PM_40_50_12 | Building codes approval | [List] | TRUE | PM_40_50_12 : Building codes approval | PM_40_50_12 : Building codes approval | Project Management | recSSyO6uW5rXPWOQ
rec8mVSZ7f6W3LVvZ | 2021-06-14T07:47:08.000Z | PM_40_50_14 | Consent | [List] | TRUE | PM_40_50_14 : Consent | PM_40_50_14 : Consent | Project Management | rec8mVSZ7f6W3LVvZ
recKpj7XVWiu2ORHL | 2021-06-14T07:47:08.000Z | PM_40_50_16 | Contribution agreement | [List] | TRUE | PM_40_50_16 : Contribution agreement | PM_40_50_16 : Contribution agreement | Project Management | recKpj7XVWiu2ORHL
reczGgDJ97a99HR5c | 2021-11-11T11:10:56.000Z | PM_40_50_21 | Design submittals | [List] | TRUE | PM_40_50_21 : Design submittals | PM_40_50_21 : Design submittals | Project Management | reczGgDJ97a99HR5c
rechiQDacqptaU1oe | 2021-06-14T07:47:08.000Z | PM_40_50_30 | Fire officer approval | [List] | TRUE | PM_40_50_30 : Fire officer approval | PM_40_50_30 : Fire officer approval | Project Management | rechiQDacqptaU1oe
recubxZZLgRxyDnoA | 2021-06-14T07:47:08.000Z | PM_40_50_32 | Funding profile | [List] | TRUE | PM_40_50_32 : Funding profile | PM_40_50_32 : Funding profile | Project Management | recubxZZLgRxyDnoA
recLjB9PmvWxrn0sw | 2021-06-14T07:47:08.000Z | PM_40_50_37 | Heritage registration | [List] | TRUE | PM_40_50_37 : Heritage registration | PM_40_50_37 : Heritage registration | Project Management | recLjB9PmvWxrn0sw
recH5K6gyxIQCV6Hb | 2021-06-14T07:47:08.000Z | PM_40_50_41 | Internal approval | [List] | TRUE | PM_40_50_41 : Internal approval | PM_40_50_41 : Internal approval | Project Management | recH5K6gyxIQCV6Hb
recRcSXM8URcJBb5y | 2021-06-14T07:47:08.000Z | PM_40_50_47 | Landowner agreement | [List] | TRUE | PM_40_50_47 : Landowner agreement | PM_40_50_47 : Landowner agreement | Project Management | recRcSXM8URcJBb5y
recjA0UIdvfB0872C | 2021-06-14T07:47:08.000Z | PM_40_50_49 | Letter of authority | [List] | TRUE | PM_40_50_49 : Letter of authority | PM_40_50_49 : Letter of authority | Project Management | recjA0UIdvfB0872C
rec7LqniUHpWVK9vV | 2021-06-14T07:47:08.000Z | PM_40_50_60 | Partnership agreement | [List] | TRUE | PM_40_50_60 : Partnership agreement | PM_40_50_60 : Partnership agreement | Project Management | rec7LqniUHpWVK9vV
recnvq9oejRYEBDRu | 2021-06-14T07:47:08.000Z | PM_40_50_63 | Planning application | [List] | TRUE | PM_40_50_63 : Planning application | PM_40_50_63 : Planning application | Project Management | recnvq9oejRYEBDRu
recfsz8BliUG3Hq1k | 2021-06-14T07:47:08.000Z | PM_40_50_64 | Planning conditions information | [List] | TRUE | PM_40_50_64 : Planning conditions information | PM_40_50_64 : Planning conditions information | Project Management | recfsz8BliUG3Hq1k
recN6aT7vzAQ6CZLB | 2021-06-14T07:47:08.000Z | PM_40_50_65 | Planning permission | [List] | TRUE | PM_40_50_65 : Planning permission | PM_40_50_65 : Planning permission | Project Management | recN6aT7vzAQ6CZLB
recbM4EoC24uWijOk | 2021-06-14T07:47:08.000Z | PM_40_50_67 | Project board agreement | [List] | TRUE | PM_40_50_67 : Project board agreement | PM_40_50_67 : Project board agreement | Project Management | recbM4EoC24uWijOk
reciMcyyXH2Z7JxI1 | 2021-06-14T07:47:08.000Z | PM_40_50_69 | Project team agreement | [List] | TRUE | PM_40_50_69 : Project team agreement | PM_40_50_69 : Project team agreement | Project Management | reciMcyyXH2Z7JxI1
recFWL08tQ1vXU1tO | 2021-06-14T07:47:08.000Z | PM_40_60 | Project information management information | [List] | TRUE | PM_40_60 : Project information management information | PM_40_60 : Project information management information | Project Management | recFWL08tQ1vXU1tO
recpSNdmHZ5QxoBAr | 2021-06-14T07:47:08.000Z | PM_40_60_01 | 4D programme federated model | [List] | TRUE | PM_40_60_01 : 4D programme federated model | PM_40_60_01 : 4D programme federated model | Project Management | recpSNdmHZ5QxoBAr
rec5nlT353CGN3IZH | 2021-06-14T07:47:08.000Z | PM_40_60_02 | 5D cost federated model | [List] | TRUE | PM_40_60_02 : 5D cost federated model | PM_40_60_02 : 5D cost federated model | Project Management | rec5nlT353CGN3IZH
recDkP0sNM24W7J4k | 2021-06-14T07:47:08.000Z | PM_40_60_03 | 6D handover sequence federated model | [List] | TRUE | PM_40_60_03 : 6D handover sequence federated model | PM_40_60_03 : 6D handover sequence federated model | Project Management | recDkP0sNM24W7J4k
rec0lI5yp9IQIBIAF | 2021-06-14T07:47:08.000Z | PM_40_60_05 | Activities terminology | [List] | TRUE | PM_40_60_05 : Activities terminology | PM_40_60_05 : Activities terminology | Project Management | rec0lI5yp9IQIBIAF
reco7VXIGsQvWlPlk | 2021-11-11T11:10:56.000Z | PM_40_60_06 | Asset delivery description | [List] | TRUE | PM_40_60_06 : Asset delivery description | PM_40_60_06 : Asset delivery description | Project Management | reco7VXIGsQvWlPlk
recjcVeWI3jNhnh2W | 2021-06-14T07:47:08.000Z | PM_40_60_07 | Benefits realization plan | [List] | TRUE | PM_40_60_07 : Benefits realization plan | PM_40_60_07 : Benefits realization plan | Project Management | recjcVeWI3jNhnh2W
recPclm5cua6Mm41C | 2021-06-14T07:47:08.000Z | PM_40_60_08 | BIM execution plan | [List] | TRUE | PM_40_60_08 : BIM execution plan | PM_40_60_08 : BIM execution plan | Project Management | recPclm5cua6Mm41C
reci4DCOAdFYGkryN | 2021-06-14T07:47:08.000Z | PM_40_60_11 | Capability and capacity assessment report | [List] | TRUE | PM_40_60_11 : Capability and capacity assessment report | PM_40_60_11 : Capability and capacity assessment report | Project Management | reci4DCOAdFYGkryN
recU2aOg0vzQgnjep | 2021-06-14T07:47:08.000Z | PM_40_60_12 | Clash detection resolution report | [List] | TRUE | PM_40_60_12 : Clash detection resolution report | PM_40_60_12 : Clash detection resolution report | Project Management | recU2aOg0vzQgnjep
recR6KVhqawmnZYOE | 2021-06-14T07:47:08.000Z | PM_40_60_16 | COBie data set | [List] | TRUE | PM_40_60_16 : COBie data set | PM_40_60_16 : COBie data set | Project Management | recR6KVhqawmnZYOE
recgtTXVVMsY8wo2l | 2021-06-14T07:47:08.000Z | PM_40_60_18 | Communications plan | [List] | TRUE | PM_40_60_18 : Communications plan | PM_40_60_18 : Communications plan | Project Management | recgtTXVVMsY8wo2l
recz1yjnNC0zTS3da | 2021-06-14T07:47:08.000Z | PM_40_60_19 | Construction risk review | [List] | TRUE | PM_40_60_19 : Construction risk review | PM_40_60_19 : Construction risk review | Project Management | recz1yjnNC0zTS3da
recG1wKQSUXxpfu6l | 2021-06-14T07:47:08.000Z | PM_40_60_20 | Contingency plan | [List] | TRUE | PM_40_60_20 : Contingency plan | PM_40_60_20 : Contingency plan | Project Management | recG1wKQSUXxpfu6l
recYe97qSGG0IrC0h | 2021-06-14T07:47:08.000Z | PM_40_60_21 | Curriculum vitae (CV) | [List] | TRUE | PM_40_60_21 : Curriculum vitae (CV) | PM_40_60_21 : Curriculum vitae (CV) | Project Management | recYe97qSGG0IrC0h
recQrRk9tw0XnDHL8 | 2021-06-14T07:47:08.000Z | PM_40_60_22 | Data security policy | [List] | TRUE | PM_40_60_22 : Data security policy | PM_40_60_22 : Data security policy | Project Management | recQrRk9tw0XnDHL8
rectXOkaBJx6b5pKn | 2021-06-14T07:47:08.000Z | PM_40_60_23 | Description terminology | [List] | TRUE | PM_40_60_23 : Description terminology | PM_40_60_23 : Description terminology | Project Management | rectXOkaBJx6b5pKn
recHOu9ab0Qfk5HHw | 2021-06-14T07:47:08.000Z | PM_40_60_24 | Detailed responsibility matrix | [List] | TRUE | PM_40_60_24 : Detailed responsibility matrix | PM_40_60_24 : Detailed responsibility matrix | Project Management | recHOu9ab0Qfk5HHw
recHJkBGZNaD9dXE7 | 2021-06-14T07:47:08.000Z | PM_40_60_25 | Design process management plan | [List] | TRUE | PM_40_60_25 : Design process management plan | PM_40_60_25 : Design process management plan | Project Management | recHJkBGZNaD9dXE7
rec7meivnRywQUeYx | 2021-06-14T07:47:08.000Z | PM_40_60_26 | Design programme | [List] | TRUE | PM_40_60_26 : Design programme | PM_40_60_26 : Design programme | Project Management | rec7meivnRywQUeYx
rec4MZRsRCvBWJ89G | 2021-06-14T07:47:08.000Z | PM_40_60_27 | Electronic data interchange (EDI) | [List] | TRUE | PM_40_60_27 : Electronic data interchange (EDI) | PM_40_60_27 : Electronic data interchange (EDI) | Project Management | rec4MZRsRCvBWJ89G
recCpKTU0z9L66cMO | 2022-01-28T12:20:29.000Z | PM_40_60_28 | Document numbering system | [List] | TRUE | PM_40_60_28 : Document numbering system | PM_40_60_28 : Document numbering system | Project Management | recCpKTU0z9L66cMO
rec2Ajj39lmjjA6FR | 2021-06-14T07:47:08.000Z | PM_40_60_31 | Federated coordination models | [List] | TRUE | PM_40_60_31 : Federated coordination models | PM_40_60_31 : Federated coordination models | Project Management | rec2Ajj39lmjjA6FR
reccDocIjwCTz0AiK | 2021-06-14T07:47:08.000Z | PM_40_60_33 | Federated information models | [List] | TRUE | PM_40_60_33 : Federated information models | PM_40_60_33 : Federated information models | Project Management | reccDocIjwCTz0AiK
recmFWjZVhko9BTAp | 2021-06-14T07:47:08.000Z | PM_40_60_38 | Information assurance | [List] | TRUE | PM_40_60_38 : Information assurance | PM_40_60_38 : Information assurance | Project Management | recmFWjZVhko9BTAp
recfPxgrHKDVKkll7 | 2021-06-14T07:47:08.000Z | PM_40_60_39 | Information validation | [List] | TRUE | PM_40_60_39 : Information validation | PM_40_60_39 : Information validation | Project Management | recfPxgrHKDVKkll7
recXLw6tPD39bYz0m | 2021-06-14T07:47:08.000Z | PM_40_60_40 | Information verification | [List] | TRUE | PM_40_60_40 : Information verification | PM_40_60_40 : Information verification | Project Management | recXLw6tPD39bYz0m
recIAX7yARcjbCua4 | 2021-06-14T07:47:08.000Z | PM_40_60_41 | Information delivery plan | [List] | TRUE | PM_40_60_41 : Information delivery plan | PM_40_60_41 : Information delivery plan | Project Management | recIAX7yARcjbCua4
recPscOLPrj1ErRmT | 2021-06-14T07:47:08.000Z | PM_40_60_43 | Installation process management plan | [List] | TRUE | PM_40_60_43 : Installation process management plan | PM_40_60_43 : Installation process management plan | Project Management | recPscOLPrj1ErRmT
recrLtFPP6xLpu7T2 | 2021-06-14T07:47:08.000Z | PM_40_60_45 | Key performance indicator (KPI) information | [List] | TRUE | PM_40_60_45 : Key performance indicator (KPI) information | PM_40_60_45 : Key performance indicator (KPI) information | Project Management | recrLtFPP6xLpu7T2
rec6whuRZkx1r2dZs | 2021-11-11T11:10:56.000Z | PM_40_60_47 | Landowner notice | [List] | TRUE | PM_40_60_47 : Landowner notice | PM_40_60_47 : Landowner notice | Project Management | rec6whuRZkx1r2dZs
recxHP69D5RWJOSLe | 2021-06-14T07:47:08.000Z | PM_40_60_50 | Master information delivery plan | [List] | TRUE | PM_40_60_50 : Master information delivery plan | PM_40_60_50 : Master information delivery plan | Project Management | recxHP69D5RWJOSLe
recBStu8qhbBNtJvG | 2021-06-14T07:47:08.000Z | PM_40_60_53 | Mobilization plan | [List] | TRUE | PM_40_60_53 : Mobilization plan | PM_40_60_53 : Mobilization plan | Project Management | recBStu8qhbBNtJvG
recy0U1baJDqXZ1i9 | 2021-06-14T07:47:08.000Z | PM_40_60_62 | Post-occupancy evaluation | [List] | TRUE | PM_40_60_62 : Post-occupancy evaluation | PM_40_60_62 : Post-occupancy evaluation | Project Management | recy0U1baJDqXZ1i9
recufYkXd5aSt37bd | 2021-06-14T07:47:08.000Z | PM_40_60_64 | Pre-appointment BIM execution plan | [List] | TRUE | PM_40_60_64 : Pre-appointment BIM execution plan | PM_40_60_64 : Pre-appointment BIM execution plan | Project Management | recufYkXd5aSt37bd
recxJGgQpc4inrZZ5 | 2021-06-14T07:47:08.000Z | PM_40_60_65 | Project execution plan | [List] | TRUE | PM_40_60_65 : Project execution plan | PM_40_60_65 : Project execution plan | Project Management | recxJGgQpc4inrZZ5
recOvn4SuC7PUm2fZ | 2021-06-14T07:47:08.000Z | PM_40_60_66 | Project information production methods and procedures | [List] | TRUE | PM_40_60_66 : Project information production methods and procedures | PM_40_60_66 : Project information production methods and procedures | Project Management | recOvn4SuC7PUm2fZ
recE04muPK7anclea | 2021-06-14T07:47:08.000Z | PM_40_60_67 | Project information protocol | [List] | TRUE | PM_40_60_67 : Project information protocol | PM_40_60_67 : Project information protocol | Project Management | recE04muPK7anclea
rec8AKS5oS8cHb9TB | 2021-06-14T07:47:08.000Z | PM_40_60_68 | Project information standards | [List] | TRUE | PM_40_60_68 : Project information standards | PM_40_60_68 : Project information standards | Project Management | rec8AKS5oS8cHb9TB
recV247rE79AqrlYD | 2021-06-14T07:47:08.000Z | PM_40_60_70 | Risk schedule | [List] | TRUE | PM_40_60_70 : Risk schedule | PM_40_60_70 : Risk schedule | Project Management | recV247rE79AqrlYD
recYAuTC7IvEPHhnv | 2021-06-14T07:47:08.000Z | PM_40_60_72 | Risk and opportunities management plan | [List] | TRUE | PM_40_60_72 : Risk and opportunities management plan | PM_40_60_72 : Risk and opportunities management plan | Project Management | recYAuTC7IvEPHhnv
recEfMEOoyOHDj4GN | 2021-06-14T07:47:08.000Z | PM_40_60_85 | Stakeholder management plan | [List] | TRUE | PM_40_60_85 : Stakeholder management plan | PM_40_60_85 : Stakeholder management plan | Project Management | recEfMEOoyOHDj4GN
recBOh2r0zDgndYMT | 2021-06-14T07:47:08.000Z | PM_40_60_87 | Task information delivery plan | [List] | TRUE | PM_40_60_87 : Task information delivery plan | PM_40_60_87 : Task information delivery plan | Project Management | recBOh2r0zDgndYMT
recZVh7mnhYiUnK6g | 2021-06-14T07:47:08.000Z | PM_40_60_89 | Through-life management plan (TLMP) | [List] | TRUE | PM_40_60_89 : Through-life management plan (TLMP) | PM_40_60_89 : Through-life management plan (TLMP) | Project Management | recZVh7mnhYiUnK6g
recj4jlClmghB6frS | 2021-06-14T07:47:08.000Z | PM_50 | Financial and commercial information | [List] | TRUE | PM_50 : Financial and commercial information | PM_50 : Financial and commercial information | Project Management | recj4jlClmghB6frS
recghFG0vD6ZKmuvl | 2021-06-14T07:47:08.000Z | PM_50_30 | Economic viability information | [List] | TRUE | PM_50_30 : Economic viability information | PM_50_30 : Economic viability information | Project Management | recghFG0vD6ZKmuvl
rec8lfy9Qx6HozAyv | 2021-06-14T07:47:08.000Z | PM_50_30_10 | Business case | [List] | TRUE | PM_50_30_10 : Business case | PM_50_30_10 : Business case | Project Management | rec8lfy9Qx6HozAyv
recEc2gzNhgVMY52E | 2021-06-14T07:47:08.000Z | PM_50_30_11 | Capital contributions information | [List] | TRUE | PM_50_30_11 : Capital contributions information | PM_50_30_11 : Capital contributions information | Project Management | recEc2gzNhgVMY52E
recUbmUOmUIjgyafZ | 2021-06-14T07:47:08.000Z | PM_50_30_12 | Commercial compliance report | [List] | TRUE | PM_50_30_12 : Commercial compliance report | PM_50_30_12 : Commercial compliance report | Project Management | recUbmUOmUIjgyafZ
rec6VWJhO70s0W20f | 2021-06-14T07:47:08.000Z | PM_50_30_14 | Commercial plan | [List] | TRUE | PM_50_30_14 : Commercial plan | PM_50_30_14 : Commercial plan | Project Management | rec6VWJhO70s0W20f
recEZ8CvvyMGQgHPi | 2021-06-14T07:47:08.000Z | PM_50_30_16 | Commercial strategy | [List] | TRUE | PM_50_30_16 : Commercial strategy | PM_50_30_16 : Commercial strategy | Project Management | recEZ8CvvyMGQgHPi
recHJKMXZCI6VnVVK | 2021-06-14T07:47:08.000Z | PM_50_30_18 | Cost model and indicative costing | [List] | TRUE | PM_50_30_18 : Cost model and indicative costing | PM_50_30_18 : Cost model and indicative costing | Project Management | recHJKMXZCI6VnVVK
recCLdiuvYPkJTFrs | 2021-06-14T07:47:08.000Z | PM_50_30_26 | Earned value management report | [List] | TRUE | PM_50_30_26 : Earned value management report | PM_50_30_26 : Earned value management report | Project Management | recCLdiuvYPkJTFrs
recjNBlggrSYQL3AE | 2021-11-11T11:10:56.000Z | PM_50_30_27 | Efficiency assessment | [List] | TRUE | PM_50_30_27 : Efficiency assessment | PM_50_30_27 : Efficiency assessment | Project Management | recjNBlggrSYQL3AE
reclrSoMt63PTc0jn | 2021-06-14T07:47:08.000Z | PM_50_30_28 | Financial damage assessment | [List] | TRUE | PM_50_30_28 : Financial damage assessment | PM_50_30_28 : Financial damage assessment | Project Management | reclrSoMt63PTc0jn
recbWVIrh2Y4hbvME | 2021-06-14T07:47:08.000Z | PM_50_30_29 | Financial strategy | [List] | TRUE | PM_50_30_29 : Financial strategy | PM_50_30_29 : Financial strategy | Project Management | recbWVIrh2Y4hbvME
rec3SfiEPRupnYSmO | 2021-06-14T07:47:08.000Z | PM_50_30_30 | Funding information | [List] | TRUE | PM_50_30_30 : Funding information | PM_50_30_30 : Funding information | Project Management | rec3SfiEPRupnYSmO
recVxXNgtX8atEt4q | 2021-06-14T07:47:08.000Z | PM_50_30_40 | Initial planning estimate | [List] | TRUE | PM_50_30_40 : Initial planning estimate | PM_50_30_40 : Initial planning estimate | Project Management | recVxXNgtX8atEt4q
recNiT27WQQjsAJe4 | 2021-06-14T07:47:08.000Z | PM_50_30_42 | Investment appraisal | [List] | TRUE | PM_50_30_42 : Investment appraisal | PM_50_30_42 : Investment appraisal | Project Management | recNiT27WQQjsAJe4
recAh0CIBDdnRxIXE | 2021-06-14T07:47:08.000Z | PM_50_30_60 | Partnership funding report | [List] | TRUE | PM_50_30_60 : Partnership funding report | PM_50_30_60 : Partnership funding report | Project Management | recAh0CIBDdnRxIXE
rec1EZhSnl0ZjpO9A | 2021-06-14T07:47:08.000Z | PM_50_30_64 | Preliminary business case | [List] | TRUE | PM_50_30_64 : Preliminary business case | PM_50_30_64 : Preliminary business case | Project Management | rec1EZhSnl0ZjpO9A
recqgYXqH5rovbIRN | 2021-06-14T07:47:08.000Z | PM_50_30_66 | Pre-tender estimate | [List] | TRUE | PM_50_30_66 : Pre-tender estimate | PM_50_30_66 : Pre-tender estimate | Project Management | recqgYXqH5rovbIRN
recWQD5sFZkFJXQIX | 2021-06-14T07:47:08.000Z | PM_50_30_68 | Private-sector participation (PSP) evaluation report | [List] | TRUE | PM_50_30_68 : Private-sector participation (PSP) evaluation report | PM_50_30_68 : Private-sector participation (PSP) evaluation report | Project Management | recWQD5sFZkFJXQIX
recxKrsM3DKsFovLG | 2021-06-14T07:47:08.000Z | PM_50_30_70 | Private-sector participation (PSP) financial close | [List] | TRUE | PM_50_30_70 : Private-sector participation (PSP) financial close | PM_50_30_70 : Private-sector participation (PSP) financial close | Project Management | recxKrsM3DKsFovLG
rec7rxHrrVSK23mZL | 2021-06-14T07:47:08.000Z | PM_50_30_85 | Supply chain agreement | [List] | TRUE | PM_50_30_85 : Supply chain agreement | PM_50_30_85 : Supply chain agreement | Project Management | rec7rxHrrVSK23mZL
rec5I4krZjEjYtSGt | 2021-06-14T07:47:08.000Z | PM_50_30_96 | Whole-life costing | [List] | TRUE | PM_50_30_96 : Whole-life costing | PM_50_30_96 : Whole-life costing | Project Management | rec5I4krZjEjYtSGt
rec5naEVJ16QTqyjD | 2021-06-14T07:47:08.000Z | PM_50_50 | Procurement and tendering information | [List] | TRUE | PM_50_50 : Procurement and tendering information | PM_50_50 : Procurement and tendering information | Project Management | rec5naEVJ16QTqyjD
recgRudBwupfKWIhF | 2021-06-14T07:47:08.000Z | PM_50_50_01 | Procurement strategy | [List] | TRUE | PM_50_50_01 : Procurement strategy | PM_50_50_01 : Procurement strategy | Project Management | recgRudBwupfKWIhF
recJe5fJuJDLDdK61 | 2021-06-14T07:47:08.000Z | PM_50_50_03 | Prior information notice | [List] | TRUE | PM_50_50_03 : Prior information notice | PM_50_50_03 : Prior information notice | Project Management | recJe5fJuJDLDdK61
recqg4LVvSFqs28vP | 2021-06-14T07:47:08.000Z | PM_50_50_05 | Advance procurement information | [List] | TRUE | PM_50_50_05 : Advance procurement information | PM_50_50_05 : Advance procurement information | Project Management | recqg4LVvSFqs28vP
recIItem8JDgx145R | 2021-06-14T07:47:08.000Z | PM_50_50_10 | Tender enquiry | [List] | TRUE | PM_50_50_10 : Tender enquiry | PM_50_50_10 : Tender enquiry | Project Management | recIItem8JDgx145R
recUcVpW86ySDcvXX | 2021-06-14T07:47:08.000Z | PM_50_50_12 | Tender programme | [List] | TRUE | PM_50_50_12 : Tender programme | PM_50_50_12 : Tender programme | Project Management | recUcVpW86ySDcvXX
recRVcupo1PGpVuxn | 2021-06-14T07:47:08.000Z | PM_50_50_15 | Tender invitation | [List] | TRUE | PM_50_50_15 : Tender invitation | PM_50_50_15 : Tender invitation | Project Management | recRVcupo1PGpVuxn
recvMKcZnuujYxqi6 | 2021-06-14T07:47:08.000Z | PM_50_50_20 | Early contractor involvement information | [List] | TRUE | PM_50_50_20 : Early contractor involvement information | PM_50_50_20 : Early contractor involvement information | Project Management | recvMKcZnuujYxqi6
recMBcHDmsbP4HHeY | 2021-06-14T07:47:08.000Z | PM_50_50_25 | Framework agreement information | [List] | TRUE | PM_50_50_25 : Framework agreement information | PM_50_50_25 : Framework agreement information | Project Management | recMBcHDmsbP4HHeY
recM39mCT62bbtWHX | 2021-06-14T07:47:08.000Z | PM_50_50_30 | Tender acceptance criteria | [List] | TRUE | PM_50_50_30 : Tender acceptance criteria | PM_50_50_30 : Tender acceptance criteria | Project Management | recM39mCT62bbtWHX
rec6BmL9G4mzTPNZZ | 2021-06-14T07:47:08.000Z | PM_50_50_35 | Tender documents | [List] | TRUE | PM_50_50_35 : Tender documents | PM_50_50_35 : Tender documents | Project Management | rec6BmL9G4mzTPNZZ
recVKrzpu2fp9d5Ki | 2021-06-14T07:47:08.000Z | PM_50_50_40 | Private-sector participation (PSP) tender | [List] | TRUE | PM_50_50_40 : Private-sector participation (PSP) tender | PM_50_50_40 : Private-sector participation (PSP) tender | Project Management | recVKrzpu2fp9d5Ki
rec7I1ssIofJeKfuc | 2021-06-14T07:47:08.000Z | PM_50_50_45 | Tender clarification report | [List] | TRUE | PM_50_50_45 : Tender clarification report | PM_50_50_45 : Tender clarification report | Project Management | rec7I1ssIofJeKfuc
recTV4KEqehLLzMYd | 2021-06-14T07:47:08.000Z | PM_50_50_50 | Tender instruction | [List] | TRUE | PM_50_50_50 : Tender instruction | PM_50_50_50 : Tender instruction | Project Management | recTV4KEqehLLzMYd
recKpyMDfapXUc1o7 | 2021-06-14T07:47:08.000Z | PM_50_50_55 | Tender site visit strategy | [List] | TRUE | PM_50_50_55 : Tender site visit strategy | PM_50_50_55 : Tender site visit strategy | Project Management | recKpyMDfapXUc1o7
recSGtaTsgMTClDIy | 2021-06-14T07:47:08.000Z | PM_50_50_60 | Tender return | [List] | TRUE | PM_50_50_60 : Tender return | PM_50_50_60 : Tender return | Project Management | recSGtaTsgMTClDIy
recAiWDEv0IEwlZ92 | 2021-06-14T07:47:08.000Z | PM_50_50_65 | Tender assessment report | [List] | TRUE | PM_50_50_65 : Tender assessment report | PM_50_50_65 : Tender assessment report | Project Management | recAiWDEv0IEwlZ92
recSLR9D1HykKmpKi | 2021-06-14T07:47:08.000Z | PM_50_50_70 | Tender evaluation report | [List] | TRUE | PM_50_50_70 : Tender evaluation report | PM_50_50_70 : Tender evaluation report | Project Management | recSLR9D1HykKmpKi
recNK2Qwt4oOrW4J2 | 2021-06-14T07:47:08.000Z | PM_50_50_75 | Tender error resolution strategy | [List] | TRUE | PM_50_50_75 : Tender error resolution strategy | PM_50_50_75 : Tender error resolution strategy | Project Management | recNK2Qwt4oOrW4J2
reczM4bEABD5nMu8z | 2021-06-14T07:47:08.000Z | PM_50_50_80 | Tender acceptance report | [List] | TRUE | PM_50_50_80 : Tender acceptance report | PM_50_50_80 : Tender acceptance report | Project Management | reczM4bEABD5nMu8z
rec49Tw0JJesdRuVr | 2021-06-14T07:47:08.000Z | PM_50_50_85 | Post-tender negotiation | [List] | TRUE | PM_50_50_85 : Post-tender negotiation | PM_50_50_85 : Post-tender negotiation | Project Management | rec49Tw0JJesdRuVr
reca64pMvTCVXkLqK | 2021-06-14T07:47:08.000Z | PM_50_50_90 | Tender notification | [List] | TRUE | PM_50_50_90 : Tender notification | PM_50_50_90 : Tender notification | Project Management | reca64pMvTCVXkLqK
recJoBvUNTVNJfnfo | 2021-06-14T07:47:08.000Z | PM_55 | Contract information | [List] | TRUE | PM_55 : Contract information | PM_55 : Contract information | Project Management | recJoBvUNTVNJfnfo
recppIe5M0gQkWTH1 | 2021-06-14T07:47:08.000Z | PM_55_15 | Contract compliance information | [List] | TRUE | PM_55_15 : Contract compliance information | PM_55_15 : Contract compliance information | Project Management | recppIe5M0gQkWTH1
recsoNiK63lN7qRej | 2021-11-11T11:10:56.000Z | PM_55_15_04 | Asset compliance information | [List] | TRUE | PM_55_15_04 : Asset compliance information | PM_55_15_04 : Asset compliance information | Project Management | recsoNiK63lN7qRej
recnMpszOhgeeJLBP | 2021-06-14T07:47:08.000Z | PM_55_15_15 | Compliance statement | [List] | TRUE | PM_55_15_15 : Compliance statement | PM_55_15_15 : Compliance statement | Project Management | recnMpszOhgeeJLBP
recOKnVfa7iKBoVCq | 2021-06-14T07:47:08.000Z | PM_55_15_17 | Contract notice | [List] | TRUE | PM_55_15_17 : Contract notice | PM_55_15_17 : Contract notice | Project Management | recOKnVfa7iKBoVCq
recouivwK9WnQeu79 | 2022-01-28T12:20:29.000Z | PM_55_15_28 | Escrow agreement | [List] | TRUE | PM_55_15_28 : Escrow agreement | PM_55_15_28 : Escrow agreement | Project Management | recouivwK9WnQeu79
recVZOMd0UJrnBpoG | 2021-06-14T07:47:08.000Z | PM_55_15_47 | Liquidated damages information | [List] | TRUE | PM_55_15_47 : Liquidated damages information | PM_55_15_47 : Liquidated damages information | Project Management | recVZOMd0UJrnBpoG
recdxFDbMckK9Taz9 | 2021-06-14T07:47:08.000Z | PM_55_15_65 | Project brief derogations | [List] | TRUE | PM_55_15_65 : Project brief derogations | PM_55_15_65 : Project brief derogations | Project Management | recdxFDbMckK9Taz9
recUqEIuFbmMQ05OA | 2021-06-14T07:47:08.000Z | PM_55_55 | Contract | [List] | TRUE | PM_55_55 : Contract | PM_55_55 : Contract | Project Management | recUqEIuFbmMQ05OA
recEZDvx83CkXlz0P | 2021-06-14T07:47:08.000Z | PM_55_55_70 | Services contract | [List] | TRUE | PM_55_55_70 : Services contract | PM_55_55_70 : Services contract | Project Management | recEZDvx83CkXlz0P
recIlLux6SgvCIKuG | 2021-06-14T07:47:08.000Z | PM_55_55_80 | Supplies contract | [List] | TRUE | PM_55_55_80 : Supplies contract | PM_55_55_80 : Supplies contract | Project Management | recIlLux6SgvCIKuG
rec9YiBosDvXEqnmo | 2021-11-11T11:10:56.000Z | PM_55_55_85 | Target cost contracts | [List] | TRUE | PM_55_55_85 : Target cost contracts | PM_55_55_85 : Target cost contracts | Project Management | rec9YiBosDvXEqnmo
reczPg2klWYA1gsNL | 2021-06-14T07:47:08.000Z | PM_55_55_90 | Works contract | [List] | TRUE | PM_55_55_90 : Works contract | PM_55_55_90 : Works contract | Project Management | reczPg2klWYA1gsNL
recIyFGvYypK34hzw | 2021-06-14T07:47:08.000Z | PM_60 | Construction management information | [List] | TRUE | PM_60 : Construction management information | PM_60 : Construction management information | Project Management | recIyFGvYypK34hzw
recP25TyM2BGxnI3j | 2021-06-14T07:47:08.000Z | PM_60_10 | Site information | [List] | TRUE | PM_60_10 : Site information | PM_60_10 : Site information | Project Management | recP25TyM2BGxnI3j
recRuouV29mueErf8 | 2021-06-14T07:47:08.000Z | PM_60_10_50 | Site access information | [List] | TRUE | PM_60_10_50 : Site access information | PM_60_10_50 : Site access information | Project Management | recRuouV29mueErf8
recFn1vSCOz5w5Dn8 | 2021-06-14T07:47:08.000Z | PM_60_10_52 | Site altitude | [List] | TRUE | PM_60_10_52 : Site altitude | PM_60_10_52 : Site altitude | Project Management | recFn1vSCOz5w5Dn8
recHDeUeyXYEe4HTy | 2021-06-14T07:47:08.000Z | PM_60_10_55 | Site branding information | [List] | TRUE | PM_60_10_55 : Site branding information | PM_60_10_55 : Site branding information | Project Management | recHDeUeyXYEe4HTy
recZ1q3OeaRMdNE0a | 2021-06-14T07:47:08.000Z | PM_60_10_58 | Site establishment information | [List] | TRUE | PM_60_10_58 : Site establishment information | PM_60_10_58 : Site establishment information | Project Management | recZ1q3OeaRMdNE0a
recUxJ3sDKmaunQq8 | 2021-06-14T07:47:08.000Z | PM_60_10_60 | Site grid reference | [List] | TRUE | PM_60_10_60 : Site grid reference | PM_60_10_60 : Site grid reference | Project Management | recUxJ3sDKmaunQq8
recqC1Gp3X0nXlBuF | 2022-01-28T12:20:29.000Z | PM_60_10_63 | Site logistics plan | [List] | TRUE | PM_60_10_63 : Site logistics plan | PM_60_10_63 : Site logistics plan | Project Management | recqC1Gp3X0nXlBuF
recAYGQdGo27vbzC8 | 2021-06-14T07:47:08.000Z | PM_60_10_65 | Site safety plan | [List] | TRUE | PM_60_10_65 : Site safety plan | PM_60_10_65 : Site safety plan | Project Management | recAYGQdGo27vbzC8
recVmkfcs69Y0ln67 | 2021-06-14T07:47:08.000Z | PM_60_10_70 | Site services information | [List] | TRUE | PM_60_10_70 : Site services information | PM_60_10_70 : Site services information | Project Management | recVmkfcs69Y0ln67
recoTZQdpKfMXx4qn | 2021-06-14T07:47:08.000Z | PM_60_10_75 | Site set-up information | [List] | TRUE | PM_60_10_75 : Site set-up information | PM_60_10_75 : Site set-up information | Project Management | recoTZQdpKfMXx4qn
recvcMZ2O4roxEehY | 2021-06-14T07:47:08.000Z | PM_60_10_77 | Site security information | [List] | TRUE | PM_60_10_77 : Site security information | PM_60_10_77 : Site security information | Project Management | recvcMZ2O4roxEehY
rec1WnlDGepex8Hnc | 2021-06-14T07:47:08.000Z | PM_60_10_80 | Surrounding land and building uses report | [List] | TRUE | PM_60_10_80 : Surrounding land and building uses report | PM_60_10_80 : Surrounding land and building uses report | Project Management | rec1WnlDGepex8Hnc
rec4mVqPlb8qsWy4M | 2021-06-14T07:47:08.000Z | PM_60_10_83 | Temporary services information | [List] | TRUE | PM_60_10_83 : Temporary services information | PM_60_10_83 : Temporary services information | Project Management | rec4mVqPlb8qsWy4M
reco9x7V2JEbHmjrc | 2021-06-14T07:47:08.000Z | PM_60_10_85 | Temporary works information | [List] | TRUE | PM_60_10_85 : Temporary works information | PM_60_10_85 : Temporary works information | Project Management | reco9x7V2JEbHmjrc
recfKt0lya1B8eZj9 | 2021-06-14T07:47:08.000Z | PM_60_10_90 | Temporary works impact report | [List] | TRUE | PM_60_10_90 : Temporary works impact report | PM_60_10_90 : Temporary works impact report | Project Management | recfKt0lya1B8eZj9
recxZRiHJ16cCPQjL | 2021-06-14T07:47:08.000Z | PM_60_10_95 | Working area information | [List] | TRUE | PM_60_10_95 : Working area information | PM_60_10_95 : Working area information | Project Management | recxZRiHJ16cCPQjL
recRsfpvZ10LSNhN5 | 2021-06-14T07:47:08.000Z | PM_60_20 | Project requirements | [List] | TRUE | PM_60_20 : Project requirements | PM_60_20 : Project requirements | Project Management | recRsfpvZ10LSNhN5
rec94eHrvQToBGmdT | 2021-06-14T07:47:08.000Z | PM_60_20_15 | Completion work information | [List] | TRUE | PM_60_20_15 : Completion work information | PM_60_20_15 : Completion work information | Project Management | rec94eHrvQToBGmdT
recbfD4R0GPQntxrH | 2021-06-14T07:47:08.000Z | PM_60_20_20 | Concurrent work information | [List] | TRUE | PM_60_20_20 : Concurrent work information | PM_60_20_20 : Concurrent work information | Project Management | recbfD4R0GPQntxrH
rec77IqRUmgfXx6cm | 2021-06-14T07:47:08.000Z | PM_60_20_22 | Construction method statement | [List] | TRUE | PM_60_20_22 : Construction method statement | PM_60_20_22 : Construction method statement | Project Management | rec77IqRUmgfXx6cm
recpXwRgO6xhZPn8J | 2021-06-14T07:47:08.000Z | PM_60_20_24 | Decant programme | [List] | TRUE | PM_60_20_24 : Decant programme | PM_60_20_24 : Decant programme | Project Management | recpXwRgO6xhZPn8J
rec7qKihvG7mVmOYL | 2021-06-14T07:47:08.000Z | PM_60_20_26 | Decant protocol | [List] | TRUE | PM_60_20_26 : Decant protocol | PM_60_20_26 : Decant protocol | Project Management | rec7qKihvG7mVmOYL
recccx5GheCXahtSZ | 2021-06-14T07:47:08.000Z | PM_60_20_55 | Nominated subcontractor or supplier work information | [List] | TRUE | PM_60_20_55 : Nominated subcontractor or supplier work information | PM_60_20_55 : Nominated subcontractor or supplier work information | Project Management | recccx5GheCXahtSZ
recDUN3GSrqsiHLh7 | 2021-06-14T07:47:08.000Z | PM_60_20_60 | Pre-construction information | [List] | TRUE | PM_60_20_60 : Pre-construction information | PM_60_20_60 : Pre-construction information | Project Management | recDUN3GSrqsiHLh7
recmbkpzHqGfG6C6h | 2021-06-14T07:47:08.000Z | PM_60_20_62 | Pre-ordered items information | [List] | TRUE | PM_60_20_62 : Pre-ordered items information | PM_60_20_62 : Pre-ordered items information | Project Management | recmbkpzHqGfG6C6h
recsf6I4NMgF7D2FN | 2021-06-14T07:47:08.000Z | PM_60_20_64 | Prime cost item | [List] | TRUE | PM_60_20_64 : Prime cost item | PM_60_20_64 : Prime cost item | Project Management | recsf6I4NMgF7D2FN
recK6rzSkZK6mWThc | 2021-06-14T07:47:08.000Z | PM_60_20_65 | Preparatory work information | [List] | TRUE | PM_60_20_65 : Preparatory work information | PM_60_20_65 : Preparatory work information | Project Management | recK6rzSkZK6mWThc
recS7op0wjwLXt4RG | 2021-06-14T07:47:08.000Z | PM_60_20_67 | Provisional item | [List] | TRUE | PM_60_20_67 : Provisional item | PM_60_20_67 : Provisional item | Project Management | recS7op0wjwLXt4RG
recCvyT6dHzPmfWYj | 2021-11-11T11:10:56.000Z | PM_60_20_70 | Red, amber, green (RAG) list compliance | [List] | TRUE | PM_60_20_70 : Red, amber, green (RAG) list compliance | PM_60_20_70 : Red, amber, green (RAG) list compliance | Project Management | recCvyT6dHzPmfWYj
rec6E5L5x1YUPmE8H | 2022-01-28T12:20:29.000Z | PM_60_20_73 | Reuse and recycling information | [List] | TRUE | PM_60_20_73 : Reuse and recycling information | PM_60_20_73 : Reuse and recycling information | Project Management | rec6E5L5x1YUPmE8H
rectV8Qg59d7MjVfT | 2021-06-14T07:47:08.000Z | PM_60_20_79 | Setting out methodology | [List] | TRUE | PM_60_20_79 : Setting out methodology | PM_60_20_79 : Setting out methodology | Project Management | rectV8Qg59d7MjVfT
recR7iXwkwRM7piWs | 2021-06-14T07:47:08.000Z | PM_60_20_90 | Works by local authority information | [List] | TRUE | PM_60_20_90 : Works by local authority information | PM_60_20_90 : Works by local authority information | Project Management | recR7iXwkwRM7piWs
rec0b1OWOnW9cWtVO | 2021-06-14T07:47:08.000Z | PM_60_20_95 | Work by statutory undertakers information | [List] | TRUE | PM_60_20_95 : Work by statutory undertakers information | PM_60_20_95 : Work by statutory undertakers information | Project Management | rec0b1OWOnW9cWtVO
recjurCm7jsu0GCXB | 2021-06-14T07:47:08.000Z | PM_60_25 | Construction models | [List] | TRUE | PM_60_25 : Construction models | PM_60_25 : Construction models | Project Management | recjurCm7jsu0GCXB
recLLABsG45QLIR8Y | 2021-06-14T07:47:08.000Z | PM_60_25_83 | Structural fabrication models | [List] | TRUE | PM_60_25_83 : Structural fabrication models | PM_60_25_83 : Structural fabrication models | Project Management | recLLABsG45QLIR8Y
recMgPhmyBag8WbMs | 2021-06-14T07:47:08.000Z | PM_60_30 | Contract programme and progress | [List] | TRUE | PM_60_30 : Contract programme and progress | PM_60_30 : Contract programme and progress | Project Management | recMgPhmyBag8WbMs
recqfypZObHGMTTiY | 2021-06-14T07:47:08.000Z | PM_60_30_05 | Actions log | [List] | TRUE | PM_60_30_05 : Actions log | PM_60_30_05 : Actions log | Project Management | recqfypZObHGMTTiY
recysBv9oqnk7nUM7 | 2021-06-14T07:47:08.000Z | PM_60_30_13 | Commissioning programme | [List] | TRUE | PM_60_30_13 : Commissioning programme | PM_60_30_13 : Commissioning programme | Project Management | recysBv9oqnk7nUM7
recUtbyeXQ8nwJbrk | 2021-06-14T07:47:08.000Z | PM_60_30_15 | Contract communications log | [List] | TRUE | PM_60_30_15 : Contract communications log | PM_60_30_15 : Contract communications log | Project Management | recUtbyeXQ8nwJbrk
recip3dhLIrQGOLXU | 2021-06-14T07:47:08.000Z | PM_60_30_17 | Contract consultation strategy | [List] | TRUE | PM_60_30_17 : Contract consultation strategy | PM_60_30_17 : Contract consultation strategy | Project Management | recip3dhLIrQGOLXU
recfAFm9QxzjFfEhJ | 2021-06-14T07:47:08.000Z | PM_60_30_19 | Contract administration information | [List] | TRUE | PM_60_30_19 : Contract administration information | PM_60_30_19 : Contract administration information | Project Management | recfAFm9QxzjFfEhJ
recHyklS6VJiwXxCC | 2021-06-14T07:47:08.000Z | PM_60_30_20 | Contract programme | [List] | TRUE | PM_60_30_20 : Contract programme | PM_60_30_20 : Contract programme | Project Management | recHyklS6VJiwXxCC
recuYpdas6Q5AT4ps | 2021-06-14T07:47:08.000Z | PM_60_30_22 | Delivery risk review | [List] | TRUE | PM_60_30_22 : Delivery risk review | PM_60_30_22 : Delivery risk review | Project Management | recuYpdas6Q5AT4ps
reclgIZmB0R620ziV | 2021-06-14T07:47:08.000Z | PM_60_30_26 | Early warning notice | [List] | TRUE | PM_60_30_26 : Early warning notice | PM_60_30_26 : Early warning notice | Project Management | reclgIZmB0R620ziV
rec5yfbLYGUgGunZi | 2021-06-14T07:47:08.000Z | PM_60_30_28 | Exception report | [List] | TRUE | PM_60_30_28 : Exception report | PM_60_30_28 : Exception report | Project Management | rec5yfbLYGUgGunZi
rec913laHl1trLcje | 2021-06-14T07:47:08.000Z | PM_60_30_37 | Highlights report | [List] | TRUE | PM_60_30_37 : Highlights report | PM_60_30_37 : Highlights report | Project Management | rec913laHl1trLcje
rectnhhw1afEsofYp | 2021-06-14T07:47:08.000Z | PM_60_30_40 | Issues log | [List] | TRUE | PM_60_30_40 : Issues log | PM_60_30_40 : Issues log | Project Management | rectnhhw1afEsofYp
recRNN8CfRQ3eX6Hp | 2021-06-14T07:47:08.000Z | PM_60_30_45 | Limitations on method report | [List] | TRUE | PM_60_30_45 : Limitations on method report | PM_60_30_45 : Limitations on method report | Project Management | recRNN8CfRQ3eX6Hp
recQ75QyZbT2A48wF | 2021-06-14T07:47:08.000Z | PM_60_30_47 | Limitations on sequence report | [List] | TRUE | PM_60_30_47 : Limitations on sequence report | PM_60_30_47 : Limitations on sequence report | Project Management | recQ75QyZbT2A48wF
reckbx1g1A7iJYmoS | 2021-06-14T07:47:08.000Z | PM_60_30_49 | Limitations on timing report | [List] | TRUE | PM_60_30_49 : Limitations on timing report | PM_60_30_49 : Limitations on timing report | Project Management | reckbx1g1A7iJYmoS
recrex2niRBZnILXN | 2021-06-14T07:47:08.000Z | PM_60_30_51 | Limitations on use of site report | [List] | TRUE | PM_60_30_51 : Limitations on use of site report | PM_60_30_51 : Limitations on use of site report | Project Management | recrex2niRBZnILXN
recSEAn19WLEO0WhV | 2021-06-14T07:47:08.000Z | PM_60_30_57 | Notice of commencement | [List] | TRUE | PM_60_30_57 : Notice of commencement | PM_60_30_57 : Notice of commencement | Project Management | recSEAn19WLEO0WhV
rec2SQRNDHFulvRgh | 2021-06-14T07:47:08.000Z | PM_60_30_66 | Progress report | [List] | TRUE | PM_60_30_66 : Progress report | PM_60_30_66 : Progress report | Project Management | rec2SQRNDHFulvRgh
recK8uGayU454r5Sy | 2021-06-14T07:47:08.000Z | PM_60_30_71 | Request for information (RFI) | [List] | TRUE | PM_60_30_71 : Request for information (RFI) | PM_60_30_71 : Request for information (RFI) | Project Management | recK8uGayU454r5Sy
recGu3SxD1CjoPzS9 | 2021-06-14T07:47:08.000Z | PM_60_30_73 | Responsible, accountable, consulted and informed (RACI) log | [List] | TRUE | PM_60_30_73 : Responsible, accountable, consulted and informed (RACI) log | PM_60_30_73 : Responsible, accountable, consulted and informed (RACI) log | Project Management | recGu3SxD1CjoPzS9
recSEXGOBLjulL35A | 2021-06-14T07:47:08.000Z | PM_60_30_80 | Stage end report | [List] | TRUE | PM_60_30_80 : Stage end report | PM_60_30_80 : Stage end report | Project Management | recSEXGOBLjulL35A
recnW6j1n6QO7KqaQ | 2021-06-14T07:47:08.000Z | PM_60_40 | Meetings and records | [List] | TRUE | PM_60_40 : Meetings and records | PM_60_40 : Meetings and records | Project Management | recnW6j1n6QO7KqaQ
recKQF2ndE8gBQUGQ | 2021-11-11T11:10:56.000Z | PM_60_40_05 | Accident report | [List] | TRUE | PM_60_40_05 : Accident report | PM_60_40_05 : Accident report | Project Management | recKQF2ndE8gBQUGQ
recG4Bla7fYSGecTe | 2021-06-14T07:47:08.000Z | PM_60_40_40 | Labour and equipment record | [List] | TRUE | PM_60_40_40 : Labour and equipment record | PM_60_40_40 : Labour and equipment record | Project Management | recG4Bla7fYSGecTe
recHaq2xDHH6rkk5e | 2021-06-14T07:47:08.000Z | PM_60_40_50 | Meeting agenda | [List] | TRUE | PM_60_40_50 : Meeting agenda | PM_60_40_50 : Meeting agenda | Project Management | recHaq2xDHH6rkk5e
recMwtW9KOIDzx3Cw | 2021-06-14T07:47:08.000Z | PM_60_40_55 | Meeting minutes | [List] | TRUE | PM_60_40_55 : Meeting minutes | PM_60_40_55 : Meeting minutes | Project Management | recMwtW9KOIDzx3Cw
reczQRraEEfYSMg8N | 2021-06-14T07:47:08.000Z | PM_60_40_58 | Progress photographs | [List] | TRUE | PM_60_40_58 : Progress photographs | PM_60_40_58 : Progress photographs | Project Management | reczQRraEEfYSMg8N
rectrEFHRMeB08YgQ | 2021-06-14T07:47:08.000Z | PM_60_40_60 | Progress record | [List] | TRUE | PM_60_40_60 : Progress record | PM_60_40_60 : Progress record | Project Management | rectrEFHRMeB08YgQ
recK5jtdsDG4uRxfo | 2021-06-14T07:47:08.000Z | PM_60_40_70 | Record photographs | [List] | TRUE | PM_60_40_70 : Record photographs | PM_60_40_70 : Record photographs | Project Management | recK5jtdsDG4uRxfo
rec1BTsL959nFVuhw | 2021-11-11T11:10:56.000Z | PM_60_40_72 | Risk register | [List] | TRUE | PM_60_40_72 : Risk register | PM_60_40_72 : Risk register | Project Management | rec1BTsL959nFVuhw
rec2GNNZ7hYJ8AHkf | 2021-06-14T07:47:08.000Z | PM_60_50 | Contract cost management | [List] | TRUE | PM_60_50 : Contract cost management | PM_60_50 : Contract cost management | Project Management | rec2GNNZ7hYJ8AHkf
rec3AdNOjSODLJtBF | 2021-06-14T07:47:08.000Z | PM_60_50_10 | Budget | [List] | TRUE | PM_60_50_10 : Budget | PM_60_50_10 : Budget | Project Management | rec3AdNOjSODLJtBF
recbis4023tfdC49P | 2021-06-14T07:47:08.000Z | PM_60_50_12 | Cash flow forecast | [List] | TRUE | PM_60_50_12 : Cash flow forecast | PM_60_50_12 : Cash flow forecast | Project Management | recbis4023tfdC49P
reciDUGvJ1nY5V03x | 2021-06-14T07:47:08.000Z | PM_60_50_16 | Compensation event | [List] | TRUE | PM_60_50_16 : Compensation event | PM_60_50_16 : Compensation event | Project Management | reciDUGvJ1nY5V03x
rec6fIIdValnExeya | 2021-06-14T07:47:08.000Z | PM_60_50_17 | Completion certificate | [List] | TRUE | PM_60_50_17 : Completion certificate | PM_60_50_17 : Completion certificate | Project Management | rec6fIIdValnExeya
recCbh9miyXvFuLOV | 2021-06-14T07:47:08.000Z | PM_60_50_19 | Contract change to forecast | [List] | TRUE | PM_60_50_19 : Contract change to forecast | PM_60_50_19 : Contract change to forecast | Project Management | recCbh9miyXvFuLOV
receapISzhlgCkH3r | 2021-11-11T11:10:56.000Z | PM_60_50_20 | Contract instruction | [List] | TRUE | PM_60_50_20 : Contract instruction | PM_60_50_20 : Contract instruction | Project Management | receapISzhlgCkH3r
recuRhq9PM4qRJNK3 | 2021-06-14T07:47:08.000Z | PM_60_50_23 | Cost estimate | [List] | TRUE | PM_60_50_23 : Cost estimate | PM_60_50_23 : Cost estimate | Project Management | recuRhq9PM4qRJNK3
recbEN1mNuUd2bLdj | 2021-06-14T07:47:08.000Z | PM_60_50_25 | Cost forecast | [List] | TRUE | PM_60_50_25 : Cost forecast | PM_60_50_25 : Cost forecast | Project Management | recbEN1mNuUd2bLdj
recEfAqhRa5g59JQY | 2021-06-14T07:47:08.000Z | PM_60_50_27 | Cost information report | [List] | TRUE | PM_60_50_27 : Cost information report | PM_60_50_27 : Cost information report | Project Management | recEfAqhRa5g59JQY
recaNO7BhNzO3I3Qv | 2021-06-14T07:47:08.000Z | PM_60_50_35 | Fee note | [List] | TRUE | PM_60_50_35 : Fee note | PM_60_50_35 : Fee note | Project Management | recaNO7BhNzO3I3Qv
reciIUyWnBAiY5eu4 | 2021-06-14T07:47:08.000Z | PM_60_50_37 | Financial report | [List] | TRUE | PM_60_50_37 : Financial report | PM_60_50_37 : Financial report | Project Management | reciIUyWnBAiY5eu4
recZN9gJxZ0vs4I0F | 2021-06-14T07:47:08.000Z | PM_60_50_50 | Milestone payment schedule | [List] | TRUE | PM_60_50_50 : Milestone payment schedule | PM_60_50_50 : Milestone payment schedule | Project Management | recZN9gJxZ0vs4I0F
rec3gWzWgx9zpdQMk | 2021-06-14T07:47:08.000Z | PM_60_50_58 | Order | [List] | TRUE | PM_60_50_58 : Order | PM_60_50_58 : Order | Project Management | rec3gWzWgx9zpdQMk
recPAXGo8LsXsRRLr | 2021-06-14T07:47:08.000Z | PM_60_50_60 | Payment application | [List] | TRUE | PM_60_50_60 : Payment application | PM_60_50_60 : Payment application | Project Management | recPAXGo8LsXsRRLr
recEedXESyLRjzMEQ | 2021-06-14T07:47:08.000Z | PM_60_50_62 | Payment certificate | [List] | TRUE | PM_60_50_62 : Payment certificate | PM_60_50_62 : Payment certificate | Project Management | recEedXESyLRjzMEQ
recZbM5DougLha1En | 2021-06-14T07:47:08.000Z | PM_60_50_63 | Pricing document | [List] | TRUE | PM_60_50_63 : Pricing document | PM_60_50_63 : Pricing document | Project Management | recZbM5DougLha1En
recPHUKjpB240hqai | 2021-06-14T07:47:08.000Z | PM_60_50_67 | Purchasing protocol | [List] | TRUE | PM_60_50_67 : Purchasing protocol | PM_60_50_67 : Purchasing protocol | Project Management | recPHUKjpB240hqai
recgflbuafLOUfbS5 | 2021-06-14T07:47:08.000Z | PM_60_50_69 | Quotation | [List] | TRUE | PM_60_50_69 : Quotation | PM_60_50_69 : Quotation | Project Management | recgflbuafLOUfbS5
rec0wXrfPxipWp66K | 2021-06-14T07:47:08.000Z | PM_60_50_88 | Technical query | [List] | TRUE | PM_60_50_88 : Technical query | PM_60_50_88 : Technical query | Project Management | rec0wXrfPxipWp66K
recrjv6bxDC3v6iI5 | 2021-06-14T07:47:08.000Z | PM_60_50_90 | Timesheet | [List] | TRUE | PM_60_50_90 : Timesheet | PM_60_50_90 : Timesheet | Project Management | recrjv6bxDC3v6iI5
recGtvJYvm68SfvZP | 2021-06-14T07:47:08.000Z | PM_60_60 | Contract support information | [List] | TRUE | PM_60_60 : Contract support information | PM_60_60 : Contract support information | Project Management | recGtvJYvm68SfvZP
recmodxCpcMIt6lIX | 2021-06-14T07:47:08.000Z | PM_60_60_15 | Contract contacts list | [List] | TRUE | PM_60_60_15 : Contract contacts list | PM_60_60_15 : Contract contacts list | Project Management | recmodxCpcMIt6lIX
reccm1lFEiltUlbgR | 2021-06-14T07:47:08.000Z | PM_60_60_26 | Environmental protection information | [List] | TRUE | PM_60_60_26 : Environmental protection information | PM_60_60_26 : Environmental protection information | Project Management | reccm1lFEiltUlbgR
reckvvtD8H1DULlyc | 2021-06-14T07:47:08.000Z | PM_60_60_40 | Insurance policies and records | [List] | TRUE | PM_60_60_40 : Insurance policies and records | PM_60_60_40 : Insurance policies and records | Project Management | reckvvtD8H1DULlyc
reccnU8XiSNxXYzVF | 2021-11-11T11:10:56.000Z | PM_60_60_44 | Lifting plan | [List] | TRUE | PM_60_60_44 : Lifting plan | PM_60_60_44 : Lifting plan | Project Management | reccnU8XiSNxXYzVF
recOcpYce7HEtyg6D | 2021-11-11T11:10:56.000Z | PM_60_60_55 | Permit to work | [List] | TRUE | PM_60_60_55 : Permit to work | PM_60_60_55 : Permit to work | Project Management | recOcpYce7HEtyg6D
recUVeHJ3ek8EdTzM | 2021-11-11T11:10:56.000Z | PM_60_60_58 | Site communication plan | [List] | TRUE | PM_60_60_58 : Site communication plan | PM_60_60_58 : Site communication plan | Project Management | recUVeHJ3ek8EdTzM
reck0k1EFwDCCcdEI | 2021-06-14T07:47:08.000Z | PM_60_60_60 | Site control and protection information | [List] | TRUE | PM_60_60_60 : Site control and protection information | PM_60_60_60 : Site control and protection information | Project Management | reck0k1EFwDCCcdEI
reccFxLcrklHlnx1v | 2021-06-14T07:47:08.000Z | PM_60_60_63 | Site organization chart | [List] | TRUE | PM_60_60_63 : Site organization chart | PM_60_60_63 : Site organization chart | Project Management | reccFxLcrklHlnx1v
recwPoM93rQMGlD9G | 2021-06-14T07:47:08.000Z | PM_60_60_65 | Site personnel records | [List] | TRUE | PM_60_60_65 : Site personnel records | PM_60_60_65 : Site personnel records | Project Management | recwPoM93rQMGlD9G
recSck5f1pGCYxWLp | 2021-06-14T07:47:08.000Z | PM_60_60_70 | Site records | [List] | TRUE | PM_60_60_70 : Site records | PM_60_60_70 : Site records | Project Management | recSck5f1pGCYxWLp
recrSHLV2YrrnWl8Y | 2021-06-14T07:47:08.000Z | PM_60_60_75 | Site safety information | [List] | TRUE | PM_60_60_75 : Site safety information | PM_60_60_75 : Site safety information | Project Management | recrSHLV2YrrnWl8Y
recepK2wUvkLmvHC3 | 2021-06-14T07:47:08.000Z | PM_60_60_78 | Site waste management plan | [List] | TRUE | PM_60_60_78 : Site waste management plan | PM_60_60_78 : Site waste management plan | Project Management | recepK2wUvkLmvHC3
rechKryZg7gCvawiV | 2021-06-14T07:47:08.000Z | PM_60_60_88 | Temporary services records | [List] | TRUE | PM_60_60_88 : Temporary services records | PM_60_60_88 : Temporary services records | Project Management | rechKryZg7gCvawiV
recL5lbHp6dyTfBPT | 2021-06-14T07:47:08.000Z | PM_60_60_90 | Temporary works records | [List] | TRUE | PM_60_60_90 : Temporary works records | PM_60_60_90 : Temporary works records | Project Management | recL5lbHp6dyTfBPT
recet50JA5iktxlqg | 2021-11-11T11:10:56.000Z | PM_60_60_96 | Winch operation plan | [List] | TRUE | PM_60_60_96 : Winch operation plan | PM_60_60_96 : Winch operation plan | Project Management | recet50JA5iktxlqg
rec9RdREPdxlO0nLd | 2021-11-11T11:10:56.000Z | PM_60_60_98 | Work equipment report | [List] | TRUE | PM_60_60_98 : Work equipment report | PM_60_60_98 : Work equipment report | Project Management | rec9RdREPdxlO0nLd
recOEi1VZ3QG8k0wP | 2021-06-14T07:47:08.000Z | PM_60_70 | Construction risk management | [List] | TRUE | PM_60_70 : Construction risk management | PM_60_70 : Construction risk management | Project Management | recOEi1VZ3QG8k0wP
recnOiwY0Ofv1NNaU | 2021-11-11T11:10:56.000Z | PM_60_70_15 | Construction notification report | [List] | TRUE | PM_60_70_15 : Construction notification report | PM_60_70_15 : Construction notification report | Project Management | recnOiwY0Ofv1NNaU
rec0vxYyYP03GXA0V | 2021-06-14T07:47:08.000Z | PM_60_70_17 | Construction phase health and safety plan | [List] | TRUE | PM_60_70_17 : Construction phase health and safety plan | PM_60_70_17 : Construction phase health and safety plan | Project Management | rec0vxYyYP03GXA0V
recAqp2ykP91ZD1jl | 2021-11-11T11:10:56.000Z | PM_60_70_18 | Construction phase risk assessment report | [List] | TRUE | PM_60_70_18 : Construction phase risk assessment report | PM_60_70_18 : Construction phase risk assessment report | Project Management | recAqp2ykP91ZD1jl
recIXduHJa5tqRmcP | 2021-06-14T07:47:08.000Z | PM_60_70_20 | Demolition hazard report | [List] | TRUE | PM_60_70_20 : Demolition hazard report | PM_60_70_20 : Demolition hazard report | Project Management | recIXduHJa5tqRmcP
recjGWL71YO3D6CxU | 2021-06-14T07:47:08.000Z | PM_60_70_23 | Environmental management plan | [List] | TRUE | PM_60_70_23 : Environmental management plan | PM_60_70_23 : Environmental management plan | Project Management | recjGWL71YO3D6CxU
recNZ7hAuKDZwhL5X | 2021-06-14T07:47:08.000Z | PM_60_70_25 | Execution hazard report | [List] | TRUE | PM_60_70_25 : Execution hazard report | PM_60_70_25 : Execution hazard report | Project Management | recNZ7hAuKDZwhL5X
recRlHMVtfUos5D7s | 2021-11-11T11:10:56.000Z | PM_60_70_38 | Health and safety audit report | [List] | TRUE | PM_60_70_38 : Health and safety audit report | PM_60_70_38 : Health and safety audit report | Project Management | recRlHMVtfUos5D7s
recdFdf0gfceYtbc9 | 2021-06-14T07:47:08.000Z | PM_60_70_40 | Health and safety statement | [List] | TRUE | PM_60_70_40 : Health and safety statement | PM_60_70_40 : Health and safety statement | Project Management | recdFdf0gfceYtbc9
recpR8qqUFJZmWNTt | 2021-06-14T07:47:08.000Z | PM_60_70_60 | Product hazard report | [List] | TRUE | PM_60_70_60 : Product hazard report | PM_60_70_60 : Product hazard report | Project Management | recpR8qqUFJZmWNTt
recYWpylm9EHEhaie | 2021-11-11T11:10:56.000Z | PM_60_70_66 | Safety, health, environment and wellbeing (SHEW) reports | [List] | TRUE | PM_60_70_66 : Safety, health, environment and wellbeing (SHEW) reports | PM_60_70_66 : Safety, health, environment and wellbeing (SHEW) reports | Project Management | recYWpylm9EHEhaie
rec5HLpz3lG4CMWT3 | 2021-11-11T11:10:56.000Z | PM_60_70_68 | Site hazard report | [List] | TRUE | PM_60_70_68 : Site hazard report | PM_60_70_68 : Site hazard report | Project Management | rec5HLpz3lG4CMWT3
recOqyuxx6e3DZsFL | 2021-06-14T07:47:08.000Z | PM_60_70_70 | Site risk assessment | [List] | TRUE | PM_60_70_70 : Site risk assessment | PM_60_70_70 : Site risk assessment | Project Management | recOqyuxx6e3DZsFL
rec3swyFCnxbuvnaY | 2021-06-14T07:47:08.000Z | PM_60_70_72 | Site risk report | [List] | TRUE | PM_60_70_72 : Site risk report | PM_60_70_72 : Site risk report | Project Management | rec3swyFCnxbuvnaY
recysRIBbCSYWbXsO | 2021-06-14T07:47:08.000Z | PM_60_70_75 | Site security policy | [List] | TRUE | PM_60_70_75 : Site security policy | PM_60_70_75 : Site security policy | Project Management | recysRIBbCSYWbXsO
rec4Ah20nKnUr9vpx | 2021-06-14T07:47:08.000Z | PM_60_70_80 | Social responsibility registration scheme | [List] | TRUE | PM_60_70_80 : Social responsibility registration scheme | PM_60_70_80 : Social responsibility registration scheme | Project Management | rec4Ah20nKnUr9vpx
recsgwPAA4E6tG4Cw | 2021-06-14T07:47:08.000Z | PM_60_70_93 | Vehicle safety report | [List] | TRUE | PM_60_70_93 : Vehicle safety report | PM_60_70_93 : Vehicle safety report | Project Management | recsgwPAA4E6tG4Cw
recRxg6ysECMs8mAj | 2021-06-14T07:47:08.000Z | PM_60_70_95 | Welfare responsibility registration scheme | [List] | TRUE | PM_60_70_95 : Welfare responsibility registration scheme | PM_60_70_95 : Welfare responsibility registration scheme | Project Management | recRxg6ysECMs8mAj
rech3tcqw5yVpBCnJ | 2021-06-14T07:47:08.000Z | PM_60_90 | Contract quality standards information | [List] | TRUE | PM_60_90 : Contract quality standards information | PM_60_90 : Contract quality standards information | Project Management | rech3tcqw5yVpBCnJ
recPTrWM5yiqfXD7C | 2021-06-14T07:47:08.000Z | PM_60_90_40 | Site inspection report | [List] | TRUE | PM_60_90_40 : Site inspection report | PM_60_90_40 : Site inspection report | Project Management | recPTrWM5yiqfXD7C
recfTYsTuYI9sAQYO | 2021-11-11T11:10:56.000Z | PM_60_90_46 | Lessons learned logs | [List] | TRUE | PM_60_90_46 : Lessons learned logs | PM_60_90_46 : Lessons learned logs | Project Management | recfTYsTuYI9sAQYO
recrmyfDVkPlJg3uK | 2021-11-11T11:10:56.000Z | PM_60_90_47 | Lessons learned report | [List] | TRUE | PM_60_90_47 : Lessons learned report | PM_60_90_47 : Lessons learned report | Project Management | recrmyfDVkPlJg3uK
rec4D9kJIP7CmqsrX | 2021-06-14T07:47:08.000Z | PM_60_90_70 | Quality control and management report | [List] | TRUE | PM_60_90_70 : Quality control and management report | PM_60_90_70 : Quality control and management report | Project Management | rec4D9kJIP7CmqsrX
rec1jDk89nwi5HcQS | 2021-06-14T07:47:08.000Z | PM_70 | Testing, commissioning and completion information | [List] | TRUE | PM_70 : Testing, commissioning and completion information | PM_70 : Testing, commissioning and completion information | Project Management | rec1jDk89nwi5HcQS
recBd8HHGFc30BkuF | 2021-06-14T07:47:08.000Z | PM_70_15 | Compliance and certification documents | [List] | TRUE | PM_70_15 : Compliance and certification documents | PM_70_15 : Compliance and certification documents | Project Management | recBd8HHGFc30BkuF
recQjh2zjs5XRvjDe | 2021-06-14T07:47:08.000Z | PM_70_15_01 | Acoustic test certificate | [List] | TRUE | PM_70_15_01 : Acoustic test certificate | PM_70_15_01 : Acoustic test certificate | Project Management | recQjh2zjs5XRvjDe
recZ423xecaFeqNpL | 2021-06-14T07:47:08.000Z | PM_70_15_04 | Asbestos clearance certificate | [List] | TRUE | PM_70_15_04 : Asbestos clearance certificate | PM_70_15_04 : Asbestos clearance certificate | Project Management | recZ423xecaFeqNpL
recT7wwhVlmZlmAlr | 2021-06-14T07:47:08.000Z | PM_70_15_07 | Building control completion certificate | [List] | TRUE | PM_70_15_07 : Building control completion certificate | PM_70_15_07 : Building control completion certificate | Project Management | recT7wwhVlmZlmAlr
rec50V04SfQaKaKhD | 2021-06-14T07:47:08.000Z | PM_70_15_08 | Building control occupation certificate | [List] | TRUE | PM_70_15_08 : Building control occupation certificate | PM_70_15_08 : Building control occupation certificate | Project Management | rec50V04SfQaKaKhD
recVJHbbaDc13XgCe | 2021-06-14T07:47:08.000Z | PM_70_15_11 | Cabling test certificate | [List] | TRUE | PM_70_15_11 : Cabling test certificate | PM_70_15_11 : Cabling test certificate | Project Management | recVJHbbaDc13XgCe
recjIeIVvTooNdWzZ | 2021-06-14T07:47:08.000Z | PM_70_15_12 | Certificate of making good defects | [List] | TRUE | PM_70_15_12 : Certificate of making good defects | PM_70_15_12 : Certificate of making good defects | Project Management | recjIeIVvTooNdWzZ
recO2oGlfty8oySyQ | 2021-06-14T07:47:08.000Z | PM_70_15_13 | Chlorination certificate | [List] | TRUE | PM_70_15_13 : Chlorination certificate | PM_70_15_13 : Chlorination certificate | Project Management | recO2oGlfty8oySyQ
recLyaoetkK60Ymir | 2021-06-14T07:47:08.000Z | PM_70_15_16 | Control of legionella certificate | [List] | TRUE | PM_70_15_16 : Control of legionella certificate | PM_70_15_16 : Control of legionella certificate | Project Management | recLyaoetkK60Ymir
reclo7qchCYAAyEBI | 2022-01-28T12:20:29.000Z | PM_70_15_21 | Demolition certificate | [List] | TRUE | PM_70_15_21 : Demolition certificate | PM_70_15_21 : Demolition certificate | Project Management | reclo7qchCYAAyEBI
recWBbGiqP9D0nBMd | 2021-06-14T07:47:08.000Z | PM_70_15_23 | Disinfection and sterilization certificate | [List] | TRUE | PM_70_15_23 : Disinfection and sterilization certificate | PM_70_15_23 : Disinfection and sterilization certificate | Project Management | recWBbGiqP9D0nBMd
rec8V5GllIrW1jioe | 2021-06-14T07:47:08.000Z | PM_70_15_24 | Distribution network operator (DNO) notification certificate | [List] | TRUE | PM_70_15_24 : Distribution network operator (DNO) notification certificate | PM_70_15_24 : Distribution network operator (DNO) notification certificate | Project Management | rec8V5GllIrW1jioe
recOPAw6xeq9UQ6bv | 2021-06-14T07:47:08.000Z | PM_70_15_25 | Emergency lighting certificate | [List] | TRUE | PM_70_15_25 : Emergency lighting certificate | PM_70_15_25 : Emergency lighting certificate | Project Management | recOPAw6xeq9UQ6bv
recXzA3TO21rTJ9Z0 | 2021-06-14T07:47:08.000Z | PM_70_15_26 | Environmental completion certificate | [List] | TRUE | PM_70_15_26 : Environmental completion certificate | PM_70_15_26 : Environmental completion certificate | Project Management | recXzA3TO21rTJ9Z0
recurW6c43I5DZwtZ | 2021-06-14T07:47:08.000Z | PM_70_15_27 | Electrical test certificate | [List] | TRUE | PM_70_15_27 : Electrical test certificate | PM_70_15_27 : Electrical test certificate | Project Management | recurW6c43I5DZwtZ
recWAPJoyxSeBXnKr | 2021-06-14T07:47:08.000Z | PM_70_15_28 | Fire alarm electrical supply test certificate | [List] | TRUE | PM_70_15_28 : Fire alarm electrical supply test certificate | PM_70_15_28 : Fire alarm electrical supply test certificate | Project Management | recWAPJoyxSeBXnKr
recXRGEabSFzGAsBC | 2021-06-14T07:47:08.000Z | PM_70_15_29 | Fire safety acceptance certificate | [List] | TRUE | PM_70_15_29 : Fire safety acceptance certificate | PM_70_15_29 : Fire safety acceptance certificate | Project Management | recXRGEabSFzGAsBC
recmx1ei7xMvyKZqp | 2021-06-14T07:47:08.000Z | PM_70_15_30 | Fire-stopping protection certificate | [List] | TRUE | PM_70_15_30 : Fire-stopping protection certificate | PM_70_15_30 : Fire-stopping protection certificate | Project Management | recmx1ei7xMvyKZqp
recmLy16HZmrcKc3x | 2021-06-14T07:47:08.000Z | PM_70_15_31 | Fire-stopping protection register | [List] | TRUE | PM_70_15_31 : Fire-stopping protection register | PM_70_15_31 : Fire-stopping protection register | Project Management | recmLy16HZmrcKc3x
recnGfpK1lG7RvlIH | 2021-06-14T07:47:08.000Z | PM_70_15_32 | Flat roof electronic test results | [List] | TRUE | PM_70_15_32 : Flat roof electronic test results | PM_70_15_32 : Flat roof electronic test results | Project Management | recnGfpK1lG7RvlIH
recf2fE7Uy36Ahvgn | 2021-06-14T07:47:08.000Z | PM_70_15_33 | Gas installation pressure test and purging certificate | [List] | TRUE | PM_70_15_33 : Gas installation pressure test and purging certificate | PM_70_15_33 : Gas installation pressure test and purging certificate | Project Management | recf2fE7Uy36Ahvgn
rec3QYMOvuhrmYcjE | 2021-06-14T07:47:08.000Z | PM_70_15_34 | Gas installation safety certificate | [List] | TRUE | PM_70_15_34 : Gas installation safety certificate | PM_70_15_34 : Gas installation safety certificate | Project Management | rec3QYMOvuhrmYcjE
recLvu6ZGrQoFCRK1 | 2021-06-14T07:47:08.000Z | PM_70_15_40 | Incoming gas supply pressure test report | [List] | TRUE | PM_70_15_40 : Incoming gas supply pressure test report | PM_70_15_40 : Incoming gas supply pressure test report | Project Management | recLvu6ZGrQoFCRK1
recOTsu7ksJ8atbFj | 2021-06-14T07:47:08.000Z | PM_70_15_42 | Insurance certificate | [List] | TRUE | PM_70_15_42 : Insurance certificate | PM_70_15_42 : Insurance certificate | Project Management | recOTsu7ksJ8atbFj
recxzsw0XfY5aLh0j | 2021-06-14T07:47:08.000Z | PM_70_15_50 | Material fire performance test certificate | [List] | TRUE | PM_70_15_50 : Material fire performance test certificate | PM_70_15_50 : Material fire performance test certificate | Project Management | recxzsw0XfY5aLh0j
recWCd6OkHHfKVkbD | 2021-06-14T07:47:08.000Z | PM_70_15_60 | Party wall certificate | [List] | TRUE | PM_70_15_60 : Party wall certificate | PM_70_15_60 : Party wall certificate | Project Management | recWCd6OkHHfKVkbD
recS4K9dHVd4EBF8J | 2021-06-14T07:47:08.000Z | PM_70_15_63 | Power metering commissioning certificate | [List] | TRUE | PM_70_15_63 : Power metering commissioning certificate | PM_70_15_63 : Power metering commissioning certificate | Project Management | recS4K9dHVd4EBF8J
reck3EtQs2waguIN9 | 2021-06-14T07:47:08.000Z | PM_70_15_65 | Primary fresh air supply test certificate | [List] | TRUE | PM_70_15_65 : Primary fresh air supply test certificate | PM_70_15_65 : Primary fresh air supply test certificate | Project Management | reck3EtQs2waguIN9
recQGnz6T7ZDeP5BS | 2021-06-14T07:47:08.000Z | PM_70_15_76 | Secondary and backup electricity supplies test certificate | [List] | TRUE | PM_70_15_76 : Secondary and backup electricity supplies test certificate | PM_70_15_76 : Secondary and backup electricity supplies test certificate | Project Management | recQGnz6T7ZDeP5BS
recB1IDF3F41SBbdl | 2021-06-14T07:47:08.000Z | PM_70_15_80 | Smoke and fire alarm and fire suppression system telephone lines test results | [List] | TRUE | PM_70_15_80 : Smoke and fire alarm and fire suppression system telephone lines test results | PM_70_15_80 : Smoke and fire alarm and fire suppression system telephone lines test results | Project Management | recB1IDF3F41SBbdl
recjLnAhWm2K69hwg | 2021-06-14T07:47:08.000Z | PM_70_15_82 | Soak test results | [List] | TRUE | PM_70_15_82 : Soak test results | PM_70_15_82 : Soak test results | Project Management | recjLnAhWm2K69hwg
recFbvavumZu70MCv | 2021-06-14T07:47:08.000Z | PM_70_15_83 | Sports pitch certificate | [List] | TRUE | PM_70_15_83 : Sports pitch certificate | PM_70_15_83 : Sports pitch certificate | Project Management | recFbvavumZu70MCv
recVfkEsmyGJlaCa0 | 2022-01-28T12:20:29.000Z | PM_70_15_84 | Structured data cabling test certificate | [List] | TRUE | PM_70_15_84 : Structured data cabling test certificate | PM_70_15_84 : Structured data cabling test certificate | Project Management | recVfkEsmyGJlaCa0
reckDoWjYzbP6faIP | 2021-06-14T07:47:08.000Z | PM_70_15_85 | Sustainable timber certificate | [List] | TRUE | PM_70_15_85 : Sustainable timber certificate | PM_70_15_85 : Sustainable timber certificate | Project Management | reckDoWjYzbP6faIP
recNc5MFTtQCQWYRS | 2021-06-14T07:47:08.000Z | PM_70_15_96 | Water quality and flushing test certificate | [List] | TRUE | PM_70_15_96 : Water quality and flushing test certificate | PM_70_15_96 : Water quality and flushing test certificate | Project Management | recNc5MFTtQCQWYRS
recvO3XLUybesUpGl | 2022-01-28T12:20:29.000Z | PM_70_15_98 | White lining sign-off certificate | [List] | TRUE | PM_70_15_98 : White lining sign-off certificate | PM_70_15_98 : White lining sign-off certificate | Project Management | recvO3XLUybesUpGl
recywb4ieBWvry0jf | 2021-06-14T07:47:08.000Z | PM_70_30 | Equipment certification documents | [List] | TRUE | PM_70_30 : Equipment certification documents | PM_70_30 : Equipment certification documents | Project Management | recywb4ieBWvry0jf
recHv8S1gERGkX8HD | 2021-06-14T07:47:08.000Z | PM_70_30_02 | Air handling unit commissioning certificate | [List] | TRUE | PM_70_30_02 : Air handling unit commissioning certificate | PM_70_30_02 : Air handling unit commissioning certificate | Project Management | recHv8S1gERGkX8HD
recCWpzz7xW9ti5ok | 2021-06-14T07:47:08.000Z | PM_70_30_06 | Boiler commissioning certificate | [List] | TRUE | PM_70_30_06 : Boiler commissioning certificate | PM_70_30_06 : Boiler commissioning certificate | Project Management | recCWpzz7xW9ti5ok
reccrcJfSOm2WlpY7 | 2021-06-14T07:47:08.000Z | PM_70_30_10 | Building management systems (BMS) commissioning certificate | [List] | TRUE | PM_70_30_10 : Building management systems (BMS) commissioning certificate | PM_70_30_10 : Building management systems (BMS) commissioning certificate | Project Management | reccrcJfSOm2WlpY7
recowW64V6ne7Io46 | 2021-06-14T07:47:08.000Z | PM_70_30_15 | Closed-circuit television (CCTV) commissioning certificate | [List] | TRUE | PM_70_30_15 : Closed-circuit television (CCTV) commissioning certificate | PM_70_30_15 : Closed-circuit television (CCTV) commissioning certificate | Project Management | recowW64V6ne7Io46
rec9vsHwbfP7SbcO0 | 2021-06-14T07:47:08.000Z | PM_70_30_21 | Data cable test certificate | [List] | TRUE | PM_70_30_21 : Data cable test certificate | PM_70_30_21 : Data cable test certificate | Project Management | rec9vsHwbfP7SbcO0
recv3lHPCaMsPh72I | 2021-06-14T07:47:08.000Z | PM_70_30_22 | Disabled alarms and disabled refuge alarm testing certificate | [List] | TRUE | PM_70_30_22 : Disabled alarms and disabled refuge alarm testing certificate | PM_70_30_22 : Disabled alarms and disabled refuge alarm testing certificate | Project Management | recv3lHPCaMsPh72I
recN8gUMvltyQTPxA | 2021-06-14T07:47:08.000Z | PM_70_30_24 | Ductwork air leakage test certificate | [List] | TRUE | PM_70_30_24 : Ductwork air leakage test certificate | PM_70_30_24 : Ductwork air leakage test certificate | Project Management | recN8gUMvltyQTPxA
reck3krLINUskvqF2 | 2021-06-14T07:47:08.000Z | PM_70_30_26 | Equipment safety certificate | [List] | TRUE | PM_70_30_26 : Equipment safety certificate | PM_70_30_26 : Equipment safety certificate | Project Management | reck3krLINUskvqF2
recArQuVgI3Alz1lY | 2021-06-14T07:47:08.000Z | PM_70_30_27 | Fire hydrant and mains commissioning certificate | [List] | TRUE | PM_70_30_27 : Fire hydrant and mains commissioning certificate | PM_70_30_27 : Fire hydrant and mains commissioning certificate | Project Management | recArQuVgI3Alz1lY
rec3ULI0rUpMyw9rt | 2021-06-14T07:47:08.000Z | PM_70_30_28 | Fire-rated doors test certificate | [List] | TRUE | PM_70_30_28 : Fire-rated doors test certificate | PM_70_30_28 : Fire-rated doors test certificate | Project Management | rec3ULI0rUpMyw9rt
recbZjSiydF88tUar | 2021-06-14T07:47:08.000Z | PM_70_30_32 | Fume cupboard commissioning certificate | [List] | TRUE | PM_70_30_32 : Fume cupboard commissioning certificate | PM_70_30_32 : Fume cupboard commissioning certificate | Project Management | recbZjSiydF88tUar
reck1vN6T5pbh7UpO | 2021-06-14T07:47:08.000Z | PM_70_30_33 | Gas appliance commissioning certificate | [List] | TRUE | PM_70_30_33 : Gas appliance commissioning certificate | PM_70_30_33 : Gas appliance commissioning certificate | Project Management | reck1vN6T5pbh7UpO
recBH8mnsUFdLEjeS | 2021-06-14T07:47:08.000Z | PM_70_30_35 | Generator commissioning certificate | [List] | TRUE | PM_70_30_35 : Generator commissioning certificate | PM_70_30_35 : Generator commissioning certificate | Project Management | recBH8mnsUFdLEjeS
recKjfg71xM0C5ndc | 2022-01-28T12:20:29.000Z | PM_70_30_40 | Information and communications technology (ICT) security certification information | [List] | TRUE | PM_70_30_40 : Information and communications technology (ICT) security certification information | PM_70_30_40 : Information and communications technology (ICT) security certification information | Project Management | recKjfg71xM0C5ndc
recOXDtTdXQj16gZF | 2021-06-14T07:47:08.000Z | PM_70_30_45 | Kitchen equipment certificate | [List] | TRUE | PM_70_30_45 : Kitchen equipment certificate | PM_70_30_45 : Kitchen equipment certificate | Project Management | recOXDtTdXQj16gZF
recsFxmb1qTjFJN2P | 2021-06-14T07:47:08.000Z | PM_70_30_47 | Lightning protection certificate | [List] | TRUE | PM_70_30_47 : Lightning protection certificate | PM_70_30_47 : Lightning protection certificate | Project Management | recsFxmb1qTjFJN2P
recNb9brsgVX8aPRn | 2021-06-14T07:47:08.000Z | PM_70_30_64 | Photovoltaic solar panel test certificate | [List] | TRUE | PM_70_30_64 : Photovoltaic solar panel test certificate | PM_70_30_64 : Photovoltaic solar panel test certificate | Project Management | recNb9brsgVX8aPRn
rec3ut2tNCLgDj2ed | 2021-06-14T07:47:08.000Z | PM_70_30_70 | Retractable seating safety certificate | [List] | TRUE | PM_70_30_70 : Retractable seating safety certificate | PM_70_30_70 : Retractable seating safety certificate | Project Management | rec3ut2tNCLgDj2ed
recolA8x3HJ4rBL1w | 2021-06-14T07:47:08.000Z | PM_70_30_73 | Roller shutter commissioning and conformity certificate | [List] | TRUE | PM_70_30_73 : Roller shutter commissioning and conformity certificate | PM_70_30_73 : Roller shutter commissioning and conformity certificate | Project Management | recolA8x3HJ4rBL1w
rec3mDkEvC23kFUB7 | 2021-06-14T07:47:08.000Z | PM_70_30_78 | Security and intruder alarm commissioning certificate | [List] | TRUE | PM_70_30_78 : Security and intruder alarm commissioning certificate | PM_70_30_78 : Security and intruder alarm commissioning certificate | Project Management | rec3mDkEvC23kFUB7
rece4A3LSW64kR5Ml | 2021-06-14T07:47:08.000Z | PM_70_30_80 | Solar hot water collector commissioning certificate | [List] | TRUE | PM_70_30_80 : Solar hot water collector commissioning certificate | PM_70_30_80 : Solar hot water collector commissioning certificate | Project Management | rece4A3LSW64kR5Ml
rec5Gnp3syErfDlZk | 2021-06-14T07:47:08.000Z | PM_70_30_83 | Sprinkler installation test certificate | [List] | TRUE | PM_70_30_83 : Sprinkler installation test certificate | PM_70_30_83 : Sprinkler installation test certificate | Project Management | rec5Gnp3syErfDlZk
recQgSmO366ZCfdx2 | 2021-06-14T07:47:08.000Z | PM_70_30_88 | Theatre lighting certificate | [List] | TRUE | PM_70_30_88 : Theatre lighting certificate | PM_70_30_88 : Theatre lighting certificate | Project Management | recQgSmO366ZCfdx2
recSjKw4IDSS2emTc | 2021-06-14T07:47:08.000Z | PM_70_30_92 | Uninterruptible power supply (UPS) test certificate | [List] | TRUE | PM_70_30_92 : Uninterruptible power supply (UPS) test certificate | PM_70_30_92 : Uninterruptible power supply (UPS) test certificate | Project Management | recSjKw4IDSS2emTc
recwSDhJmf48dLuv4 | 2022-01-28T12:20:29.000Z | PM_70_30_97 | Window certificates | [List] | TRUE | PM_70_30_97 : Window certificates | PM_70_30_97 : Window certificates | Project Management | recwSDhJmf48dLuv4
recHVxF6KMFk58yu6 | 2021-06-14T07:47:08.000Z | PM_70_30_98 | Workshop equipment commissioning certificate | [List] | TRUE | PM_70_30_98 : Workshop equipment commissioning certificate | PM_70_30_98 : Workshop equipment commissioning certificate | Project Management | recHVxF6KMFk58yu6
recC4NCFRrC2MBO59 | 2021-06-14T07:47:08.000Z | PM_70_75 | Testing information | [List] | TRUE | PM_70_75 : Testing information | PM_70_75 : Testing information | Project Management | recC4NCFRrC2MBO59
recG3LrkQEcziicZR | 2021-06-14T07:47:08.000Z | PM_70_75_01 | Acoustic test report | [List] | TRUE | PM_70_75_01 : Acoustic test report | PM_70_75_01 : Acoustic test report | Project Management | recG3LrkQEcziicZR
recwzNEsy9fIedjsM | 2021-06-14T07:47:08.000Z | PM_70_75_02 | Air distribution test report | [List] | TRUE | PM_70_75_02 : Air distribution test report | PM_70_75_02 : Air distribution test report | Project Management | recwzNEsy9fIedjsM
recAVxmrJIGIwHbMw | 2021-06-14T07:47:08.000Z | PM_70_75_03 | Access equipment test report | [List] | TRUE | PM_70_75_03 : Access equipment test report | PM_70_75_03 : Access equipment test report | Project Management | recAVxmrJIGIwHbMw
recoDB8dlN63ywZey | 2021-06-14T07:47:08.000Z | PM_70_75_04 | Air leakage test certificate | [List] | TRUE | PM_70_75_04 : Air leakage test certificate | PM_70_75_04 : Air leakage test certificate | Project Management | recoDB8dlN63ywZey
recLSY3SqJeYmnq1s | 2021-06-14T07:47:08.000Z | PM_70_75_05 | Air quality test certificate | [List] | TRUE | PM_70_75_05 : Air quality test certificate | PM_70_75_05 : Air quality test certificate | Project Management | recLSY3SqJeYmnq1s
recQ63shqGLnNh2Qw | 2021-06-14T07:47:08.000Z | PM_70_75_07 | Bell system test report | [List] | TRUE | PM_70_75_07 : Bell system test report | PM_70_75_07 : Bell system test report | Project Management | recQ63shqGLnNh2Qw
recd0reKBol9jIf8P | 2022-01-28T12:20:29.000Z | PM_70_75_08 | Boiler test report | [List] | TRUE | PM_70_75_08 : Boiler test report | PM_70_75_08 : Boiler test report | Project Management | recd0reKBol9jIf8P
recmKLUz8x5zwtHDX | 2022-01-28T12:20:29.000Z | PM_70_75_10 | Chlorination test report | [List] | TRUE | PM_70_75_10 : Chlorination test report | PM_70_75_10 : Chlorination test report | Project Management | recmKLUz8x5zwtHDX
recCMlGylC4MjeWYR | 2021-06-14T07:47:08.000Z | PM_70_75_11 | Cable test report | [List] | TRUE | PM_70_75_11 : Cable test report | PM_70_75_11 : Cable test report | Project Management | recCMlGylC4MjeWYR
reczRJfqxXA4aJeL6 | 2021-06-14T07:47:08.000Z | PM_70_75_12 | Cladding and curtain walling water test report | [List] | TRUE | PM_70_75_12 : Cladding and curtain walling water test report | PM_70_75_12 : Cladding and curtain walling water test report | Project Management | reczRJfqxXA4aJeL6
rec1dEFZzglQuWHRr | 2021-06-14T07:47:08.000Z | PM_70_75_13 | Coliform and bacteria count test report | [List] | TRUE | PM_70_75_13 : Coliform and bacteria count test report | PM_70_75_13 : Coliform and bacteria count test report | Project Management | rec1dEFZzglQuWHRr
recQqrZROSTT8UC53 | 2021-06-14T07:47:08.000Z | PM_70_75_14 | Combined heat and power (CHP) system test report | [List] | TRUE | PM_70_75_14 : Combined heat and power (CHP) system test report | PM_70_75_14 : Combined heat and power (CHP) system test report | Project Management | recQqrZROSTT8UC53
recm491rPPkMNl3AG | 2021-06-14T07:47:08.000Z | PM_70_75_15 | Control system test report | [List] | TRUE | PM_70_75_15 : Control system test report | PM_70_75_15 : Control system test report | Project Management | recm491rPPkMNl3AG
recbDr1FYyHj0zLGh | 2021-06-14T07:47:08.000Z | PM_70_75_17 | Co-ordinated shut down interface test report | [List] | TRUE | PM_70_75_17 : Co-ordinated shut down interface test report | PM_70_75_17 : Co-ordinated shut down interface test report | Project Management | recbDr1FYyHj0zLGh
rec00SDcJxvG25d4H | 2022-01-28T12:20:29.000Z | PM_70_75_21 | Disabled alarms and disabled refuge alarm test report | [List] | TRUE | PM_70_75_21 : Disabled alarms and disabled refuge alarm test report | PM_70_75_21 : Disabled alarms and disabled refuge alarm test report | Project Management | rec00SDcJxvG25d4H
reczHMoq3ES6Gjrp4 | 2021-06-14T07:47:08.000Z | PM_70_75_22 | Drainage leakage test results | [List] | TRUE | PM_70_75_22 : Drainage leakage test results | PM_70_75_22 : Drainage leakage test results | Project Management | reczHMoq3ES6Gjrp4
recyYBhChGhSahauk | 2021-06-14T07:47:08.000Z | PM_70_75_23 | Ductwork cleaning test certificate | [List] | TRUE | PM_70_75_23 : Ductwork cleaning test certificate | PM_70_75_23 : Ductwork cleaning test certificate | Project Management | recyYBhChGhSahauk
rec8FG7RzCFjNbl32 | 2021-06-14T07:47:08.000Z | PM_70_75_24 | Ductwork cleaning test report | [List] | TRUE | PM_70_75_24 : Ductwork cleaning test report | PM_70_75_24 : Ductwork cleaning test report | Project Management | rec8FG7RzCFjNbl32
recq9JTfcrwdZXuIy | 2021-06-14T07:47:08.000Z | PM_70_75_25 | Ductwork pressure test certificate | [List] | TRUE | PM_70_75_25 : Ductwork pressure test certificate | PM_70_75_25 : Ductwork pressure test certificate | Project Management | recq9JTfcrwdZXuIy
recJ9AxJ7Losm66uJ | 2021-06-14T07:47:08.000Z | PM_70_75_27 | Electrical installation test report | [List] | TRUE | PM_70_75_27 : Electrical installation test report | PM_70_75_27 : Electrical installation test report | Project Management | recJ9AxJ7Losm66uJ
recdSozIJqXeK9l69 | 2021-06-14T07:47:08.000Z | PM_70_75_28 | Emergency lighting test report | [List] | TRUE | PM_70_75_28 : Emergency lighting test report | PM_70_75_28 : Emergency lighting test report | Project Management | recdSozIJqXeK9l69
rec75dbQrBJARt6MO | 2021-06-14T07:47:08.000Z | PM_70_75_29 | Energy meter calibration test report | [List] | TRUE | PM_70_75_29 : Energy meter calibration test report | PM_70_75_29 : Energy meter calibration test report | Project Management | rec75dbQrBJARt6MO
recOyZIRCbYY9iscA | 2021-06-14T07:47:08.000Z | PM_70_75_30 | Fire protection installation test report | [List] | TRUE | PM_70_75_30 : Fire protection installation test report | PM_70_75_30 : Fire protection installation test report | Project Management | recOyZIRCbYY9iscA
recFbqRjbv0lCppGV | 2021-06-14T07:47:08.000Z | PM_70_75_31 | Fire alarm test certificate | [List] | TRUE | PM_70_75_31 : Fire alarm test certificate | PM_70_75_31 : Fire alarm test certificate | Project Management | recFbqRjbv0lCppGV
recBCA2EwPASX0DVa | 2021-06-14T07:47:08.000Z | PM_70_75_32 | Fire alarm decibel level test report | [List] | TRUE | PM_70_75_32 : Fire alarm decibel level test report | PM_70_75_32 : Fire alarm decibel level test report | Project Management | recBCA2EwPASX0DVa
recS49oymFdN7zbnN | 2021-06-14T07:47:08.000Z | PM_70_75_33 | Fume cupboard test report | [List] | TRUE | PM_70_75_33 : Fume cupboard test report | PM_70_75_33 : Fume cupboard test report | Project Management | recS49oymFdN7zbnN
recqSBpBv6R10Zd6Q | 2021-06-14T07:47:08.000Z | PM_70_75_34 | Gas interlock test report | [List] | TRUE | PM_70_75_34 : Gas interlock test report | PM_70_75_34 : Gas interlock test report | Project Management | recqSBpBv6R10Zd6Q
rec1qszsYEB7yiImP | 2021-06-14T07:47:08.000Z | PM_70_75_35 | Generator test report | [List] | TRUE | PM_70_75_35 : Generator test report | PM_70_75_35 : Generator test report | Project Management | rec1qszsYEB7yiImP
recUcJu6LSVdvLTFN | 2021-06-14T07:47:08.000Z | PM_70_75_36 | Heating installation test report | [List] | TRUE | PM_70_75_36 : Heating installation test report | PM_70_75_36 : Heating installation test report | Project Management | recUcJu6LSVdvLTFN
recjeixjCdZ6qhHcf | 2021-06-14T07:47:08.000Z | PM_70_75_37 | High-voltage electrical installation test report | [List] | TRUE | PM_70_75_37 : High-voltage electrical installation test report | PM_70_75_37 : High-voltage electrical installation test report | Project Management | recjeixjCdZ6qhHcf
rec5SW0wU7bI74PBJ | 2021-06-14T07:47:08.000Z | PM_70_75_40 | Information and communications technology (ICT) infrastructure test report | [List] | TRUE | PM_70_75_40 : Information and communications technology (ICT) infrastructure test report | PM_70_75_40 : Information and communications technology (ICT) infrastructure test report | Project Management | rec5SW0wU7bI74PBJ
rec1A2wqxtwmPZwrb | 2021-06-14T07:47:08.000Z | PM_70_75_45 | Kitchen equipment installation test report | [List] | TRUE | PM_70_75_45 : Kitchen equipment installation test report | PM_70_75_45 : Kitchen equipment installation test report | Project Management | rec1A2wqxtwmPZwrb
recE8Vf9A0UddOL9S | 2021-06-14T07:47:08.000Z | PM_70_75_47 | Lifts test report | [List] | TRUE | PM_70_75_47 : Lifts test report | PM_70_75_47 : Lifts test report | Project Management | recE8Vf9A0UddOL9S
recVoTHnlUi8ZIZ2s | 2021-06-14T07:47:08.000Z | PM_70_75_48 | Lighting lux level test report | [List] | TRUE | PM_70_75_48 : Lighting lux level test report | PM_70_75_48 : Lighting lux level test report | Project Management | recVoTHnlUi8ZIZ2s
recRCYZ3LCY5jDKnj | 2021-06-14T07:47:08.000Z | PM_70_75_49 | Lightning protection installation test report | [List] | TRUE | PM_70_75_49 : Lightning protection installation test report | PM_70_75_49 : Lightning protection installation test report | Project Management | recRCYZ3LCY5jDKnj
recOTY8Xg1gMdJk45 | 2021-06-14T07:47:08.000Z | PM_70_75_52 | Monitoring systems connection test report | [List] | TRUE | PM_70_75_52 : Monitoring systems connection test report | PM_70_75_52 : Monitoring systems connection test report | Project Management | recOTY8Xg1gMdJk45
recevvTuNo74cOzoc | 2021-06-14T07:47:08.000Z | PM_70_75_61 | Perimeter gates test report | [List] | TRUE | PM_70_75_61 : Perimeter gates test report | PM_70_75_61 : Perimeter gates test report | Project Management | recevvTuNo74cOzoc
recHM89TKn2Dn81cz | 2021-06-14T07:47:08.000Z | PM_70_75_63 | Pipeline pressure test certificate | [List] | TRUE | PM_70_75_63 : Pipeline pressure test certificate | PM_70_75_63 : Pipeline pressure test certificate | Project Management | recHM89TKn2Dn81cz
rectSTZMQaTCwRoC4 | 2021-06-14T07:47:08.000Z | PM_70_75_65 | Pressure system installation test report | [List] | TRUE | PM_70_75_65 : Pressure system installation test report | PM_70_75_65 : Pressure system installation test report | Project Management | rectSTZMQaTCwRoC4
recKsjGr1dyL241U6 | 2021-06-14T07:47:08.000Z | PM_70_75_68 | Public health installation test report | [List] | TRUE | PM_70_75_68 : Public health installation test report | PM_70_75_68 : Public health installation test report | Project Management | recKsjGr1dyL241U6
recTVp6xGasKewkYq | 2021-06-14T07:47:08.000Z | PM_70_75_71 | Refrigerant pipeline pressure test certificate | [List] | TRUE | PM_70_75_71 : Refrigerant pipeline pressure test certificate | PM_70_75_71 : Refrigerant pipeline pressure test certificate | Project Management | recTVp6xGasKewkYq
recYv509S25hjLWM5 | 2021-06-14T07:47:08.000Z | PM_70_75_79 | Sliding partitions test report | [List] | TRUE | PM_70_75_79 : Sliding partitions test report | PM_70_75_79 : Sliding partitions test report | Project Management | recYv509S25hjLWM5
recVQ9XKsWsGx7VLR | 2021-06-14T07:47:08.000Z | PM_70_75_81 | Solar panel wind uplift test report | [List] | TRUE | PM_70_75_81 : Solar panel wind uplift test report | PM_70_75_81 : Solar panel wind uplift test report | Project Management | recVQ9XKsWsGx7VLR
reccAtAapJ0neDzVI | 2021-06-14T07:47:08.000Z | PM_70_75_83 | Sound and lighting systems test report | [List] | TRUE | PM_70_75_83 : Sound and lighting systems test report | PM_70_75_83 : Sound and lighting systems test report | Project Management | reccAtAapJ0neDzVI
recxeOQSx1nwbiEBa | 2021-06-14T07:47:08.000Z | PM_70_75_85 | Surveillance equipment installation test report | [List] | TRUE | PM_70_75_85 : Surveillance equipment installation test report | PM_70_75_85 : Surveillance equipment installation test report | Project Management | recxeOQSx1nwbiEBa
recr0DARFWULg0270 | 2022-01-28T12:20:29.000Z | PM_70_75_88 | Telecommunications installation test report | [List] | TRUE | PM_70_75_88 : Telecommunications installation test report | PM_70_75_88 : Telecommunications installation test report | Project Management | recr0DARFWULg0270
recginyyXrMnidCne | 2022-01-28T12:20:29.000Z | PM_70_75_94 | Ventilation test report | [List] | TRUE | PM_70_75_94 : Ventilation test report | PM_70_75_94 : Ventilation test report | Project Management | recginyyXrMnidCne
recsxsMeEXO5eiIpg | 2021-06-14T07:47:08.000Z | PM_70_75_96 | Water distribution pressure test report | [List] | TRUE | PM_70_75_96 : Water distribution pressure test report | PM_70_75_96 : Water distribution pressure test report | Project Management | recsxsMeEXO5eiIpg
recRfxS1sBv96Xxt7 | 2021-06-14T07:47:08.000Z | PM_70_75_97 | Window cleaning equipment test report | [List] | TRUE | PM_70_75_97 : Window cleaning equipment test report | PM_70_75_97 : Window cleaning equipment test report | Project Management | recRfxS1sBv96Xxt7
recdGWjZDymMm2GFv | 2021-06-14T07:47:08.000Z | PM_70_75_98 | Workshop equipment test certificate | [List] | TRUE | PM_70_75_98 : Workshop equipment test certificate | PM_70_75_98 : Workshop equipment test certificate | Project Management | recdGWjZDymMm2GFv
rec6vXKCECgRP4rPe | 2021-06-14T07:47:08.000Z | PM_70_80 | Commissioning information | [List] | TRUE | PM_70_80 : Commissioning information | PM_70_80 : Commissioning information | Project Management | rec6vXKCECgRP4rPe
recxAUky3mMgO7r9K | 2021-06-14T07:47:08.000Z | PM_70_80_01 | Access control commissioning certificate | [List] | TRUE | PM_70_80_01 : Access control commissioning certificate | PM_70_80_01 : Access control commissioning certificate | Project Management | recxAUky3mMgO7r9K
recxcnck8pfDpKlTb | 2021-06-14T07:47:08.000Z | PM_70_80_02 | Air distribution systems commissioning report | [List] | TRUE | PM_70_80_02 : Air distribution systems commissioning report | PM_70_80_02 : Air distribution systems commissioning report | Project Management | recxcnck8pfDpKlTb
recTE47xyV7wTEjDe | 2021-06-14T07:47:08.000Z | PM_70_80_03 | Air conditioning systems commissioninng certificate | [List] | TRUE | PM_70_80_03 : Air conditioning systems commissioninng certificate | PM_70_80_03 : Air conditioning systems commissioninng certificate | Project Management | recTE47xyV7wTEjDe
recvqXoh7xz139wQf | 2021-06-14T07:47:08.000Z | PM_70_80_04 | Air source heat pump commissioning certificate | [List] | TRUE | PM_70_80_04 : Air source heat pump commissioning certificate | PM_70_80_04 : Air source heat pump commissioning certificate | Project Management | recvqXoh7xz139wQf
reciNqkfMCf3CKH9s | 2021-06-14T07:47:08.000Z | PM_70_80_05 | Audiovisual systems commissioning and acceptance certificate | [List] | TRUE | PM_70_80_05 : Audiovisual systems commissioning and acceptance certificate | PM_70_80_05 : Audiovisual systems commissioning and acceptance certificate | Project Management | reciNqkfMCf3CKH9s
recHbwwT1xGRSPMgL | 2021-06-14T07:47:08.000Z | PM_70_80_07 | Bell system commissioning certificate | [List] | TRUE | PM_70_80_07 : Bell system commissioning certificate | PM_70_80_07 : Bell system commissioning certificate | Project Management | recHbwwT1xGRSPMgL
reckWtlKiiLRmLL5t | 2021-06-14T07:47:08.000Z | PM_70_80_13 | Combined heat and power (CHP) system commissioning certificate | [List] | TRUE | PM_70_80_13 : Combined heat and power (CHP) system commissioning certificate | PM_70_80_13 : Combined heat and power (CHP) system commissioning certificate | Project Management | reckWtlKiiLRmLL5t
recTcepCmN99gEXDr | 2022-01-28T12:20:29.000Z | PM_70_80_14 | Communications systems commissioning certificate | [List] | TRUE | PM_70_80_14 : Communications systems commissioning certificate | PM_70_80_14 : Communications systems commissioning certificate | Project Management | recTcepCmN99gEXDr
recHfBYDntgMqhjX0 | 2021-06-14T07:47:08.000Z | PM_70_80_15 | Control system commissioning report | [List] | TRUE | PM_70_80_15 : Control system commissioning report | PM_70_80_15 : Control system commissioning report | Project Management | recHfBYDntgMqhjX0
recyDzr0Fd56xCUwm | 2021-06-14T07:47:08.000Z | PM_70_80_28 | Emergency lighting installation commissioning report | [List] | TRUE | PM_70_80_28 : Emergency lighting installation commissioning report | PM_70_80_28 : Emergency lighting installation commissioning report | Project Management | recyDzr0Fd56xCUwm
recqfKRzsFwd3lM42 | 2021-06-14T07:47:08.000Z | PM_70_80_30 | Fire alarm system commissioning certificate | [List] | TRUE | PM_70_80_30 : Fire alarm system commissioning certificate | PM_70_80_30 : Fire alarm system commissioning certificate | Project Management | recqfKRzsFwd3lM42
reckPSR9LrkNeiITk | 2021-06-14T07:47:08.000Z | PM_70_80_31 | Fire suppression system commissioning certificate | [List] | TRUE | PM_70_80_31 : Fire suppression system commissioning certificate | PM_70_80_31 : Fire suppression system commissioning certificate | Project Management | reckPSR9LrkNeiITk
recQOXwooKnIqxYtU | 2021-06-14T07:47:08.000Z | PM_70_80_32 | Fume cupboard commissioning report | [List] | TRUE | PM_70_80_32 : Fume cupboard commissioning report | PM_70_80_32 : Fume cupboard commissioning report | Project Management | recQOXwooKnIqxYtU
rec2uj3ubdgaUVXqf | 2021-06-14T07:47:08.000Z | PM_70_80_34 | Ground source heat pump commissioning certificate | [List] | TRUE | PM_70_80_34 : Ground source heat pump commissioning certificate | PM_70_80_34 : Ground source heat pump commissioning certificate | Project Management | rec2uj3ubdgaUVXqf
receUUSNQEvUdWjdS | 2021-06-14T07:47:08.000Z | PM_70_80_37 | Heating system water treatment certificate | [List] | TRUE | PM_70_80_37 : Heating system water treatment certificate | PM_70_80_37 : Heating system water treatment certificate | Project Management | receUUSNQEvUdWjdS
reczbd0Z3BpbIcmyg | 2021-06-14T07:47:08.000Z | PM_70_80_42 | Induction loop commissioning certificate | [List] | TRUE | PM_70_80_42 : Induction loop commissioning certificate | PM_70_80_42 : Induction loop commissioning certificate | Project Management | reczbd0Z3BpbIcmyg
recReyOHAywZREm0O | 2021-06-14T07:47:08.000Z | PM_70_80_45 | Kitchen ventilation certificate | [List] | TRUE | PM_70_80_45 : Kitchen ventilation certificate | PM_70_80_45 : Kitchen ventilation certificate | Project Management | recReyOHAywZREm0O
reckgCjzd3Yoa9Jkc | 2021-06-14T07:47:08.000Z | PM_70_80_46 | Lifts commissioning certificate | [List] | TRUE | PM_70_80_46 : Lifts commissioning certificate | PM_70_80_46 : Lifts commissioning certificate | Project Management | reckgCjzd3Yoa9Jkc
reczSolvbDNDP0en5 | 2021-06-14T07:47:08.000Z | PM_70_80_47 | Lifts commissioning report | [List] | TRUE | PM_70_80_47 : Lifts commissioning report | PM_70_80_47 : Lifts commissioning report | Project Management | reczSolvbDNDP0en5
recNO5i9QFOGa4zVn | 2021-06-14T07:47:08.000Z | PM_70_80_48 | Lighting commissioning report | [List] | TRUE | PM_70_80_48 : Lighting commissioning report | PM_70_80_48 : Lighting commissioning report | Project Management | recNO5i9QFOGa4zVn
recg8eDpmervz7cNu | 2021-06-14T07:47:08.000Z | PM_70_80_49 | Lighting control certificate | [List] | TRUE | PM_70_80_49 : Lighting control certificate | PM_70_80_49 : Lighting control certificate | Project Management | recg8eDpmervz7cNu
recHUOLHelE4ZtZsC | 2021-06-14T07:47:08.000Z | PM_70_80_75 | Seasonal commissioning certificate | [List] | TRUE | PM_70_80_75 : Seasonal commissioning certificate | PM_70_80_75 : Seasonal commissioning certificate | Project Management | recHUOLHelE4ZtZsC
recxFaOX0oDhonlLS | 2021-06-14T07:47:08.000Z | PM_70_80_77 | Security system commissioning report | [List] | TRUE | PM_70_80_77 : Security system commissioning report | PM_70_80_77 : Security system commissioning report | Project Management | recxFaOX0oDhonlLS
recYQmlqFPPtcFYlD | 2022-01-28T12:20:29.000Z | PM_70_80_80 | Smoke extract and control system commissioning report | [List] | TRUE | PM_70_80_80 : Smoke extract and control system commissioning report | PM_70_80_80 : Smoke extract and control system commissioning report | Project Management | recYQmlqFPPtcFYlD
recrTMMJuZiAmXtNJ | 2021-06-14T07:47:08.000Z | PM_70_80_85 | Surveillance system installation commissioning report | [List] | TRUE | PM_70_80_85 : Surveillance system installation commissioning report | PM_70_80_85 : Surveillance system installation commissioning report | Project Management | recrTMMJuZiAmXtNJ
recTfwbf3U209SviX | 2022-01-28T12:20:29.000Z | PM_70_80_88 | Telecommunications installation certificate | [List] | TRUE | PM_70_80_88 : Telecommunications installation certificate | PM_70_80_88 : Telecommunications installation certificate | Project Management | recTfwbf3U209SviX
rec7V0Dgja3uJFGod | 2021-06-14T07:47:08.000Z | PM_70_80_89 | Toilet alarm commissioning certificate | [List] | TRUE | PM_70_80_89 : Toilet alarm commissioning certificate | PM_70_80_89 : Toilet alarm commissioning certificate | Project Management | rec7V0Dgja3uJFGod
recTv3eYZlGlnM56s | 2022-01-28T12:20:29.000Z | PM_70_80_94 | Ventilation commissioning certificate | [List] | TRUE | PM_70_80_94 : Ventilation commissioning certificate | PM_70_80_94 : Ventilation commissioning certificate | Project Management | recTv3eYZlGlnM56s
recgUSMQqmC2Frnn8 | 2021-06-14T07:47:08.000Z | PM_70_80_96 | Water distribution commissioning report | [List] | TRUE | PM_70_80_96 : Water distribution commissioning report | PM_70_80_96 : Water distribution commissioning report | Project Management | recgUSMQqmC2Frnn8
recUE01OqYF7Tn3kU | 2021-06-14T07:47:08.000Z | PM_70_85 | Completion information | [List] | TRUE | PM_70_85 : Completion information | PM_70_85 : Completion information | Project Management | recUE01OqYF7Tn3kU
recotlU3t7Gchb87u | 2021-06-14T07:47:08.000Z | PM_70_85_08 | Building logbook | [List] | TRUE | PM_70_85_08 : Building logbook | PM_70_85_08 : Building logbook | Project Management | recotlU3t7Gchb87u
rec10FeQbp0XjMAvK | 2021-06-14T07:47:08.000Z | PM_70_85_10 | Building manual | [List] | TRUE | PM_70_85_10 : Building manual | PM_70_85_10 : Building manual | Project Management | rec10FeQbp0XjMAvK
reczvjYXTdxlyVEeE | 2021-06-14T07:47:08.000Z | PM_70_85_11 | Clarifications information | [List] | TRUE | PM_70_85_11 : Clarifications information | PM_70_85_11 : Clarifications information | Project Management | reczvjYXTdxlyVEeE
rectCunLvKxVrylrk | 2021-06-14T07:47:08.000Z | PM_70_85_14 | Contractor sign-off report | [List] | TRUE | PM_70_85_14 : Contractor sign-off report | PM_70_85_14 : Contractor sign-off report | Project Management | rectCunLvKxVrylrk
recXZahXZnE4kI4hA | 2021-06-14T07:47:08.000Z | PM_70_85_15 | Construction to occupation transition strategy | [List] | TRUE | PM_70_85_15 : Construction to occupation transition strategy | PM_70_85_15 : Construction to occupation transition strategy | Project Management | recXZahXZnE4kI4hA
recTbPr3dzbpGjmrG | 2021-06-14T07:47:08.000Z | PM_70_85_18 | Defects notification information | [List] | TRUE | PM_70_85_18 : Defects notification information | PM_70_85_18 : Defects notification information | Project Management | recTbPr3dzbpGjmrG
recOBIv6bZSUmE19D | 2021-06-14T07:47:08.000Z | PM_70_85_20 | Defects rectification report | [List] | TRUE | PM_70_85_20 : Defects rectification report | PM_70_85_20 : Defects rectification report | Project Management | recOBIv6bZSUmE19D
recXUcjX70W5Kj4To | 2021-06-14T07:47:08.000Z | PM_70_85_22 | Defects register | [List] | TRUE | PM_70_85_22 : Defects register | PM_70_85_22 : Defects register | Project Management | recXUcjX70W5Kj4To
receLCrj9G8u1G6wP | 2021-06-14T07:47:08.000Z | PM_70_85_25 | End user operating information | [List] | TRUE | PM_70_85_25 : End user operating information | PM_70_85_25 : End user operating information | Project Management | receLCrj9G8u1G6wP
recfPgvuEcuAb66hD | 2021-06-14T07:47:08.000Z | PM_70_85_30 | Final inspection report | [List] | TRUE | PM_70_85_30 : Final inspection report | PM_70_85_30 : Final inspection report | Project Management | recfPgvuEcuAb66hD
recAi0eCJSqmAEEcp | 2021-06-14T07:47:08.000Z | PM_70_85_31 | Fire safety management plan information | [List] | TRUE | PM_70_85_31 : Fire safety management plan information | PM_70_85_31 : Fire safety management plan information | Project Management | recAi0eCJSqmAEEcp
recRdXxLkp9heF7Yc | 2021-06-14T07:47:08.000Z | PM_70_85_33 | Handover board record of acceptance for occupation | [List] | TRUE | PM_70_85_33 : Handover board record of acceptance for occupation | PM_70_85_33 : Handover board record of acceptance for occupation | Project Management | recRdXxLkp9heF7Yc
recM8jNFx3avGvYU5 | 2021-06-14T07:47:08.000Z | PM_70_85_34 | Handover communications information | [List] | TRUE | PM_70_85_34 : Handover communications information | PM_70_85_34 : Handover communications information | Project Management | recM8jNFx3avGvYU5
receICtpjc8y0S7zw | 2021-06-14T07:47:08.000Z | PM_70_85_35 | Handover strategy | [List] | TRUE | PM_70_85_35 : Handover strategy | PM_70_85_35 : Handover strategy | Project Management | receICtpjc8y0S7zw
rec2b1CLWTu4YqCiI | 2021-06-14T07:47:08.000Z | PM_70_85_40 | Health and safety file | [List] | TRUE | PM_70_85_40 : Health and safety file | PM_70_85_40 : Health and safety file | Project Management | rec2b1CLWTu4YqCiI
recE3QzZqmq77DSm2 | 2021-06-14T07:47:08.000Z | PM_70_85_44 | Life expectancy information | [List] | TRUE | PM_70_85_44 : Life expectancy information | PM_70_85_44 : Life expectancy information | Project Management | recE3QzZqmq77DSm2
recY6dsKzoq0PT05S | 2021-06-14T07:47:08.000Z | PM_70_85_45 | List of spares and consumables | [List] | TRUE | PM_70_85_45 : List of spares and consumables | PM_70_85_45 : List of spares and consumables | Project Management | recY6dsKzoq0PT05S
rec7BevvTn2TnXb7D | 2021-06-14T07:47:08.000Z | PM_70_85_50 | Maintenance schedules | [List] | TRUE | PM_70_85_50 : Maintenance schedules | PM_70_85_50 : Maintenance schedules | Project Management | rec7BevvTn2TnXb7D
recf3Sv5cTOAZuT6j | 2021-06-14T07:47:08.000Z | PM_70_85_52 | Manufacturer information | [List] | TRUE | PM_70_85_52 : Manufacturer information | PM_70_85_52 : Manufacturer information | Project Management | recf3Sv5cTOAZuT6j
rec0g8jv32TYllfUx | 2021-06-14T07:47:08.000Z | PM_70_85_55 | Operating instruction | [List] | TRUE | PM_70_85_55 : Operating instruction | PM_70_85_55 : Operating instruction | Project Management | rec0g8jv32TYllfUx
rec8JHW0HZdHxDEKH | 2021-06-14T07:47:08.000Z | PM_70_85_56 | Operation and maintenance manual | [List] | TRUE | PM_70_85_56 : Operation and maintenance manual | PM_70_85_56 : Operation and maintenance manual | Project Management | rec8JHW0HZdHxDEKH
recZUISUauFeE6GTT | 2021-06-14T07:47:08.000Z | PM_70_85_60 | Plant logbook | [List] | TRUE | PM_70_85_60 : Plant logbook | PM_70_85_60 : Plant logbook | Project Management | recZUISUauFeE6GTT
recV6IPSdizBtRrnr | 2021-06-14T07:47:08.000Z | PM_70_85_62 | Pre-handover plan | [List] | TRUE | PM_70_85_62 : Pre-handover plan | PM_70_85_62 : Pre-handover plan | Project Management | recV6IPSdizBtRrnr
reccIEPyvx3q3eKk6 | 2021-06-14T07:47:08.000Z | PM_70_85_64 | Project completion report | [List] | TRUE | PM_70_85_64 : Project completion report | PM_70_85_64 : Project completion report | Project Management | reccIEPyvx3q3eKk6
recpVWbLHuF7L6UrE | 2021-06-14T07:47:08.000Z | PM_70_85_70 | Remedial work completion report | [List] | TRUE | PM_70_85_70 : Remedial work completion report | PM_70_85_70 : Remedial work completion report | Project Management | recpVWbLHuF7L6UrE
recVNdHJ0x2PbLQqb | 2021-06-14T07:47:08.000Z | PM_70_85_79 | Soft landings process information | [List] | TRUE | PM_70_85_79 : Soft landings process information | PM_70_85_79 : Soft landings process information | Project Management | recVNdHJ0x2PbLQqb
recMLBymqrSpaD78x | 2021-06-14T07:47:08.000Z | PM_70_85_83 | Supplier directory | [List] | TRUE | PM_70_85_83 : Supplier directory | PM_70_85_83 : Supplier directory | Project Management | recMLBymqrSpaD78x
recI39BBTQRp8Rxt8 | 2021-06-14T07:47:08.000Z | PM_70_85_90 | Training documentation | [List] | TRUE | PM_70_85_90 : Training documentation | PM_70_85_90 : Training documentation | Project Management | recI39BBTQRp8Rxt8
recWXQVNybPWZfoWe | 2021-06-14T07:47:08.000Z | PM_70_85_92 | User acceptance information | [List] | TRUE | PM_70_85_92 : User acceptance information | PM_70_85_92 : User acceptance information | Project Management | recWXQVNybPWZfoWe
recxEjOsS4nOinAQi | 2022-01-28T12:20:29.000Z | PM_70_85_93 | Utilities readings | [List] | TRUE | PM_70_85_93 : Utilities readings | PM_70_85_93 : Utilities readings | Project Management | recxEjOsS4nOinAQi
rectIPMhuQhBS8NeW | 2021-06-14T07:47:08.000Z | PM_70_85_96 | Works completion certificate | [List] | TRUE | PM_70_85_96 : Works completion certificate | PM_70_85_96 : Works completion certificate | Project Management | rectIPMhuQhBS8NeW
recB4mcOSXecI3klf | 2021-06-14T07:47:08.000Z | PM_70_90 | Record information | [List] | TRUE | PM_70_90 : Record information | PM_70_90 : Record information | Project Management | recB4mcOSXecI3klf
recGWTFlFhrUKR91u | 2021-06-14T07:47:08.000Z | PM_70_90_04 | Architectural record drawings | [List] | TRUE | PM_70_90_04 : Architectural record drawings | PM_70_90_04 : Architectural record drawings | Project Management | recGWTFlFhrUKR91u
recoxppyBpMLONISz | 2021-06-14T07:47:08.000Z | PM_70_90_15 | Control system record drawings | [List] | TRUE | PM_70_90_15 : Control system record drawings | PM_70_90_15 : Control system record drawings | Project Management | recoxppyBpMLONISz
recUgKNcC6jwBlZBL | 2021-06-14T07:47:08.000Z | PM_70_90_27 | Electrical systems record drawings | [List] | TRUE | PM_70_90_27 : Electrical systems record drawings | PM_70_90_27 : Electrical systems record drawings | Project Management | recUgKNcC6jwBlZBL
recG5qxELr8liyToM | 2021-06-14T07:47:08.000Z | PM_70_90_30 | Fire system record drawings | [List] | TRUE | PM_70_90_30 : Fire system record drawings | PM_70_90_30 : Fire system record drawings | Project Management | recG5qxELr8liyToM
rec3ED6pMpgfQzz1N | 2021-06-14T07:47:08.000Z | PM_70_90_46 | Landscape record drawings | [List] | TRUE | PM_70_90_46 : Landscape record drawings | PM_70_90_46 : Landscape record drawings | Project Management | rec3ED6pMpgfQzz1N
rec84jJA8FyEXtYAL | 2021-06-14T07:47:08.000Z | PM_70_90_52 | Mechanical systems record drawings | [List] | TRUE | PM_70_90_52 : Mechanical systems record drawings | PM_70_90_52 : Mechanical systems record drawings | Project Management | rec84jJA8FyEXtYAL
recb7zX5ybT7YNLoz | 2021-06-14T07:47:08.000Z | PM_70_90_68 | Public health system record drawings | [List] | TRUE | PM_70_90_68 : Public health system record drawings | PM_70_90_68 : Public health system record drawings | Project Management | recb7zX5ybT7YNLoz
rec754JgYZiHsYjOL | 2021-06-14T07:47:08.000Z | PM_70_90_77 | Security system record drawings | [List] | TRUE | PM_70_90_77 : Security system record drawings | PM_70_90_77 : Security system record drawings | Project Management | rec754JgYZiHsYjOL
reckdtWcOVm8M14R0 | 2021-06-14T07:47:08.000Z | PM_70_90_79 | Setting out records | [List] | TRUE | PM_70_90_79 : Setting out records | PM_70_90_79 : Setting out records | Project Management | reckdtWcOVm8M14R0
recdzXnMWovM9RpEN | 2021-06-14T07:47:08.000Z | PM_70_90_83 | Structural record drawings | [List] | TRUE | PM_70_90_83 : Structural record drawings | PM_70_90_83 : Structural record drawings | Project Management | recdzXnMWovM9RpEN
recBsmPg0KtsQcAXb | 2021-06-14T07:47:08.000Z | PM_70_95 | Project assurance information | [List] | TRUE | PM_70_95 : Project assurance information | PM_70_95 : Project assurance information | Project Management | recBsmPg0KtsQcAXb
rec4bpBhgYpyKii2U | 2021-06-14T07:47:08.000Z | PM_70_95_20 | Design compliance review report | [List] | TRUE | PM_70_95_20 : Design compliance review report | PM_70_95_20 : Design compliance review report | Project Management | rec4bpBhgYpyKii2U
recv7tIQRpQijK0XY | 2022-01-28T12:20:29.000Z | PM_70_95_21 | Design compliance certificate | [List] | TRUE | PM_70_95_21 : Design compliance certificate | PM_70_95_21 : Design compliance certificate | Project Management | recv7tIQRpQijK0XY
recQO03PRwCmkqCk8 | 2021-06-14T07:47:08.000Z | PM_70_95_33 | Gateway review information | [List] | TRUE | PM_70_95_33 : Gateway review information | PM_70_95_33 : Gateway review information | Project Management | recQO03PRwCmkqCk8
reck8969BW9l2esh7 | 2021-06-14T07:47:08.000Z | PM_70_95_34 | Governance strategy information | [List] | TRUE | PM_70_95_34 : Governance strategy information | PM_70_95_34 : Governance strategy information | Project Management | reck8969BW9l2esh7
recZXEvWfoaqCcaDL | 2021-06-14T07:47:08.000Z | PM_70_95_58 | Option analysis support paper | [List] | TRUE | PM_70_95_58 : Option analysis support paper | PM_70_95_58 : Option analysis support paper | Project Management | recZXEvWfoaqCcaDL
recqVgTgai2mvv7l2 | 2021-06-14T07:47:08.000Z | PM_70_95_64 | Post-project evaluation information | [List] | TRUE | PM_70_95_64 : Post-project evaluation information | PM_70_95_64 : Post-project evaluation information | Project Management | recqVgTgai2mvv7l2
recGzlXkNcrt0Ffz8 | 2021-06-14T07:47:08.000Z | PM_70_95_66 | Project Assurance Group (PAG) sign-off | [List] | TRUE | PM_70_95_66 : Project Assurance Group (PAG) sign-off | PM_70_95_66 : Project Assurance Group (PAG) sign-off | Project Management | recGzlXkNcrt0Ffz8
recC9D5yrzIJCVjNB | 2021-06-14T07:47:08.000Z | PM_70_95_70 | Risk potential assessment | [List] | TRUE | PM_70_95_70 : Risk potential assessment | PM_70_95_70 : Risk potential assessment | Project Management | recC9D5yrzIJCVjNB
receGCQ8FRt4QS1N9 | 2021-06-14T07:47:08.000Z | PM_80 | Asset management information | [List] | TRUE | PM_80 : Asset management information | PM_80 : Asset management information | Project Management | receGCQ8FRt4QS1N9
recSdMsUfvTxZaNSF | 2021-06-14T07:47:08.000Z | PM_80_10 | Asset strategy, planning and management information | [List] | TRUE | PM_80_10 : Asset strategy, planning and management information | PM_80_10 : Asset strategy, planning and management information | Project Management | recSdMsUfvTxZaNSF
rec5vx8gGmZSTg2aW | 2021-11-11T11:10:56.000Z | PM_80_10_01 | Asbestos management plan | [List] | TRUE | PM_80_10_01 : Asbestos management plan | PM_80_10_01 : Asbestos management plan | Project Management | rec5vx8gGmZSTg2aW
rec7AQepKuhU3V2fd | 2021-06-14T07:47:08.000Z | PM_80_10_03 | Asset information protocol | [List] | TRUE | PM_80_10_03 : Asset information protocol | PM_80_10_03 : Asset information protocol | Project Management | rec7AQepKuhU3V2fd
recGUudRCrM3XJ9mk | 2021-06-14T07:47:08.000Z | PM_80_10_05 | Asset guarantee and warranty information | [List] | TRUE | PM_80_10_05 : Asset guarantee and warranty information | PM_80_10_05 : Asset guarantee and warranty information | Project Management | recGUudRCrM3XJ9mk
rec4RNSt7SC7PkCCJ | 2021-11-11T11:10:56.000Z | PM_80_10_07 | Asset management responsibility information | [List] | TRUE | PM_80_10_07 : Asset management responsibility information | PM_80_10_07 : Asset management responsibility information | Project Management | rec4RNSt7SC7PkCCJ
recaQbzYC3f4CBQ4f | 2022-01-28T12:20:29.000Z | PM_80_10_08 | Asset management policy information | [List] | TRUE | PM_80_10_08 : Asset management policy information | PM_80_10_08 : Asset management policy information | Project Management | recaQbzYC3f4CBQ4f
rec2nwpc5LFvvyqfj | 2022-01-28T12:20:29.000Z | PM_80_10_09 | Asset management strategy information | [List] | TRUE | PM_80_10_09 : Asset management strategy information | PM_80_10_09 : Asset management strategy information | Project Management | rec2nwpc5LFvvyqfj
recz85JrU2ugbjiuY | 2021-06-14T07:47:08.000Z | PM_80_10_10 | Asset register | [List] | TRUE | PM_80_10_10 : Asset register | PM_80_10_10 : Asset register | Project Management | recz85JrU2ugbjiuY
recGxDuw8VBRzjhcG | 2021-06-14T07:47:08.000Z | PM_80_10_12 | Building performance evaluation plan | [List] | TRUE | PM_80_10_12 : Building performance evaluation plan | PM_80_10_12 : Building performance evaluation plan | Project Management | recGxDuw8VBRzjhcG
rec8sUv6sv5W2Ehwv | 2022-01-28T12:20:29.000Z | PM_80_10_14 | Closed-circuit television (CCTV) strategy | [List] | TRUE | PM_80_10_14 : Closed-circuit television (CCTV) strategy | PM_80_10_14 : Closed-circuit television (CCTV) strategy | Project Management | rec8sUv6sv5W2Ehwv
rec4naUvTIj22je81 | 2021-11-11T11:10:56.000Z | PM_80_10_15 | Configuration management strategy | [List] | TRUE | PM_80_10_15 : Configuration management strategy | PM_80_10_15 : Configuration management strategy | Project Management | rec4naUvTIj22je81
reciG2bTY3DKSPSA7 | 2021-11-11T11:10:56.000Z | PM_80_10_16 | Configuration record | [List] | TRUE | PM_80_10_16 : Configuration record | PM_80_10_16 : Configuration record | Project Management | reciG2bTY3DKSPSA7
recIBdAVdrrqBZMf2 | 2022-01-28T12:20:29.000Z | PM_80_10_18 | Crime prevention strategy | [List] | TRUE | PM_80_10_18 : Crime prevention strategy | PM_80_10_18 : Crime prevention strategy | Project Management | recIBdAVdrrqBZMf2
recrXPddrQKZ0d0Iq | 2022-01-28T12:20:29.000Z | PM_80_10_19 | Critical assets list | [List] | TRUE | PM_80_10_19 : Critical assets list | PM_80_10_19 : Critical assets list | Project Management | recrXPddrQKZ0d0Iq
recgg08acAUlAMb8t | 2021-11-11T11:10:56.000Z | PM_80_10_20 | Deterioration modelling | [List] | TRUE | PM_80_10_20 : Deterioration modelling | PM_80_10_20 : Deterioration modelling | Project Management | recgg08acAUlAMb8t
recS0wXKxsatrkm9a | 2021-06-14T07:47:08.000Z | PM_80_10_22 | Display energy certificate | [List] | TRUE | PM_80_10_22 : Display energy certificate | PM_80_10_22 : Display energy certificate | Project Management | recS0wXKxsatrkm9a
recBLAJoSSouIJwIg | 2021-06-14T07:47:08.000Z | PM_80_10_24 | Energy consumption information | [List] | TRUE | PM_80_10_24 : Energy consumption information | PM_80_10_24 : Energy consumption information | Project Management | recBLAJoSSouIJwIg
rec75PBdFTz5V6O4J | 2021-06-14T07:47:08.000Z | PM_80_10_25 | Energy performance certificate | [List] | TRUE | PM_80_10_25 : Energy performance certificate | PM_80_10_25 : Energy performance certificate | Project Management | rec75PBdFTz5V6O4J
recri0Dvz3zS3k104 | 2021-06-14T07:47:08.000Z | PM_80_10_27 | Equipment schedule | [List] | TRUE | PM_80_10_27 : Equipment schedule | PM_80_10_27 : Equipment schedule | Project Management | recri0Dvz3zS3k104
recALjmIXvtl1fQTE | 2021-06-14T07:47:08.000Z | PM_80_10_30 | Finishes information | [List] | TRUE | PM_80_10_30 : Finishes information | PM_80_10_30 : Finishes information | Project Management | recALjmIXvtl1fQTE
recpXGvpGD28hg05c | 2021-11-11T11:10:56.000Z | PM_80_10_32 | Furniture audit | [List] | TRUE | PM_80_10_32 : Furniture audit | PM_80_10_32 : Furniture audit | Project Management | recpXGvpGD28hg05c
recNTnKiTjDyDqWLc | 2021-06-14T07:47:08.000Z | PM_80_10_40 | Information and communications technology (ICT) protocol | [List] | TRUE | PM_80_10_40 : Information and communications technology (ICT) protocol | PM_80_10_40 : Information and communications technology (ICT) protocol | Project Management | recNTnKiTjDyDqWLc
rechPUs7UgoiucuTS | 2021-06-14T07:47:08.000Z | PM_80_10_42 | Insurer's requirements | [List] | TRUE | PM_80_10_42 : Insurer's requirements | PM_80_10_42 : Insurer's requirements | Project Management | rechPUs7UgoiucuTS
recdtiLkrjVkbDsco | 2021-11-11T11:10:56.000Z | PM_80_10_45 | Lessons learned notice | [List] | TRUE | PM_80_10_45 : Lessons learned notice | PM_80_10_45 : Lessons learned notice | Project Management | recdtiLkrjVkbDsco
recgg3BB6RxpFdKyt | 2021-06-14T07:47:08.000Z | PM_80_10_47 | Loose equipment protocol | [List] | TRUE | PM_80_10_47 : Loose equipment protocol | PM_80_10_47 : Loose equipment protocol | Project Management | recgg3BB6RxpFdKyt
recNh4RjwVHQp4lrT | 2021-06-14T07:47:08.000Z | PM_80_10_50 | Maintenance requirements | [List] | TRUE | PM_80_10_50 : Maintenance requirements | PM_80_10_50 : Maintenance requirements | Project Management | recNh4RjwVHQp4lrT
rechnlwEJCRavBnJC | 2021-06-14T07:47:08.000Z | PM_80_10_52 | Maintenance plan information | [List] | TRUE | PM_80_10_52 : Maintenance plan information | PM_80_10_52 : Maintenance plan information | Project Management | rechnlwEJCRavBnJC
recZ6caphRS4J9l5F | 2021-06-14T07:47:08.000Z | PM_80_10_53 | Maintenance programme information | [List] | TRUE | PM_80_10_53 : Maintenance programme information | PM_80_10_53 : Maintenance programme information | Project Management | recZ6caphRS4J9l5F
recNIrbxLZ16Fbtns | 2021-06-14T07:47:08.000Z | PM_80_10_54 | Maintenance records | [List] | TRUE | PM_80_10_54 : Maintenance records | PM_80_10_54 : Maintenance records | Project Management | recNIrbxLZ16Fbtns
recjvOfxUApPtsGty | 2022-01-28T12:20:29.000Z | PM_80_10_55 | Metering strategy | [List] | TRUE | PM_80_10_55 : Metering strategy | PM_80_10_55 : Metering strategy | Project Management | recjvOfxUApPtsGty
rec3T65wCKX8RGVVV | 2021-06-14T07:47:08.000Z | PM_80_10_56 | Non-conformance notification | [List] | TRUE | PM_80_10_56 : Non-conformance notification | PM_80_10_56 : Non-conformance notification | Project Management | rec3T65wCKX8RGVVV
recbGA5L6Nc2dtR2d | 2021-06-14T07:47:08.000Z | PM_80_10_57 | Non-conformance protocol | [List] | TRUE | PM_80_10_57 : Non-conformance protocol | PM_80_10_57 : Non-conformance protocol | Project Management | recbGA5L6Nc2dtR2d
recNhjnUIhA6bjenR | 2021-06-14T07:47:08.000Z | PM_80_10_58 | Organization chart | [List] | TRUE | PM_80_10_58 : Organization chart | PM_80_10_58 : Organization chart | Project Management | recNhjnUIhA6bjenR
recEqkvF7cyl7rqpx | 2021-11-11T11:10:56.000Z | PM_80_10_59 | Organization operational instructions | [List] | TRUE | PM_80_10_59 : Organization operational instructions | PM_80_10_59 : Organization operational instructions | Project Management | recEqkvF7cyl7rqpx
recvx1z0HoHntHVsh | 2021-06-14T07:47:08.000Z | PM_80_10_60 | Performance analysis | [List] | TRUE | PM_80_10_60 : Performance analysis | PM_80_10_60 : Performance analysis | Project Management | recvx1z0HoHntHVsh
recXIdoYY5p6b5ilt | 2021-06-14T07:47:08.000Z | PM_80_10_63 | Plant and equipment service life report | [List] | TRUE | PM_80_10_63 : Plant and equipment service life report | PM_80_10_63 : Plant and equipment service life report | Project Management | recXIdoYY5p6b5ilt
recm8Sd3YDF0Ye2AJ | 2021-06-14T07:47:08.000Z | PM_80_10_65 | Post-operational evaluation | [List] | TRUE | PM_80_10_65 : Post-operational evaluation | PM_80_10_65 : Post-operational evaluation | Project Management | recm8Sd3YDF0Ye2AJ
reck3L8uvFnhiMtfN | 2021-06-14T07:47:08.000Z | PM_80_10_72 | Road sewer adoption licence | [List] | TRUE | PM_80_10_72 : Road sewer adoption licence | PM_80_10_72 : Road sewer adoption licence | Project Management | reck3L8uvFnhiMtfN
recqvuZN2lgQUaxHp | 2021-11-11T11:10:56.000Z | PM_80_10_78 | Scenario modelling | [List] | TRUE | PM_80_10_78 : Scenario modelling | PM_80_10_78 : Scenario modelling | Project Management | recqvuZN2lgQUaxHp
recb6xpTGrhJZqExL | 2022-01-28T12:20:29.000Z | PM_80_10_79 | Security management plan | [List] | TRUE | PM_80_10_79 : Security management plan | PM_80_10_79 : Security management plan | Project Management | recb6xpTGrhJZqExL
rectFcV0lsukbQ2Q9 | 2021-11-11T11:10:56.000Z | PM_80_10_80 | Shoreline management plans | [List] | TRUE | PM_80_10_80 : Shoreline management plans | PM_80_10_80 : Shoreline management plans | Project Management | rectFcV0lsukbQ2Q9
recxL8TExlhUEMojM | 2022-01-28T12:20:29.000Z | PM_80_10_84 | Survey management plan | [List] | TRUE | PM_80_10_84 : Survey management plan | PM_80_10_84 : Survey management plan | Project Management | recxL8TExlhUEMojM
reccIyNxuFKQB4jHu | 2021-06-14T07:47:08.000Z | PM_80_10_88 | Telephone system information | [List] | TRUE | PM_80_10_88 : Telephone system information | PM_80_10_88 : Telephone system information | Project Management | reccIyNxuFKQB4jHu
recWnAdFvC92KllAN | 2021-06-14T07:47:08.000Z | PM_80_10_90 | Travel plan information | [List] | TRUE | PM_80_10_90 : Travel plan information | PM_80_10_90 : Travel plan information | Project Management | recWnAdFvC92KllAN
recHJmMgpbtQBsuPH | 2021-06-14T07:47:08.000Z | PM_80_10_94 | Visit questionnaire information | [List] | TRUE | PM_80_10_94 : Visit questionnaire information | PM_80_10_94 : Visit questionnaire information | Project Management | recHJmMgpbtQBsuPH
recyRaIeh4ZDM2Mg5 | 2022-01-28T12:20:29.000Z | PM_80_15 | Asset maintenance information | [List] | TRUE | PM_80_15 : Asset maintenance information | PM_80_15 : Asset maintenance information | Project Management | recyRaIeh4ZDM2Mg5
rec8ppebZ8zMto6az | 2022-01-28T12:20:29.000Z | PM_80_15_31 | Fire safety log book | [List] | TRUE | PM_80_15_31 : Fire safety log book | PM_80_15_31 : Fire safety log book | Project Management | rec8ppebZ8zMto6az
recQ80SpipA1XZGeV | 2021-11-11T11:10:56.000Z | PM_80_20 | Communications and engagement | [List] | TRUE | PM_80_20 : Communications and engagement | PM_80_20 : Communications and engagement | Project Management | recQ80SpipA1XZGeV
recIjiGpaz3gszslm | 2021-11-11T11:10:56.000Z | PM_80_20_15 | Communications log | [List] | TRUE | PM_80_20_15 : Communications log | PM_80_20_15 : Communications log | Project Management | recIjiGpaz3gszslm
recMkry1Y8Jh6I6l4 | 2021-11-11T11:10:56.000Z | PM_80_20_17 | Consultation strategy | [List] | TRUE | PM_80_20_17 : Consultation strategy | PM_80_20_17 : Consultation strategy | Project Management | recMkry1Y8Jh6I6l4
recMwnxTNmGmdJqmX | 2021-11-11T11:10:56.000Z | PM_80_20_19 | Contacts list | [List] | TRUE | PM_80_20_19 : Contacts list | PM_80_20_19 : Contacts list | Project Management | recMwnxTNmGmdJqmX
recPf5legL4mPXZkg | 2021-11-11T11:10:56.000Z | PM_80_20_42 | Issued communications | [List] | TRUE | PM_80_20_42 : Issued communications | PM_80_20_42 : Issued communications | Project Management | recPf5legL4mPXZkg
recKPucHxDfSATEw1 | 2021-11-11T11:10:56.000Z | PM_80_20_50 | Media communications | [List] | TRUE | PM_80_20_50 : Media communications | PM_80_20_50 : Media communications | Project Management | recKPucHxDfSATEw1
recPni0d9g86jwGJz | 2021-11-11T11:10:56.000Z | PM_80_20_72 | Received communications | [List] | TRUE | PM_80_20_72 : Received communications | PM_80_20_72 : Received communications | Project Management | recPni0d9g86jwGJz
recOAgeh9qKSsb2Tn | 2021-06-14T07:47:08.000Z | PM_80_30 | Asset life cycle cost information | [List] | TRUE | PM_80_30 : Asset life cycle cost information | PM_80_30 : Asset life cycle cost information | Project Management | recOAgeh9qKSsb2Tn
recgvV2hc5pjT42j4 | 2021-06-14T07:47:08.000Z | PM_80_30_05 | Acquisition costs | [List] | TRUE | PM_80_30_05 : Acquisition costs | PM_80_30_05 : Acquisition costs | Project Management | recgvV2hc5pjT42j4
recb4vDFq9SCeJFis | 2022-01-28T12:20:29.000Z | PM_80_30_12 | Capital investment cost information | [List] | TRUE | PM_80_30_12 : Capital investment cost information | PM_80_30_12 : Capital investment cost information | Project Management | recb4vDFq9SCeJFis
recS0vkRguXSfoNOF | 2021-06-14T07:47:08.000Z | PM_80_30_30 | Finance charges information | [List] | TRUE | PM_80_30_30 : Finance charges information | PM_80_30_30 : Finance charges information | Project Management | recS0vkRguXSfoNOF
recHuHdFTChfkj8bs | 2021-06-14T07:47:08.000Z | PM_80_30_50 | Maintenance and repair cost information | [List] | TRUE | PM_80_30_50 : Maintenance and repair cost information | PM_80_30_50 : Maintenance and repair cost information | Project Management | recHuHdFTChfkj8bs
recMdwXlmtdWrELLC | 2021-06-14T07:47:08.000Z | PM_80_30_51 | Maintenance and lease agreement information | [List] | TRUE | PM_80_30_51 : Maintenance and lease agreement information | PM_80_30_51 : Maintenance and lease agreement information | Project Management | recMdwXlmtdWrELLC
recahjt64wErz7a7s | 2021-06-14T07:47:08.000Z | PM_80_30_60 | Office services cost information | [List] | TRUE | PM_80_30_60 : Office services cost information | PM_80_30_60 : Office services cost information | Project Management | recahjt64wErz7a7s
reccmhKq2uTxz5Fk4 | 2021-06-14T07:47:08.000Z | PM_80_30_63 | Operational cost information | [List] | TRUE | PM_80_30_63 : Operational cost information | PM_80_30_63 : Operational cost information | Project Management | reccmhKq2uTxz5Fk4
recEyZg33HCQU7NGK | 2021-06-14T07:47:08.000Z | PM_80_30_70 | Replacement cost information | [List] | TRUE | PM_80_30_70 : Replacement cost information | PM_80_30_70 : Replacement cost information | Project Management | recEyZg33HCQU7NGK
recmIfsPMrHmleuvL | 2021-06-14T07:47:08.000Z | PM_80_30_80 | Staff cost information | [List] | TRUE | PM_80_30_80 : Staff cost information | PM_80_30_80 : Staff cost information | Project Management | recmIfsPMrHmleuvL
recKR5bLzmFvQ2nlE | 2021-06-14T07:47:08.000Z | PM_80_30_90 | Utilities cost information | [List] | TRUE | PM_80_30_90 : Utilities cost information | PM_80_30_90 : Utilities cost information | Project Management | recKR5bLzmFvQ2nlE
recCqVutuAbXo2lOD | 2021-06-14T07:47:08.000Z | PM_80_30_96 | Written scheme of examination information | [List] | TRUE | PM_80_30_96 : Written scheme of examination information | PM_80_30_96 : Written scheme of examination information | Project Management | recCqVutuAbXo2lOD
recDP86eXxQuwgfzt | 2022-01-28T12:20:29.000Z | PM_80_40 | Personnel training information | [List] | TRUE | PM_80_40 : Personnel training information | PM_80_40 : Personnel training information | Project Management | recDP86eXxQuwgfzt
recWLXhHL11uvtqpz | 2022-01-28T12:20:29.000Z | PM_80_40_36 | High-voltage systems operator training certificate | [List] | TRUE | PM_80_40_36 : High-voltage systems operator training certificate | PM_80_40_36 : High-voltage systems operator training certificate | Project Management | recWLXhHL11uvtqpz
recFpvF7ro9RXFpzj | 2021-06-14T07:47:08.000Z | PM_80_50 | Emergency strategy information | [List] | TRUE | PM_80_50 : Emergency strategy information | PM_80_50 : Emergency strategy information | Project Management | recFpvF7ro9RXFpzj
reci5KRh544los2fo | 2021-06-14T07:47:08.000Z | PM_80_50_20 | Disaster recovery strategy | [List] | TRUE | PM_80_50_20 : Disaster recovery strategy | PM_80_50_20 : Disaster recovery strategy | Project Management | reci5KRh544los2fo
recv59uTR6bySWnVz | 2021-06-14T07:47:08.000Z | PM_80_50_25 | Disaster response strategy | [List] | TRUE | PM_80_50_25 : Disaster response strategy | PM_80_50_25 : Disaster response strategy | Project Management | recv59uTR6bySWnVz
recyQodeTD48V35tj | 2021-11-11T11:10:56.000Z | PM_80_50_27 | Emergency response packs | [List] | TRUE | PM_80_50_27 : Emergency response packs | PM_80_50_27 : Emergency response packs | Project Management | recyQodeTD48V35tj
rechRojbjALlqYAJ3 | 2021-06-14T07:47:08.000Z | PM_80_50_30 | Fire evacuation strategy | [List] | TRUE | PM_80_50_30 : Fire evacuation strategy | PM_80_50_30 : Fire evacuation strategy | Project Management | rechRojbjALlqYAJ3
recVJ8RPd1A6XgoWE | 2021-06-14T07:47:08.000Z | PM_80_50_80 | Security strategy | [List] | TRUE | PM_80_50_80 : Security strategy | PM_80_50_80 : Security strategy | Project Management | recVJ8RPd1A6XgoWE
recLTT6TeKrIH4oUw | 2021-06-14T07:47:08.000Z | PM_80_60 | Asset risk management information | [List] | TRUE | PM_80_60 : Asset risk management information | PM_80_60 : Asset risk management information | Project Management | recLTT6TeKrIH4oUw
recTrcFXgFwtAIY84 | 2021-11-11T11:10:56.000Z | PM_80_60_12 | Change of risk information | [List] | TRUE | PM_80_60_12 : Change of risk information | PM_80_60_12 : Change of risk information | Project Management | recTrcFXgFwtAIY84
recYGFfA2WBuLv8lE | 2021-06-14T07:47:08.000Z | PM_80_60_15 | Compliance risk management information | [List] | TRUE | PM_80_60_15 : Compliance risk management information | PM_80_60_15 : Compliance risk management information | Project Management | recYGFfA2WBuLv8lE
recDJxjP74ZGAcFZj | 2021-06-14T07:47:08.000Z | PM_80_60_30 | Financial risk management information | [List] | TRUE | PM_80_60_30 : Financial risk management information | PM_80_60_30 : Financial risk management information | Project Management | recDJxjP74ZGAcFZj
recYoiz8TgbPq55tx | 2022-01-28T12:20:29.000Z | PM_80_60_31 | Fire risk assessment information | [List] | TRUE | PM_80_60_31 : Fire risk assessment information | PM_80_60_31 : Fire risk assessment information | Project Management | recYoiz8TgbPq55tx
recyw8l0BLXZJHgie | 2021-11-11T11:10:56.000Z | PM_80_60_32 | Flood risk management information | [List] | TRUE | PM_80_60_32 : Flood risk management information | PM_80_60_32 : Flood risk management information | Project Management | recyw8l0BLXZJHgie
rec7d2PqAR2MhAl1Y | 2021-06-14T07:47:08.000Z | PM_80_60_50 | Health and safety risk management information | [List] | TRUE | PM_80_60_50 : Health and safety risk management information | PM_80_60_50 : Health and safety risk management information | Project Management | rec7d2PqAR2MhAl1Y
recPRSmwaSJnH3OXu | 2021-11-11T11:10:56.000Z | PM_80_60_56 | Natural flood risk management information | [List] | TRUE | PM_80_60_56 : Natural flood risk management information | PM_80_60_56 : Natural flood risk management information | Project Management | recPRSmwaSJnH3OXu
reccBAvxnCsf2GrrJ | 2021-06-14T07:47:08.000Z | PM_80_60_60 | Operational risk management information | [List] | TRUE | PM_80_60_60 : Operational risk management information | PM_80_60_60 : Operational risk management information | Project Management | reccBAvxnCsf2GrrJ
recQCBoggQ8jKsx6e | 2021-06-14T07:47:08.000Z | PM_80_60_65 | Performance risk management information | [List] | TRUE | PM_80_60_65 : Performance risk management information | PM_80_60_65 : Performance risk management information | Project Management | recQCBoggQ8jKsx6e
recfCwZ33for95wPE | 2021-06-14T07:47:08.000Z | PM_80_60_68 | Public safety risk management information | [List] | TRUE | PM_80_60_68 : Public safety risk management information | PM_80_60_68 : Public safety risk management information | Project Management | recfCwZ33for95wPE
recQi6ejAcRUuLqiJ | 2021-06-14T07:47:08.000Z | PM_80_60_70 | Residual risk information | [List] | TRUE | PM_80_60_70 : Residual risk information | PM_80_60_70 : Residual risk information | Project Management | recQi6ejAcRUuLqiJ

## Ef Classification
Name | Code | Table | Uniclass | ID | Title | Version | Current | Roles | Roles 2 | NRM 2 | Code updated - updated record here | CIBSE | Levels | Level 1 | Level 1 Formula | Level 2 Formula | Level 3 Formula | Level 2 | Level 3 | Level 4 Split | Level 3 Split | Level 2 Split | Level 1 Split
EF_15 : Earthworks and remediation | EF_15 | Elements and Functions | EF_15 : Earthworks and remediation | recD2hhw6jUntJ8wZ | Earthworks and remediation | 1.1 | checked | [5 empty] | 1 | [9 empty] | EF_15
EF_15_10 : Groundworks and earthworks | EF_15_10 | Elements and Functions | EF_15_10 : Groundworks and earthworks | recfMjiX4xmO8fsxD | Groundworks and earthworks | 1.1 | checked | [5 empty] | 2 | EF_15 : Earthworks and remediation | EF_15 | [6 empty] | EF_15_10
EF_15_30 : Remediation, repair and renovation | EF_15_30 | Elements and Functions | EF_15_30 : Remediation, repair and renovation | recRnkI6fikZdxyYH | Remediation, repair and renovation | 1.1 | checked | [5 empty] | 2 | EF_15 : Earthworks and remediation | EF_15 | [6 empty] | EF_15_30
EF_20 : Structural elements | EF_20 | Elements and Functions | EF_20 : Structural elements | recUOvj8QWppufSwN | Structural elements | 1.10,1.9 | checked | [5 empty] | 1 | [9 empty] | EF_20
EF_20_05 : Substructure | EF_20_05 | Elements and Functions | EF_20_05 : Substructure | recObGiWydduE1iFF | Substructure | 1.10,1.9 | checked | [5 empty] | 2 | EF_20 : Structural elements | EF_20 | [6 empty] | EF_20_05
EF_20_05_30 : Foundations | EF_20_05_30 | Elements and Functions | EF_20_05_30 : Foundations | recWPFJHyVjrYlFXX | Foundations | 1.10,1.9 | checked | [5 empty] | 3 | EF_20 : Structural elements | EF_20 | EF_20_05 |  | EF_20_05 : Substructure |  |  | EF_20_05_30
EF_20_10 : Superstructure | EF_20_10 | Elements and Functions | EF_20_10 : Superstructure | recRM27iOPh5fWJvo | Superstructure | 1.10,1.9 | checked | [5 empty] | 2 | EF_20 : Structural elements | EF_20 | [6 empty] | EF_20_10
EF_20_10_15 : Composite structures | EF_20_10_15 | Elements and Functions | EF_20_10_15 : Composite structures | rec088bRfWcTdGVzz | Composite structures | 1.10,1.9 | checked | [5 empty] | 3 | EF_20 : Structural elements | EF_20 | EF_20_10 |  | EF_20_10 : Superstructure |  |  | EF_20_10_15
EF_20_10_30 : Framed structures | EF_20_10_30 | Elements and Functions | EF_20_10_30 : Framed structures | rec161rnJuonCMIFp | Framed structures | 1.10,1.9 | checked | [5 empty] | 3 | EF_20 : Structural elements | EF_20 | EF_20_10 |  | EF_20_10 : Superstructure |  |  | EF_20_10_30
EF_20_10_50 : Membrane structures | EF_20_10_50 | Elements and Functions | EF_20_10_50 : Membrane structures | recRx8Zxpy8aQtzdD | Membrane structures | 1.10,1.9 | checked | [5 empty] | 3 | EF_20 : Structural elements | EF_20 | EF_20_10 |  | EF_20_10 : Superstructure |  |  | EF_20_10_50
EF_20_10_75 : Shell structures | EF_20_10_75 | Elements and Functions | EF_20_10_75 : Shell structures | recQgS9vJEMYsa26L | Shell structures | 1.10,1.9 | checked | [5 empty] | 3 | EF_20 : Structural elements | EF_20 | EF_20_10 |  | EF_20_10 : Superstructure |  |  | EF_20_10_75
EF_20_10_80 : Solid structures | EF_20_10_80 | Elements and Functions | EF_20_10_80 : Solid structures | recrcOVZGBqj2P4Ex | Solid structures | 1.10,1.9 | checked | [5 empty] | 3 | EF_20 : Structural elements | EF_20 | EF_20_10 |  | EF_20_10 : Superstructure |  |  | EF_20_10_80
EF_20_50 : Bridge structures | EF_20_50 | Elements and Functions | EF_20_50 : Bridge structures | rec2jME5PolSpk2MX | Bridge structures | 1.10,1.9 | checked | [5 empty] | 2 | EF_20 : Structural elements | EF_20 | [6 empty] | EF_20_50
EF_20_50_01 : Abutments | EF_20_50_01 | Elements and Functions | EF_20_50_01 : Abutments | rec7z618pZPMk6tGs | Abutments | 1.10,1.9 | checked | [5 empty] | 3 | EF_20 : Structural elements | EF_20 | EF_20_50 |  | EF_20_50 : Bridge structures |  |  | EF_20_50_01
EF_20_50_07 : Bearings | EF_20_50_07 | Elements and Functions | EF_20_50_07 : Bearings | recXAdkoKK99rEjwO | Bearings | 1.10,1.9 | checked | [5 empty] | 3 | EF_20 : Structural elements | EF_20 | EF_20_50 |  | EF_20_50 : Bridge structures |  |  | EF_20_50_07
EF_20_50_10 : Bridge decks | EF_20_50_10 | Elements and Functions | EF_20_50_10 : Bridge decks | recEEK3sKUPyAhXYc | Bridge decks | 1.1 | checked | [5 empty] | 3 | EF_20 : Structural elements | EF_20 | EF_20_50 |  | EF_20_50 : Bridge structures |  |  | EF_20_50_10
EF_20_50_64 : Piers | EF_20_50_64 | Elements and Functions | EF_20_50_64 : Piers | recwZOhwKm6bhYhej | Piers | 1.10,1.9 | checked | [5 empty] | 3 | EF_20 : Structural elements | EF_20 | EF_20_50 |  | EF_20_50 : Bridge structures |  |  | EF_20_50_64
EF_20_50_82 : Span | EF_20_50_82 | Elements and Functions | EF_20_50_82 : Span | reckeDEB4jjYQppXO | Span | 1.10,1.9 | checked | [5 empty] | 3 | EF_20 : Structural elements | EF_20 | EF_20_50 |  | EF_20_50 : Bridge structures |  |  | EF_20_50_82
EF_25 : Wall and barrier elements | EF_25 | Elements and Functions | EF_25 : Wall and barrier elements | recipWvzGKYTk2Tzl | Wall and barrier elements | 1.10,1.9 | checked | [5 empty] | 1 | [9 empty] | EF_25
EF_25_10 : Walls | EF_25_10 | Elements and Functions | EF_25_10 : Walls | receGpunArVLACyjH | Walls | 1.10,1.9 | checked | [5 empty] | 2 | EF_25 : Wall and barrier elements | EF_25 | [6 empty] | EF_25_10
EF_25_30 : Doors and windows | EF_25_30 | Elements and Functions | EF_25_30 : Doors and windows | recsZGrMlaLkW2dJZ | Doors and windows | 1.10,1.9 | checked | [5 empty] | 2 | EF_25 : Wall and barrier elements | EF_25 | [6 empty] | EF_25_30
EF_25_55 : Barriers | EF_25_55 | Elements and Functions | EF_25_55 : Barriers | recTJR5fWRPKb7cJU | Barriers | 1.10,1.9 | checked | [5 empty] | 2 | EF_25 : Wall and barrier elements | EF_25 | [6 empty] | EF_25_55
EF_30 : Roofs, floor and paving elements | EF_30 | Elements and Functions | EF_30 : Roofs, floor and paving elements | recH5Q2unOtto9MD4 | Roofs, floor and paving elements | 1.10,1.9 | checked | [5 empty] | 1 | [9 empty] | EF_30
EF_30_10 : Roofs | EF_30_10 | Elements and Functions | EF_30_10 : Roofs | recRUyo0wYUzwLwB3 | Roofs | 1.10,1.9 | checked | [5 empty] | 2 | "EF_30 : Roofs, floor and paving elements" | EF_30 | [6 empty] | EF_30_10
EF_30_20 : Floors | EF_30_20 | Elements and Functions | EF_30_20 : Floors | rec3mZRL1Zev3u9KT | Floors | 1.10,1.9 | checked | [5 empty] | 2 | "EF_30 : Roofs, floor and paving elements" | EF_30 | [6 empty] | EF_30_20
EF_30_25 : Ceilings and soffits | EF_30_25 | Elements and Functions | EF_30_25 : Ceilings and soffits | recSNF7kUHS9bImxF | Ceilings and soffits | 1.10,1.9 | checked | [5 empty] | 2 | "EF_30 : Roofs, floor and paving elements" | EF_30 | [6 empty] | EF_30_25
EF_30_30 : Decks | EF_30_30 | Elements and Functions | EF_30_30 : Decks | rec3w6FyI8OcmLUPn | Decks | 1.10,1.9 | checked | [5 empty] | 2 | "EF_30 : Roofs, floor and paving elements" | EF_30 | [6 empty] | EF_30_30
EF_30_60 : Pavements | EF_30_60 | Elements and Functions | EF_30_60 : Pavements | receU89YMnYOjaNxO | Pavements | 1.10,1.9 | checked | [5 empty] | 2 | "EF_30 : Roofs, floor and paving elements" | EF_30 | [6 empty] | EF_30_60
EF_30_60_60 : Pedestrian paving | EF_30_60_60 | Elements and Functions | EF_30_60_60 : Pedestrian paving | recTESkMg8RUKCqfu | Pedestrian paving | 1.10,1.9 | checked | [5 empty] | 3 | "EF_30 : Roofs, floor and paving elements" | EF_30 | EF_30_60 |  | EF_30_60 : Pavements |  |  | EF_30_60_60
EF_30_60_95 : Vehicular paving | EF_30_60_95 | Elements and Functions | EF_30_60_95 : Vehicular paving | recrkrg7jYMBbvirf | Vehicular paving | 1.10,1.9 | checked | [5 empty] | 3 | "EF_30 : Roofs, floor and paving elements" | EF_30 | EF_30_60 |  | EF_30_60 : Pavements |  |  | EF_30_60_95
EF_30_70 : Bridge decks | EF_30_70 | Elements and Functions | EF_30_70 : Bridge decks | recfJG28vaqgGZwNg | Bridge decks | 1.9 | [6 empty] | 2 | "EF_30 : Roofs, floor and paving elements" | EF_30 | [6 empty] | EF_30_70
EF_35 : Stairs and ramps | EF_35 | Elements and Functions | EF_35 : Stairs and ramps | recHclDUk6SMrFvP1 | Stairs and ramps | 1.10,1.9 | checked | [5 empty] | 1 | [9 empty] | EF_35
EF_35_10 : Stairs | EF_35_10 | Elements and Functions | EF_35_10 : Stairs | recnSE0lB4eN6aP94 | Stairs | 1.10,1.9 | checked | [5 empty] | 2 | EF_35 : Stairs and ramps | EF_35 | [6 empty] | EF_35_10
EF_35_10_30 : External stairs | EF_35_10_30 | Elements and Functions | EF_35_10_30 : External stairs | recNp6ffWRwOX3Qvq | External stairs | 1.10,1.9 | checked | [5 empty] | 3 | EF_35 : Stairs and ramps | EF_35 | EF_35_10 |  | EF_35_10 : Stairs |  |  | EF_35_10_30
EF_35_10_40 : Internal stairs | EF_35_10_40 | Elements and Functions | EF_35_10_40 : Internal stairs | recNunuEYbW3X9YPk | Internal stairs | 1.10,1.9 | checked | [5 empty] | 3 | EF_35 : Stairs and ramps | EF_35 | EF_35_10 |  | EF_35_10 : Stairs |  |  | EF_35_10_40
EF_35_20 : Ramps | EF_35_20 | Elements and Functions | EF_35_20 : Ramps | recaLC2rP13ZtfXYg | Ramps | 1.10,1.9 | checked | [5 empty] | 2 | EF_35 : Stairs and ramps | EF_35 | [6 empty] | EF_35_20
EF_35_20_30 : External ramps | EF_35_20_30 | Elements and Functions | EF_35_20_30 : External ramps | recicWxUTCqTGT0SW | External ramps | 1.10,1.9 | checked | [5 empty] | 3 | EF_35 : Stairs and ramps | EF_35 | EF_35_20 |  | EF_35_20 : Ramps |  |  | EF_35_20_30
EF_35_20_40 : Internal ramps | EF_35_20_40 | Elements and Functions | EF_35_20_40 : Internal ramps | recYgCqRaSFBVNMj2 | Internal ramps | 1.10,1.9 | checked | [5 empty] | 3 | EF_35 : Stairs and ramps | EF_35 | EF_35_20 |  | EF_35_20 : Ramps |  |  | EF_35_20_40
EF_37 : Tunnel, vessel and tower elements | EF_37 | Elements and Functions | EF_37 : Tunnel, vessel and tower elements | recFZX36JqDzkDmse | Tunnel, vessel and tower elements | 1.10,1.9 | checked | [5 empty] | 1 | [9 empty] | EF_37
EF_37_16 : Vessels and trenches | EF_37_16 | Elements and Functions | EF_37_16 : Vessels and trenches | recjtMutdd8SNgGu2 | Vessels and trenches | 1.10,1.9 | checked | [5 empty] | 2 | "EF_37 : Tunnel, vessel and tower elements" | EF_37 | [6 empty] | EF_37_16
EF_37_16_90 : Trenches | EF_37_16_90 | Elements and Functions | EF_37_16_90 : Trenches | recpVyaEFbUiW8Ggi | Trenches | 1.10,1.9 | checked | [5 empty] | 3 | "EF_37 : Tunnel, vessel and tower elements" | EF_37 | EF_37_16 |  | EF_37_16 : Vessels and trenches |  |  | EF_37_16_90
EF_37_16_94 : Vessels | EF_37_16_94 | Elements and Functions | EF_37_16_94 : Vessels | recDFZu9ExyZCN3Rg | Vessels | 1.10,1.9 | checked | [5 empty] | 3 | "EF_37 : Tunnel, vessel and tower elements" | EF_37 | EF_37_16 |  | EF_37_16 : Vessels and trenches |  |  | EF_37_16_94
EF_37_17 : Towers, chimneys and masts | EF_37_17 | Elements and Functions | EF_37_17 : Towers, chimneys and masts | recLc9UzA4x6J1scJ | Towers, chimneys and masts | 1.10,1.9 | checked | [5 empty] | 2 | "EF_37 : Tunnel, vessel and tower elements" | EF_37 | [6 empty] | EF_37_17
EF_37_17_15 : Chimneys | EF_37_17_15 | Elements and Functions | EF_37_17_15 : Chimneys | recIEEmHY3l1Ngsbz | Chimneys | 1.10,1.9 | checked | [5 empty] | 3 | "EF_37 : Tunnel, vessel and tower elements" | EF_37 | EF_37_17 |  | "EF_37_17 : Towers, chimneys and masts" |  |  | EF_37_17_15
EF_37_17_35 : Gantries | EF_37_17_35 | Elements and Functions | EF_37_17_35 : Gantries | recJrVkIoCVfN9NY7 | Gantries | 1.10,1.9 | checked | [5 empty] | 3 | "EF_37 : Tunnel, vessel and tower elements" | EF_37 | EF_37_17 |  | "EF_37_17 : Towers, chimneys and masts" |  |  | EF_37_17_35
EF_37_17_50 : Masts | EF_37_17_50 | Elements and Functions | EF_37_17_50 : Masts | recW9P6kAhey8aN1a | Masts | 1.10,1.9 | checked | [5 empty] | 3 | "EF_37 : Tunnel, vessel and tower elements" | EF_37 | EF_37_17 |  | "EF_37_17 : Towers, chimneys and masts" |  |  | EF_37_17_50
EF_37_17_70 : Pylons | EF_37_17_70 | Elements and Functions | EF_37_17_70 : Pylons | recpBfHTz5qjtik6e | Pylons | 1.10,1.9 | checked | [5 empty] | 3 | "EF_37 : Tunnel, vessel and tower elements" | EF_37 | EF_37_17 |  | "EF_37_17 : Towers, chimneys and masts" |  |  | EF_37_17_70
EF_37_17_90 : Towers | EF_37_17_90 | Elements and Functions | EF_37_17_90 : Towers | rec7jYjt2SyBgcqOS | Towers | 1.10,1.9 | checked | [5 empty] | 3 | "EF_37 : Tunnel, vessel and tower elements" | EF_37 | EF_37_17 |  | "EF_37_17 : Towers, chimneys and masts" |  |  | EF_37_17_90
EF_37_50 : Tunnels and shafts | EF_37_50 | Elements and Functions | EF_37_50 : Tunnels and shafts | recmx5xWmKNIKyf0l | Tunnels and shafts | 1.10,1.9 | checked | [5 empty] | 2 | "EF_37 : Tunnel, vessel and tower elements" | EF_37 | [6 empty] | EF_37_50
EF_40 : Signage, fittings, furnishings and equipment | EF_40 | Elements and Functions | EF_40 : Signage, fittings, furnishings and equipment | recGwJXXtsMrZ871K | Signage, fittings, furnishings and equipment | 1.10,1.9 | checked | [5 empty] | 1 | [9 empty] | EF_40
EF_40_10 : Signage | EF_40_10 | Elements and Functions | EF_40_10 : Signage | rec4McQ09I3vFGSs3 | Signage | 1.10,1.9 | checked | [5 empty] | 2 | "EF_40 : Signage, fittings, furnishings and equipment" | EF_40 | [6 empty] | EF_40_10
EF_40_20 : Fittings | EF_40_20 | Elements and Functions | EF_40_20 : Fittings | recHXiMMJoEDDECg7 | Fittings | 1.10,1.9 | checked | [5 empty] | 2 | "EF_40 : Signage, fittings, furnishings and equipment" | EF_40 | [6 empty] | EF_40_20
EF_40_30 : Furnishings | EF_40_30 | Elements and Functions | EF_40_30 : Furnishings | recDYXkDo364snDp0 | Furnishings | 1.10,1.9 | checked | [5 empty] | 2 | "EF_40 : Signage, fittings, furnishings and equipment" | EF_40 | [6 empty] | EF_40_30
EF_40_40 : Equipment | EF_40_40 | Elements and Functions | EF_40_40 : Equipment | rec3BCYYDZCujH7GT | Equipment | 1.10,1.9 | checked | [5 empty] | 2 | "EF_40 : Signage, fittings, furnishings and equipment" | EF_40 | [6 empty] | EF_40_40
EF_45 : Flora and fauna elements | EF_45 | Elements and Functions | EF_45 : Flora and fauna elements | recxS0Mp8csvs0sl5 | Flora and fauna elements | 1.10,1.9 | checked | [5 empty] | 1 | [9 empty] | EF_45
EF_45_03 : Aquatic fauna elements | EF_45_03 | Elements and Functions | EF_45_03 : Aquatic fauna elements | recWAiHA6qs40sMD2 | Aquatic fauna elements | 1.10,1.9 | checked | [5 empty] | 2 | EF_45 : Flora and fauna elements | EF_45 | [6 empty] | EF_45_03
EF_45_05 : Aquatic flora elements | EF_45_05 | Elements and Functions | EF_45_05 : Aquatic flora elements | recFH0F6IB8a6xLEA | Aquatic flora elements | 1.10,1.9 | checked | [5 empty] | 2 | EF_45 : Flora and fauna elements | EF_45 | [6 empty] | EF_45_05
EF_45_20 : Grass and meadow elements | EF_45_20 | Elements and Functions | EF_45_20 : Grass and meadow elements | recPvlvlr4n9Cxk6x | Grass and meadow elements | 1.10,1.9 | checked | [5 empty] | 2 | EF_45 : Flora and fauna elements | EF_45 | [6 empty] | EF_45_20
EF_45_45 : Land fauna elements | EF_45_45 | Elements and Functions | EF_45_45 : Land fauna elements | recDWcAhfUHJNBPLz | Land fauna elements | 1.10,1.9 | checked | [5 empty] | 2 | EF_45 : Flora and fauna elements | EF_45 | [6 empty] | EF_45_45
EF_45_90 : Tree, shrub and herbaceous plant elements | EF_45_90 | Elements and Functions | EF_45_90 : Tree, shrub and herbaceous plant elements | recUpdsDzlQxGChed | Tree, shrub and herbaceous plant elements | 1.10,1.9 | checked | [5 empty] | 2 | EF_45 : Flora and fauna elements | EF_45 | [6 empty] | EF_45_90
EF_50 : Waste disposal functions | EF_50 | Elements and Functions | EF_50 : Waste disposal functions | rec9JAXnXDFJW26vx | Waste disposal functions | 1.10,1.9 | checked | [5 empty] | 1 | [9 empty] | EF_50
EF_50_10 : Gas waste collection | EF_50_10 | Elements and Functions | EF_50_10 : Gas waste collection | recHAC3q1UGnMbKa4 | Gas waste collection | 1.10,1.9 | checked | [5 empty] | 2 | EF_50 : Waste disposal functions | EF_50 | [6 empty] | EF_50_10
EF_50_20 : Wet waste collection | EF_50_20 | Elements and Functions | EF_50_20 : Wet waste collection | recs4nlpQk3YMcoa3 | Wet waste collection | 1.10,1.9 | checked | [5 empty] | 2 | EF_50 : Waste disposal functions | EF_50 | [6 empty] | EF_50_20
EF_50_30 : Above-ground drainage collection | EF_50_30 | Elements and Functions | EF_50_30 : Above-ground drainage collection | recxs9xf3ErinYoA3 | Above-ground drainage collection | 1.10,1.9 | checked | [5 empty] | 2 | EF_50 : Waste disposal functions | EF_50 | [6 empty] | EF_50_30
EF_50_35 : Below-ground drainage collection | EF_50_35 | Elements and Functions | EF_50_35 : Below-ground drainage collection | rec0v0h8kre7j5SY5 | Below-ground drainage collection | 1.10,1.9 | checked | [5 empty] | 2 | EF_50 : Waste disposal functions | EF_50 | [6 empty] | EF_50_35
EF_50_40 : Dry waste collection | EF_50_40 | Elements and Functions | EF_50_40 : Dry waste collection | rec3fxRrpjzu2srJa | Dry waste collection | 1.10,1.9 | checked | [5 empty] | 2 | EF_50 : Waste disposal functions | EF_50 | [6 empty] | EF_50_40
EF_50_50 : Gas waste treatment and disposal | EF_50_50 | Elements and Functions | EF_50_50 : Gas waste treatment and disposal | recCOlma9Cas4RWJU | Gas waste treatment and disposal | 1.10,1.9 | checked | [5 empty] | 2 | EF_50 : Waste disposal functions | EF_50 | [6 empty] | EF_50_50
EF_50_60 : Wet waste treatment and disposal | EF_50_60 | Elements and Functions | EF_50_60 : Wet waste treatment and disposal | recoYst79QEqa9Er4 | Wet waste treatment and disposal | 1.10,1.9 | checked | [5 empty] | 2 | EF_50 : Waste disposal functions | EF_50 | [6 empty] | EF_50_60
EF_50_70 : Drainage treatment and disposal | EF_50_70 | Elements and Functions | EF_50_70 : Drainage treatment and disposal | recgkYTmGvTsgriwW | Drainage treatment and disposal | 1.10,1.9 | checked | [5 empty] | 2 | EF_50 : Waste disposal functions | EF_50 | [6 empty] | EF_50_70
EF_50_75 : Wastewater treatment and disposal | EF_50_75 | Elements and Functions | EF_50_75 : Wastewater treatment and disposal | recmyYg4yeIjgLyoS | Wastewater treatment and disposal | 1.10,1.9 | checked | [5 empty] | 2 | EF_50 : Waste disposal functions | EF_50 | [6 empty] | EF_50_75
EF_50_80 : Dry waste treatment and disposal | EF_50_80 | Elements and Functions | EF_50_80 : Dry waste treatment and disposal | recLHdBQGye4JMzgU | Dry waste treatment and disposal | 1.10,1.9 | checked | [5 empty] | 2 | EF_50 : Waste disposal functions | EF_50 | [6 empty] | EF_50_80
EF_55 : Piped supply functions | EF_55 | Elements and Functions | EF_55 : Piped supply functions | recogyVS3ZxM4u928 | Piped supply functions | 1.10,1.9 | checked | [5 empty] | 1 | [9 empty] | EF_55
EF_55_05 : Gas extraction and treatment | EF_55_05 | Elements and Functions | EF_55_05 : Gas extraction and treatment | recxQt8v5oT5lVYij | Gas extraction and treatment | 1.10,1.9 | checked | [5 empty] | 2 | EF_55 : Piped supply functions | EF_55 | [6 empty] | EF_55_05
EF_55_10 : Liquid fuel extraction and treatment | EF_55_10 | Elements and Functions | EF_55_10 : Liquid fuel extraction and treatment | recGY2l8UQ4b5aPim | Liquid fuel extraction and treatment | 1.10,1.9 | checked | [5 empty] | 2 | EF_55 : Piped supply functions | EF_55 | [6 empty] | EF_55_10
EF_55_15 : Water extraction and treatment | EF_55_15 | Elements and Functions | EF_55_15 : Water extraction and treatment | recEZekyPcp7jJVSG | Water extraction and treatment | 1.10,1.9 | checked | [5 empty] | 2 | EF_55 : Piped supply functions | EF_55 | [6 empty] | EF_55_15
EF_55_20 : Gas supply | EF_55_20 | Elements and Functions | EF_55_20 : Gas supply | recDhdAU8oXGFzMQ7 | Gas supply | 1.10,1.9 | checked | [5 empty] | 2 | EF_55 : Piped supply functions | EF_55 | [6 empty] | EF_55_20
EF_55_30 : Fire-extinguishing supply | EF_55_30 | Elements and Functions | EF_55_30 : Fire-extinguishing supply | recYX1OKSYHly52ZP | Fire-extinguishing supply | 1.10,1.9 | checked | [5 empty] | 2 | EF_55 : Piped supply functions | EF_55 | [6 empty] | EF_55_30
EF_55_40 : Steam supply | EF_55_40 | Elements and Functions | EF_55_40 : Steam supply | recBKReRLKadAK6Hb | Steam supply | 1.10,1.9 | checked | [5 empty] | 2 | EF_55 : Piped supply functions | EF_55 | [6 empty] | EF_55_40
EF_55_50 : Liquid fuel supply | EF_55_50 | Elements and Functions | EF_55_50 : Liquid fuel supply | recEp275BX6gNUaHJ | Liquid fuel supply | 1.10,1.9 | checked | [5 empty] | 2 | EF_55 : Piped supply functions | EF_55 | [6 empty] | EF_55_50
EF_55_60 : Process liquid supply | EF_55_60 | Elements and Functions | EF_55_60 : Process liquid supply | recZkyc7hrK2IBIti | Process liquid supply | 1.10,1.9 | checked | [5 empty] | 2 | EF_55 : Piped supply functions | EF_55 | [6 empty] | EF_55_60
EF_55_70 : Water supply | EF_55_70 | Elements and Functions | EF_55_70 : Water supply | recM6hOfQBsW9mLXg | Water supply | 1.10,1.9 | checked | [5 empty] | 2 | EF_55 : Piped supply functions | EF_55 | [6 empty] | EF_55_70
EF_55_90 : Piped solids supply | EF_55_90 | Elements and Functions | EF_55_90 : Piped solids supply | reciFD0uDXIkMUDEH | Piped solids supply | 1.10,1.9 | checked | [5 empty] | 2 | EF_55 : Piped supply functions | EF_55 | [6 empty] | EF_55_90
EF_60 : Heating, cooling and refrigeration functions | EF_60 | Elements and Functions | EF_60 : Heating, cooling and refrigeration functions | recEbE9bIBExkOFPE | Heating, cooling and refrigeration functions | 1.10,1.9 | checked | [5 empty] | 1 | [9 empty] | EF_60
EF_60_30 : Rail and paving heating | EF_60_30 | Elements and Functions | EF_60_30 : Rail and paving heating | recJjSk4R3Tf3JWQx | Rail and paving heating | 1.10,1.9 | checked | [5 empty] | 2 | "EF_60 : Heating, cooling and refrigeration functions" | EF_60 | [6 empty] | EF_60_30
EF_60_40 : Space heating and cooling | EF_60_40 | Elements and Functions | EF_60_40 : Space heating and cooling | rec82pR4ssJsMKQ7L | Space heating and cooling | 1.10,1.9 | checked | [5 empty] | 2 | "EF_60 : Heating, cooling and refrigeration functions" | EF_60 | [6 empty] | EF_60_40
EF_60_60 : Refrigeration | EF_60_60 | Elements and Functions | EF_60_60 : Refrigeration | recZ0mQKYe8wruC3Z | Refrigeration | 1.10,1.9 | checked | [5 empty] | 2 | "EF_60 : Heating, cooling and refrigeration functions" | EF_60 | [6 empty] | EF_60_60
EF_60_80 : Drying | EF_60_80 | Elements and Functions | EF_60_80 : Drying | recgMDZtE1bF7ejZn | Drying | 1.10,1.9 | checked | [5 empty] | 2 | "EF_60 : Heating, cooling and refrigeration functions" | EF_60 | [6 empty] | EF_60_80
EF_65 : Ventilation and air conditioning functions | EF_65 | Elements and Functions | EF_65 : Ventilation and air conditioning functions | recfjUhUDCdBfBi7M | Ventilation and air conditioning functions | 1.10,1.9 | checked | [5 empty] | 1 | [9 empty] | EF_65
EF_65_40 : Ventilation | EF_65_40 | Elements and Functions | EF_65_40 : Ventilation | rec52aVi1pUZPxN7b | Ventilation | 1.10,1.9 | checked | [5 empty] | 2 | EF_65 : Ventilation and air conditioning functions | EF_65 | [6 empty] | EF_65_40
EF_65_80 : Air conditioning | EF_65_80 | Elements and Functions | EF_65_80 : Air conditioning | rec9A7P7RewHLF6FI | Air conditioning | 1.10,1.9 | checked | [5 empty] | 2 | EF_65 : Ventilation and air conditioning functions | EF_65 | [6 empty] | EF_65_80
EF_70 : Electrical power and lighting functions | EF_70 | Elements and Functions | EF_70 : Electrical power and lighting functions | rechjeQduGZ53FFfb | Electrical power and lighting functions | 1.10,1.9 | checked | [5 empty] | 1 | [9 empty] | EF_70
EF_70_10 : Electrical power generation | EF_70_10 | Elements and Functions | EF_70_10 : Electrical power generation | recdMpaNN8hk9hwEO | Electrical power generation | 1.10,1.9 | checked | [5 empty] | 2 | EF_70 : Electrical power and lighting functions | EF_70 | [6 empty] | EF_70_10
EF_70_30 : Electricity distribution and transmission | EF_70_30 | Elements and Functions | EF_70_30 : Electricity distribution and transmission | rec7Xa3H3q6awCWUt | Electricity distribution and transmission | 1.10,1.9 | checked | [5 empty] | 2 | EF_70 : Electrical power and lighting functions | EF_70 | [6 empty] | EF_70_30
EF_70_80 : Lighting | EF_70_80 | Elements and Functions | EF_70_80 : Lighting | recJk9p9yYxyEwIEA | Lighting | 1.10,1.9 | checked | [5 empty] | 2 | EF_70 : Electrical power and lighting functions | EF_70 | [6 empty] | EF_70_80
EF_75 : Communications, security, safety and protection functions | EF_75 | Elements and Functions | EF_75 : Communications, security, safety and protection functions | recRQOGE77ybNwUxn | Communications, security, safety and protection functions | 1.10,1.9 | checked | [5 empty] | 1 | [9 empty] | EF_75
EF_75_10 : Communication | EF_75_10 | Elements and Functions | EF_75_10 : Communication | rechIidR2BIBUJzj1 | Communication | 1.10,1.9 | checked | [5 empty] | 2 | "EF_75 : Communications, security, safety and protection functions" | EF_75 | [6 empty] | EF_75_10
EF_75_30 : Signalling | EF_75_30 | Elements and Functions | EF_75_30 : Signalling | recJd3u2eSjWeEXCj | Signalling | 1.10,1.9 | checked | [5 empty] | 2 | "EF_75 : Communications, security, safety and protection functions" | EF_75 | [6 empty] | EF_75_30
EF_75_40 : Security | EF_75_40 | Elements and Functions | EF_75_40 : Security | recwnK5KIZMT9R6wO | Security | 1.10,1.9 | checked | [5 empty] | 2 | "EF_75 : Communications, security, safety and protection functions" | EF_75 | [6 empty] | EF_75_40
EF_75_50 : Safety and protection | EF_75_50 | Elements and Functions | EF_75_50 : Safety and protection | recnugKvk4KuCYmYV | Safety and protection | 1.10,1.9 | checked | [5 empty] | 2 | "EF_75 : Communications, security, safety and protection functions" | EF_75 | [6 empty] | EF_75_50
EF_75_60 : Environmental safety | EF_75_60 | Elements and Functions | EF_75_60 : Environmental safety | recCtlGvuuCKbeCmG | Environmental safety | 1.10,1.9 | checked | [5 empty] | 2 | "EF_75 : Communications, security, safety and protection functions" | EF_75 | [6 empty] | EF_75_60
EF_75_70 : Control and management | EF_75_70 | Elements and Functions | EF_75_70 : Control and management | rec0ewp2hSqnJk4S0 | Control and management | 1.10,1.9 | checked | [5 empty] | 2 | "EF_75 : Communications, security, safety and protection functions" | EF_75 | [6 empty] | EF_75_70
EF_75_80 : Protection | EF_75_80 | Elements and Functions | EF_75_80 : Protection | recMAhbIgI9GASWya | Protection | 1.10,1.9 | checked | [5 empty] | 2 | "EF_75 : Communications, security, safety and protection functions" | EF_75 | [6 empty] | EF_75_80
EF_80 : Transport functions | EF_80 | Elements and Functions | EF_80 : Transport functions | recS472vbdTcNW0Iz | Transport functions | 1.10,1.9 | checked | [5 empty] | 1 | [9 empty] | EF_80
EF_80_10 : Cable transport | EF_80_10 | Elements and Functions | EF_80_10 : Cable transport | recrffIW4knIstgHz | Cable transport | 1.10,1.9 | checked | [5 empty] | 2 | EF_80 : Transport functions | EF_80 | [6 empty] | EF_80_10
EF_80_20 : Conveyors | EF_80_20 | Elements and Functions | EF_80_20 : Conveyors | rec90xgZrxKQVVexF | Conveyors | 1.10,1.9 | checked | [5 empty] | 2 | EF_80 : Transport functions | EF_80 | [6 empty] | EF_80_20
EF_80_30 : Cranes and hoists | EF_80_30 | Elements and Functions | EF_80_30 : Cranes and hoists | recLIXVLA9Ycxopbg | Cranes and hoists | 1.10,1.9 | checked | [5 empty] | 2 | EF_80 : Transport functions | EF_80 | [6 empty] | EF_80_30
EF_80_50 : Lifts | EF_80_50 | Elements and Functions | EF_80_50 : Lifts | recrjKALsa33r2D2J | Lifts | 1.10,1.9 | checked | [5 empty] | 2 | EF_80 : Transport functions | EF_80 | [6 empty] | EF_80_50
EF_80_70 : Rail tracks | EF_80_70 | Elements and Functions | EF_80_70 : Rail tracks | recqj71fXuY715Dja | Rail tracks | 1.10,1.9 | checked | [5 empty] | 2 | EF_80 : Transport functions | EF_80 | [6 empty] | EF_80_70